Carl Williams – Weekend 050305_v3.0


Sign Off Draft – includes PIR/As Fitted Report 

Plan for: Weekend 5th March 2005  - Work Co-ordinator: Carl Williams

Consisting of 3 Items
Item1: Items brought forward from previous installations – Covered by change control numbers:

1-1: No Items to be brought forward

Item co-ordinator: Javed Dad

Item2: Break/Fix snagging - Covered by: 

2-1: VT: 1909480 - Cabling tidy up of RED fabric cabinets in RDC

2-2: VT: 1911911 – Resolution of SYM ACL Issue
Item co-ordinator: Javed Dad

Item3: ISL Remediation – Covered by Change request 05433864

Remediation of various ISL’s – Moves/Additions/Subtractions – RDC/CGC 

Item co-ordinator: Carl Williams

Locations:
TR1/TR2

CGC2 3rd floor

RDC 1st floor

Conference Call Number: 0207 986 7934 (pin 7934)
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Version Control

	Date
	Version
	Reason for Change

	24/02/2005
	050305_v0.1

CPW
	1st Draft

	01/03/2005
	050302_v0.2

CPW
	2nd Draft for 14:00 Meeting

	02/03/2005
	050305_v0.3

CPW
	Changes highlighted in the 14:00 meeting – Addition of Item 2-2 SYMACL, Appendix’s F & G, and Issues found table – typo corrections

	02/03/2005
	050305_v0.4

CPW
	Removal of 2 lines in appendix’s C / D / E / F – No additional ISL will be installed.

	04/03/2005
	050305_1.0

CPW
	Pre-installation draft – No changes from v0.4

	05/03/2005
	050305_2.0

CPW
	PIR/Wash up draft

	07/03/2005
	050305_3.0

CPW
	Sign off draft


PIR/As fitted report

All activities completed.

Only issue was with the SYM ACL open case – The arrays would not accept the suggested Syntax for the host names – Tech support contacted. – Syntax changed as a work around – issue resolved
Wash up

Present: GB, CPW, JD, and PC

Time 18:00 - 03rd March 2005

The wash-up took place by telephone conference and the ’sign of’ and issues tables were accepted as a true record of the actions resultant from the installation plan.

Carl Williams

Work Coordinator SAN Installations 05/03/2005
Issues Found

Log of issues found during weekend activities

	ITEM/SECTION NUMBER
	ISSUE
	FOLLOW UP ACTION / RESOLUTION

	 2-2
	SYMMS did not accept the suggested syntax of the

Hostnames – Tech support contacted 
	Syntax changed – This partially fixed the issue

	 
	 
	 

	 
	 
	 

	 
	 
	 

	 
	 
	 

	 
	 
	 


Documentation Changes

Changes to be reflected in the documentation after successful completion of the whole of this work plan are as follows:

The following ports will be left unblocked:
	Switch
	Port

	Switch01R
	50

	Switch11R
	50

	Switch01C 
	33

	Switch01C 
	61

	Switch13C
	96

	Switch15C
	66


Documentation Changes (continued)

The following ports will be left blocked:

	Switch
	Port

	Switch01R
	63

	Switch11R
	63

	Switch01C
	01

	Switch01C
	30

	Switch9C
	0

	Switch11C
	42

	Switch13C
	63

	Switch15C
	63


The following ports will changed

	Switch
	Port
	To
	Switch
	Port

	
	
	
	
	

	
	
	
	
	


	Documentation update Sign Off: 2 Pages – To be returned to BAU on completion

Member of: BAU 

NAME: Javed Dad

Date: 07/03/2005____


Overview of All Weekend Work

Item1: Issues brought forward that require weekend activity.

0 Items brought forward that require weekend activity – please see Item1 for full details

Item2: Break/Fix Snagging

2 Items requires weekend activity – please see Item2 for full details

Item3: ISL remediation

This is the first of a 2 stage weekend activity to remediate Incorrect ISL configurations – This involves moved, additions and subtractions of ISL’s. 

Required Resource 

Resources presence required: 

ALL RESOURCE IS UNCONFIRMED

	MEMBER OF
	CGC RESOURCE
	RDC RESOURCE

	EMC CE
	Patrick Caborn
	Patrick Caborn

	OLIVER CABLING
	Carl Williams
	Paolo Sidoli

	BUSINESS AS USUAL (Primary)
	Javed Dad
	Javed Dad

	BUSINESS AS USUAL (Secondary)
	David Coles
	David Coles

	Work Co-ordinator
	Carl Williams
	Carl Williams

	EMC Project Manager
	Gary Battersby
	Gary Battersby

	EMC SAM
	Paul Belcher
	Paul Belcher


This document is to be used as a complement of the official project document and not as substitute.

Over All Sign Off

	Item
	Status
	Owner
	Sign off



	Item 1: Items brought forward from previous installations
	No Items brought forward
	BAU – Javed Dad
	JD

	Item 2: Break/Fix Snagging
	
	BAU – Javed Dad  / Carl Williams
	JD/CPW



	Item 3: ISL remediation
	
	BAU – Carl Williams
	CPW


	Overall Sign Off: 1 Page – To be returned to BAU on completion

Member of: BAU 

NAME: Javed Dad

Date: 07/03/2005____


Item 1: Items brought forward from previous installations

0 ITEMS BROUGHT FORWARD

	Item  number
	Reference
	Description
	Prerequisites
	Comments
	Resolution

	1-1
	
	
	
	
	


	Item1 Sign Off: 1 Page – To be returned to BAU on completion

Member of: BAU 

NAME: Javed Dad

Date: 07/03/2005____


Item 2: Break/Fix Snagging

	Item Number
	VT/EMC/ARTS

Reference
	Description
	Comments
	Resolution

	2-1
	VT: 1909480
	This is to cover Oliver cabling house keeping task of removing un-connected patches in the RED fabric cabinets in RDC1
	Paolo contacted conference line @13:00 – 

Task complete @ 15:00
	Complete – Signed by CPW

	2-2
	VT: 1911911 EMC² case No. 12522318.
	SYMACL remediation  - Entries need to be added to the following arrays as per appendix G

CGC
3C  (1078)

5C  (0129)

7C  (0122)

11C (0298) 

RDC
3R  (1079)

5R  (0107)

7R  (0200)

11R (0293)
	Patrick contacted conference line @14:00 – 

Patrick encountered problems with the host name syntax, contacted Tech support.

Task 87% complete 06/03/2005
	87% Complete – No access to Symm 11R – PC to follow up and complete.


	Item2 Sign Off: 1 Page – To be returned to BAU on completion

Member of: BAU 

NAME: Javed Dad

Date: 07/03/2005____


Item 3: ISL Remediation

Work number: 050305-1

Change control number: 05433864

Item co-ordinator: Carl Williams

Date: 

5th March 2005

Location: RDC1 / CGC1 / CGC2

Start Time: 14:00 – 05/03/2005

Compulsory back-out time: 08:00 – 06/03/2005

Compulsory Completion time: 17:59 - 06/03/2005
Applicable Appendix’s: C / D / E / F

Conference Call Number: 0207 986 7934 (pin 7934)

Item 3: Section Checklist

ISL remediation

	Section
	Details
	Comments
	Sign Off

	3-1
	Pre-requisites checks.
	 Complete as per plan
	CPW

	3-2
	ISL remediation
	 Complete as per plan
	CPW

 

	3-3
	Post checks.
	Complete as per plan
	CPW

	3-4
	Back out plan
	Not required
	

	Item 3 completion Sign Off: 1 page To be returned to BAU on completion.

Member of: BAU______ NAME: Carl Williams_________________ Date: 07/03/2005




Section 3-1: Pre-requisites checks
	Step
	Time
	Owner
	Details
	Comment
	Date Due

	1
	Before starting:

5th of March 2005
	BAU
	BAU will ensure correct change control is raised for the weekend work
	Complete # 05433864
	01/03/2005 – 12:00

Complete

	2
	
	BAU
	BAU will check the change control has not been rejected
	
	01/03/2005 – 13:30

Complete

	3
	
	BAU
	BAU will check the change control has been approved.
	If not approved email/call approvals group to ensue approval before 12:00
	03/03/2005 – 10:30

	4
	Before starting:

5th of March 2005
	BAU
	BAU will ensure the Access request is submitted to DCSM for entry into the data centers and associated vendor storerooms.
	Access request #  - If access problems delay entry for over 20 minutes - Please escalate to work co-ordinator, and this can THEN be escalated to DCSM.
	03/03/2005 – 15:00 – Not required as on site presence has permanent access.

	5
	Before starting:

5th of March 2005
	Oliver cabling
	Oliver cabling will ensure sufficient patch cables are available for weekend activity
	
	01/03/2005


Section 3-2: ISL Remediation

Refer to Appendix’s C / D / E

	Step
	Time
	Owner
	Details
	Comment



	1
	14:00 – 05th March 2005
	Weekend coordinator
	Weekend coordinator will contact the command centre to inform them of the start of the change
	Complete and Confirmed @14:00

	2
	
	BAU
	BAU will take a persistent snap shot of the Red Fabric – 
	Complete and Confirmed @14:10



	3
	
	BAU
	BAU will ensure ALL ISL ports are blocked as per appendix C – Including new proposed ISL ports.
	Complete and Confirmed @14:15

	4
	
	BAU
	BAU will contact Oliver cabling via the conference line – and advise remediation work can commence.
	Complete and Confirmed @14:20

	5
	
	Oliver cabling
	Oliver cabling will remediate the ISL’s, as per appendix E
	A) Complete and Confirmed @14:20

	6
	
	Oliver cabling 
	Once all cabling works are complete Oliver cabling will contact BAU via the conference line.
	Complete and Confirmed @14:50

	7.
	
	BAU
	BAU will unblock the ISL ports as per appendix D
	Complete and Confirmed @14:50


Section 3-3: Post checks

Refer to Appendix D

	Step
	Time
	Owner
	Details
	Comment



	1.
	When section 

3-2 is confirmed and completed. 05th March 2005
	BAU
	BAU will ensure the ISLs are re-established, as per appendix D
	 Complete and Confirmed @15:00

	2
	
	Business As Usual
	BAU will take a persistent snap shot of the fabric.
	Complete and Confirmed @15:10

	3.
	
	Work coordinator
	Work coordinator will contact the command center to inform them of the completion of the change.
	Complete and Confirmed @15:15


Section 3-4: Back out plan

 Refer to appendix: C / F

	Reason for Back Out
	WORK COMPLETE - NOT REQUIRED

	Step
	Time
	Owner
	Details
	Comment



	1.
	08:00 – 06th March 2005
	Weekend coordinator
	Weekend coordinator will contact the command centre to inform them of the start of the (Back Out) change
	

	2
	
	Business As Usual
	BAU will take a persistent snap shot of the Red fabric.
	

	3
	
	BAU
	BAU will block ISL ports, as per appendix C – once complete BAU will contact oliver cabling.
	

	4.
	
	Oliver cabling
	Oliver cabling will re-patch the original ISL’s as per appendix F – once complete oliver cabling will contact BAU.
	

	5.
	
	BAU 
	BAU will unblock ISL ports, as per appendix C, and confirm ISL’s are re-established
	

	6.
	
	Business As Usual
	BAU will take another persistent snap shot of the Red fabric.
	

	7.
	
	Weekend coordinator
	Weekend coordinator will contact the command centre to inform them of the end of the (Back Out) change
	


 Appendix A: Contact details


	Company/Department
	Title
	Name
	Contact Number 1
	Contact Number 2
	Contact Email

	Citigroup - Applied Engineering
	Work Co-ordinator
	Carl Woolward
	07900 915 024
	020 7500 1104
	carl.woolward@citigroup.com

	Citigroup - Applied Engineering
	Work Co-ordinator
	Graham Rodell
	07813 602 734
	020 7508 9070
	graham.rodell@citigroup.com

	Citigroup - Applied Engineering
	Item Co-ordinator
	Carl Williams
	07966 466 956
	020 7986 5693
	carl.patrick.williams@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Salauddin Ahmed
	07764 823 914
	020 7500 6566
	salauddin.ahmed@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Javed Dad
	07841 429 769
	020 7500 9757
	javed.dad@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Paul Haynes
	07796 307 355
	020 7500 4972
	paul.haynes@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	David Coles
	07834 807 687
	020 7500 9855
	david.peter.coles@citigroup.com

	Citigroup -Oliver Cabling
	Team Leader
	Trevor Whelan
	07835 186 452
	020 7986 2596
	trevor.whelan@citigreoup.com

	Citigroup -Oliver Cabling
	Site Engineer
	Paolo Sidoli
	N/A
	020 7986 9962
	paolo.sidoli@citigroup.com

	Citigroup -Oliver Cabling
	Site Engineer
	Carl Elrick
	N/A
	020 7986 9962
	carl.elrick@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Mark Matthews
	 07979 607 118
	020 7500 8025
	mark.a.matthews@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Kevin Last
	 07778 814 088
	020 7986 2648
	kevin.last@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Matt Neill
	07971 008 665
	020 7500 8025 
	matthew.neill@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Bob Coe
	N/A
	020 7986 2651
	bob.coe@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	John Mc Bride
	07710 419 677
	776754073 - Mobex
	john.mcbride@citigroup.com

	Citigroup – WAN engineering
	WAN engineering
	Gary Crocombe
	07764 353 390
	020 7500 8197
	Gary.crocombe@citigroup.com

	Citigroup – WAN engineering
	WAN engineering
	Darren Speller
	07764 353 390
	N/A
	Darren.speller@citigroup.com

	Citigroup – CRS – UK
	CRS
	CRS
	67788
	N/A
	 TBA

	Citigroup – Command centre
	Command Centre
	Command Centre
	62020
	020 7986 2020
	 TBA

	Citigroup - Security - CGC
	Security – CGC
	Security - CGC
	62400
	020 7986 2400
	 TBA

	Citigroup - Security - RDC
	Security – RDC
	Security - RDC
	54393
	020 7500 4393
	 TBA

	EMC
	Project Manager
	Gary Battersby
	07747 765 660
	N/A
	Battersby_Gary@emc.com

	EMC
	SAM
	Paul Belcher
	07730 781 388
	N/A
	Belcher_Paul@emc.com

	EMC
	CE
	Terry Brister
	07713 505 896
	N/A
	brister_terry@emc.com

	EMC
	CE
	Patrick Caborn
	07801 214 303
	N/A
	caborn_patrick@emc.com

	EMC
	CE
	Terry Lennon
	07730 052 641
	N/A
	Lennon_Terry@emc.com

	EMC
	TS
	Ian Gray
	07715 012 248
	N/A
	grey_ian@emc.com


Appendix B: Cabinet information - RDC

	Red Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	1R
	MC5FJ01954
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	2
	6.01.00.18
	Core
	BX04 - Hub 01/02

	3R
	MC5FJ01953
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	28
	6.01.00.18
	Edge
	BX04 - Hub 04/05

	5R
	MC5FJ07237
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	27
	6.01.00.18
	Edge
	BX04 - Hub 07/08

	7R
	MC5FJ01858
	RDC4
	BU18
	MC5TN01560
	RED
	ED-140M
	26
	6.01.00.18
	Edge
	BX04 - Hub 24

	9R
	MC5FJ01292
	RDC1
	BX04
	MC5CN04024
	RED
	RD-64M
	22
	6.01.00.18
	Edge
	BX04 - Hub 09/10

	11R
	MC5CI01485
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	3
	6.01.00.18
	Core
	BX04 - Hub 17/18

	13R
	MC5CI01684
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	21
	6.01.00.18
	Edge
	BX04 - Hub 15/16

	15R
	MC5IN02551
	RDC4
	M01
	MC5TN01559
	RED
	ED-140M
	4
	6.01.00.18
	Core
	BU18 - Hub 

	17R
	MC5FJ1848
	RDC3
	Z02
	MC5CN04014
	RED
	ED-64M
	20
	6.01.00.18
	Edge
	BX04 - Hub 

	19R
	MC5IN02567
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	19
	6.01.00.18
	Edge
	BX04 - Hub 13/14

	Green RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw91r
	MC5FJ21148
	RDC1
	BX17
	MC5TN01413
	Green
	ED-64M
	3
	6.01.00.18
	rdf
	BX17 - Hub 07/08

	rdfsw93r
	MC5FJ21147
	RDC4
	M02
	MC5TN01412
	Green
	ED-64M
	7
	6.01.00.18
	rdf
	BX17 - Hub 24


	
	
	
	
	
	
	
	
	
	
	

	Blue Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	2R
	MC5FJ02061
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	2
	6.01.00.18
	Core
	BX40 - Hub 01/02

	4R
	MC5FJ02060
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	28
	6.01.00.18
	Edge
	BX40 - Hub 04/05

	6R
	MC5FJ07236
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	27
	6.01.00.18
	Edge
	BX40 - Hub 07/08

	8R
	MC5IN02565
	RDC4
	BU26
	MC5TN01562
	Blue
	ED-140M
	26
	6.01.00.18
	Edge
	BX40 - Hub 24

	10R
	MC5FJ01297
	RDC1
	BX40
	MC5CN04016
	Blue
	RD-64M
	22
	6.01.00.18
	Edge
	BX40 - Hub 09/10

	12R
	MC5CI01482
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	3
	6.01.00.18
	Core
	BX40 - Hub 17/18

	14R
	MC5CI01585
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	21
	6.01.00.18
	Edge
	BX40 - Hub 13/16

	16R
	MC5IN02566
	RDC4
	M46
	MC5TN01563
	Blue
	ED-140M
	4
	6.01.00.18
	Core
	BU26 - Hub 

	18R
	MC5FJ02020
	RDC3
	Z44
	MC5CN04016
	Blue
	ED-64M
	20
	6.01.00.18
	Edge
	 

	20R
	MC5IN02562
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	19
	6.01.00.18
	Edge
	BX40 - Hub 14/15

	Black RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw92r
	MC5FJ21144
	RDC1
	BX33
	MC5TN01409
	Black
	ED-64M
	4
	6.01.00.18
	rdf
	BX33 - Hub 07/08

	rdfsw94r
	MC5FJ21146
	RDC4
	M45
	MC5TN01411
	Black
	ED-64M
	8
	6.01.00.18
	rdf
	BX33 - Hub 24


	DMX/SYMM/CLARION
	
	
	

	DMX/ SYMM
	Serial number
	Location
	Model
	Microcode
	Software
	Modem Details
	
	
	

	1R
	CK284700428
	RDC1
	BX42-44
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	2R
	CK284701227
	RDC1
	BX01-03
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	3R
	CK284701079
	RDC1
	BX06-08
	8830
	5567.53.30
	SYMMIP
	 
	
	
	

	4R
	CK284700466
	RDC1
	BX36-38
	8730
	5567.56.22
	SYMMIP
	 
	
	
	

	5R
	SA287750107
	RDC1
	BX10
	DMX2000
	5670.25.27
	SYMMIP
	 020 8297 4092
	
	
	

	6R
	SA287750096
	RDC1
	BX19
	DMX2000
	5670.25.27
	SYMMIP
	 020 8297 4093
	
	
	

	7R
	SA287750200
	RDC1
	BX22
	DMX2000
	5670.73.69
	SYMMIP
	 020 8297 4087
	
	
	

	8R
	SA287750442
	RDC1
	BX13
	DMX2000
	5670.25.27
	SYMMIP
	 020 8297 4094
	
	
	

	CX1R
	MSL00040900021
	RDC1
	BX35
	CX600
	Flare (11)
	ClarAlert
	 
	
	
	

	9R
	CK287890275
	RDC4
	C04
	DMX3000
	5670.73.69
	SYMMIP
	020 7500 8632
	
	
	

	10R
	CK287890300
	RDC4
	C42
	DMX3000
	5670.73.69
	SYMMIP
	020 7986 9964
	
	
	

	11R
	CK287890293
	RDC4
	F04
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0881
	
	
	


	Service Processors

	Service Processor
	Serial number
	Location
	Model
	IP Address
	Connectrix Manager version
	CEP connection
	Modem Details

	Blue Active
	 
	RDC4
	M46
	1U
	169.186.192.197
	7.0.2
	srdcfwe13 3/7
	020 7508 0879

	Black Active
	 
	RDC4
	M45
	1U
	169.186.192.68
	7.0.2
	srdcfwe14 3/6
	020 7508 0880

	Blue Standby
	 
	RDC1
	BX40
	Laptop
	169.186.192.69
	7.0.1
	srdcfwe10 3/38
	020 8318 0680

	Black Standby
	 
	RDC1
	BX33
	1U
	169.186.192.196 
	7.0.2
	srdcfwe09 3/37
	

	Green Active
	 
	RDC4
	M02
	1U
	 169.186.192.132
	7.0.2
	srdcfwe13 3/2
	020 7500 8738

	Red Active
	 
	RDC4
	M01
	1U
	 169.186.192.133
	7.0.2
	srdcfwe14 3/3
	020 7508 0834

	Green Standby
	 
	RDC1
	BX17
	Laptop
	169.186.192.4
	7.0.2
	srdcfwe10 3/29
	

	Red Standby
	 
	RDC1
	BX04
	1U
	169.186.192.5
	7.0.1
	srdcfwe09 3/30
	020 8318 0509


Appendix B: Cabinet information - CGC

	Red Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	1
	MC5FJ01158
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	1
	6.01.00.18
	Core
	60AN Hub 01/02

	3
	MC5IN02560
	CGC2
	CA95
	MC5TN01558
	RED
	ED-140M
	18
	6.01.00.18
	Edge
	CA95 Hub 07/08

	5
	MC5FJ01267
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	30
	6.01.00.18
	Edge
	60AN Hub 07/08

	7
	MC5FJ01159
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	29
	6.01.00.18
	Edge
	60AN Hub 04/05

	9
	MC5FJ07225
	CGC2
	BW100
	MC5CN03485
	RED
	ED-64M
	25
	6.01.00.18
	Edge
	BW100 Hub 01/02

	11
	MC5FJ01673
	CGC2
	BW100
	MC5CN04635
	RED
	ED-64M
	24
	6.01.00.18
	Edge
	BW100 Hub 03/04

	13
	MC51N01268
	CGC2
	BW100
	MC5CN04635
	RED
	ED-140M
	23
	6.01.00.18
	Core
	BW100 Hub 05/06

	15
	MC5CIN01483
	CGC2
	BW101
	MC5CN07127
	RED
	ED-140M
	20
	6.01.00.18
	Edge
	BW100 Hub 07/20

	Green RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw91C
	MC5FJ21145
	CGC1
	59AN
	MC5TN01410
	Green
	ED-64M
	1
	6.01.00.18
	RDF
	59AN Hub 07/08

	rdfsw93C
	MC5FJ21149
	CGC2
	CA96
	MC5TN01414
	Green
	ED-64M
	5
	6.01.00.18
	RDF
	CA96 Hub 07/08

	
	
	
	
	
	
	
	
	
	
	


	Blue Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	2
	MC5FJ01182
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	1
	6.01.00.18
	Core
	71CF Hub 01/02

	4
	MC5IN02580
	CGC2
	CB15
	MC5TN01561
	Blue
	ED-140M
	18
	6.01.00.18
	Edge
	CB15 Hub 07/08

	6
	MC5FJ01308
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	30
	6.01.00.18
	Edge
	71CF Hub 07/08

	8
	MC5FJ01183
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	29
	6.01.00.18
	Edge
	71CF Hub 04/05

	10
	MC5FJ07208
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-64M
	25
	6.01.00.18
	Edge
	CB05 Hub 01/02

	12
	MC5FJ09611
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-64M
	24
	6.01.00.18
	Edge
	CB05 Hub 03/04

	14
	MCF1N01267
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-140M
	23
	6.01.00.18
	Core
	CB05 Hub 07/08

	16
	MC5IN01484
	CGC2
	CB06
	MC5TN06731
	Blue
	ED-140M
	20
	6.01.00.18
	Edge
	CB05 Hub 13/14

	Black RDF Fabric

	Switch
	Switch serial number
	Location
	 
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw92C
	MC5FJ21143
	CGC1
	70CF
	MC5TN01408
	Black
	ED-64M
	2
	6.01.00.18
	RDF
	70CF Hub 07/08

	rdfsw94C
	MC5FJ21150
	CGC2
	CB14
	MC5TN01415
	Black
	ED-64M
	6
	6.01.00.18
	RDf
	CB14 Hub 07/08


	DMX/SYMM/CLARION
	
	
	

	DMX/ SYMM
	Serial number
	Location
	Model
	Microcode
	Software
	Modem Details
	
	
	

	1C
	CK284700679
	CGC1
	69AZ
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	2C
	CK284700995
	CGC1
	56AZ
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	3C
	CK284701078
	CGC1
	67BN
	8830
	5567.53.30
	SYMMIP
	 
	
	
	

	4C
	CK284700214
	CGC2
	BW98
	8730
	5568.56.22
	SYMMIP
	020 7516 9101
	
	
	

	5C
	SA287750129
	CGC2
	CB09
	DMX2000
	5670.25.27
	SYMMIP
	020 7516 9095
	
	
	

	6C
	SA287750125
	CGC2
	BW94
	DMX2000
	5670.25.27
	SYMMIP
	020 7516 9097
	
	
	

	7C
	SA287750122
	CGC2
	CB12
	DMX2000
	5670.73.69
	SYMMIP
	020 7519 6812
	
	
	

	8C
	SA287750383
	CGC2
	BW92
	DMX2000
	5670.25.27
	SYMMIP
	020 7516 6803
	
	
	

	9C
	CK287890296
	CGC2
	BC06
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0813
	
	
	

	10C
	CK287890294
	CGC2
	BH100
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0614
	
	
	

	11C
	CK287890298
	CGC2
	AZ07
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0820
	
	
	

	CX1C
	MSL00040800040
	CGC2
	CA101
	CX600
	 
	 
	 
	
	
	


	Service Processors

	Service Processor
	Serial number
	Location
	Model
	IP Address
	Connectrix Manager version
	CEP connection
	Modem Details

	Blue Standby
	 
	CGC2
	CB15
	1U
	169.186.141.197
	7.0.2
	sol2fwe01 4/10
	020 7500 1723

	Black Standby
	 
	CGC1
	70CF
	1U
	169.186.141.68
	7.0.2
	sol1fwe15 4/10
	 

	Blue Active
	 
	CGC1
	71CF
	Laptop
	169.186.141.69
	7.0.1
	sol1fwe16 4/10
	 

	Black Active
	 
	CGC2
	CB14
	1U
	169.186.141.196
	7.0.2
	sol2fwe02 4/9
	020 7508 0626

	Green Stanby
	 
	CGC1
	59AN
	1U
	169.186.141.4
	7.0.2
	sol1fwe16 4/1
	 

	Red new Active
	 
	CGC2
	CA95
	1U
	169.186.141.133
	7.0.2
	sol2fwe02 4/3
	020 7500 1165

	Green active
	 
	CGC2
	CA96
	1U
	169.186.141.132
	7.0.2
	sol2fwe01 4/2
	020 7508 0826

	Red old Active
	 
	CGC1
	60AN
	Laptop
	169.186.141.5
	7.0.1
	sol1fwe15 4/2
	 


Appendix C: 
Appendix D:

Reference Item 3-2 / 3-4
Reference Item 3-2 / 3-3
	PORTS TO BLOCK
	
	PORTS TO UNBLOCK

	RDC
	 
	 
	
	RDC
	 

	Switch
	Port
	Comment
	
	Switch
	Port

	Switch01R
	50
	 
	
	Switch01R
	50

	Switch01R
	63
	Leave Blocked Mark as spare
	
	Switch11R
	50

	Switch11R
	50
	 
	
	CGC
	 

	Switch11R
	63
	Leave Blocked Mark as spare
	
	Switch
	Port

	CGC
	 
	 
	
	Switch01C 
	33

	Switch
	Port
	Comment
	
	Switch01C 
	61

	Switch01C
	01
	Leave Blocked Mark as spare
	
	Switch13C
	96

	Switch01C
	30
	Leave Blocked Mark as spare
	
	Switch15C
	66

	Switch01C
	33
	 
	
	
	

	Switch01C
	61
	 
	
	
	

	Switch9C
	0
	Leave Blocked Mark as spare
	
	
	

	Switch11C
	42
	Leave Blocked Mark as spare
	
	
	

	Switch13C
	63
	Leave Blocked Mark as spare
	
	
	

	Switch13C
	96
	 
	
	
	

	Switch15C
	63
	Leave Blocked Mark as spare
	
	
	

	Switch15C
	66
	 
	
	
	


Appendix E:
Appendix F:

Reference Item 3-2
Reference Item 3-4
	RDC ISL MOVES
	
	RDC ISL MOVES

	Switch
	Port
	 
	Switch
	Port
	
	Switch
	Port
	 
	Switch
	Port

	Switch01R
	63
	>>
	Switch01R
	50
	
	Switch01R
	50
	>>
	Switch01R
	63

	Switch11R
	63
	>>
	Switch11R
	50
	
	Switch11R
	50
	>>
	Switch11R
	63

	CGC ISL MOVES
	
	CGC ISL MOVES

	Switch01C
	01
	>>
	Switch01C
	33
	
	Switch01C
	33
	>>
	Switch01C
	1

	Switch01C
	30
	>>
	Switch01C
	61
	
	Switch01C
	61
	>>
	Switch01C
	30

	Switch13C
	63
	>>
	Switch13C
	96
	
	Switch13C
	96
	>>
	Switch13C
	63

	Switch15C
	63
	>>
	Switch15C
	66
	
	Switch15C
	66
	>>
	Switch15C
	63

	ISL REMOVALS
	
	ISL ADDITIONS

	Switch09C
	0
	>>
	Switch11C
	42
	
	Switch09C
	0
	>>
	Switch11C
	42


Appendix G:

Reference Item: 2-2

Resolution of SYMACL issue (EMC Case ref: 12522318) 

The entries below need to be added to the following arrays:

CGC


RDC
3C  (1078)

3R  (1079)

5C  (0129)

5R  (0107)

7C  (0122)

7R  (0200)

11C (0298) 

11R (0293)
Host Name: EU-MGT1

Host ID: 2F5802A8-57478BC1-993C757A

User Name: acl-mgt1

User Id: acl1

Host Name: EU-MGT2

Host ID: 2F5802A8-52498BC0-9B3C757A

User Name: acl-mgt2 

User Id: acl2

Host Name: EU-MGT3

Host ID: 2F5802A8-5C498AC8-9D3C757A

User Name: acl-mgt3 

User Id: acl3

Host Name: EU-MGT4

Host ID: 2F5802A8-5C498ACB-993C757A

User Name: acl-mgt4 

User Id: acl4 
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