Carl Williams – Weekend 290105_v3.0 – Signoff Draft


Weekend 29th January 2005  - Signoff Draft includes PIR and ‘As Fitted Report’
Work Co-ordinator: Graham Rodell

Consisting of 4 Items
Item1: 6 Items brought forward from previous installations – Covered by change control numbers:

1-1: CR:05260070 – SP upgrades Blue Zones RDC/CGC

1-2: CR: 05318352 - Enabling dial-in reporting on all SYMMS RDC/CGC

1-3: CR:05273311 – SP upgrades Red Zone CGC

1-4: ARTS315542/315550 - Decommissioning of old management workstations.

1-5: CR: 05318384 – Restricting access to VCMDB

1-6: CR:05273311 – Retrieving nickname information form the old Red SP

Item co-ordinator: Javed Dad

Item2: Break/Fix snagging – 2 Items Covered by: 

VT1671915 – System clock changes on Switch16R

VT1671991 – Unblocking of ports on Switch14C

Item co-ordinator: Javed Dad

Item3: 290105-01 – Covered by change control number: 05305859
SP upgrades Blue Zones RDC/CGC
Item co-ordinator: Carl Williams

Item4: 290105-02 - Covered by ARTS: 318818

ISL remediation for switch16R

Item co-ordinator: Carl Williams

Locations:
TR1/TR2

CGC2 3rd floor

RDC 1st floor

RDC 4th floor

Conference Call Number: 0207 986 7934 (pin 7934)
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Version Control

	Date
	Version
	Reason for Change

	20/01/2005
	290105_v0.1

CPW
	1st Draft

	24/01/2005
	290105_v0.2

CPW
	Includes Items brought forward from 220105, Item 4 ISL remediation 16R >> 8R.

	25/01/2005
	290105_v0.3

CPW
	Includes CR/Arts for Item 1&2, and confirmed BAU names for weekend work, additional item 2-2

	26/01/2005
	290105_v0.4

CPW
	Includes changes highlighted in 14:00 meeting 25/01/05, updated contacts list, scripts for dial in reporting

	27/01/2005
	290105_1.0

CPW
	Confirmed EMC resource, updated work co-ordinator.

	29/01/05
	Weekend290105_v2.0

Graham Rodell
	V1.0 Converted into PIM ‘As Fitted ‘ Report

	31/02/2005
	290105_v3.0

CPW
	Sign off draft – with confirmation of dial in reporting status – Sign off from 13:00 BAU meeting

	
	
	


As Fitted Overview

The following is the ‘as fitted’ report for Item 1. The colours from the Version 1.0 Implementation Plan indicating responsibility for the individual tasks have been removed and replaced by redlining information indicating changes from the last pre-installation documentation. 

Found issues

1. No Connectrix Manager 7.0.2 was available at RDC. Software transferred from CGC2 L3 Store  - Software now on site in connectrix cabinet.
2. Graham Rodell access to CGC2 L3 DCSM Store had been removed by Citigroup Security who verbally cited a revocation order covering just this store dated 7/1/2005. – GR to follow up. 
3. After the migration to the new 1u CSP for RDCBLUEFABRIC the following issues where found
a. Although eusan-mgt2 could be used as a login root to RDCBLUEFABRIC eusan-mgt4 could not acquire a login screen. – As per item 7. SA is following up.
b. The zones from RDCBLUESTANDBY could not be transferred to RDCBLUEFABRIC. This included the new zone set due to be pushed out this weekend  - EMC procedure could not be followed as mapping network drive would not be possible through the firewall – The zone set info needs to be transferred either via Zip drive or on to another laptop via a crossover cable.
4. JD was also involved in a BAU Break/Fix issue and had a conference call at 19:30. Due to 3 above, the non-essential nature of this move and the on-going unrelated Break/Fix issue, it was decided that if the zone set issue was not fixed by 19:30 then a roll-back would be undertaken. The issue not being fixed by 19:30 roll-back was implemented, tested and found correct. Roll-back was successful at 19:30.

5. RDC Symm 1227 SYMM2R could not have its flags activated (Item 1-2) as the SP was found to be faulty. TB raised call with EMC – EMC engineer to visit 31/01/2005 @19:00
6. On try to take a persistent snapshot of RDCBLUSTANDBY it was noted that both Persist and un-persist where greyed out.   – The service processor on the 4th floor may still be powered up.
7. eusan-mgt4 was found not to be able to produce a login screen for RDCBLUEFABRIC or RDCBLUESTANDBY on rollback. When tested last week when login screen was presented and used to login to RDCREDFABRIC. The login screen is run from eusan-mgt4 and from the CSP thus break/fix issue with eusan-mgt4, or Firewall/CEP settings have change from last week. SA agreed to follow-up on Monday.
Wash-UP

Present: CPW SA & GR

Time 21:00 22901/2005

The wash-up took place by telephone conference and the ’sign of’ and issues tables were accepted as a true record of the actions resultant from the installation plan.

Graham Rodell

Co-Coordinator SAN Installations 29/01/2005
Documentation Changes

Changes to be reflected in the documentation after successful completion of the whole of this work plan are as follows:

Connectrix service processors names will now be: 

The following ports will be unblocked:

	Switch
	Port

	14C
	86 

	14C
	88

	14C
	92

	
	

	
	

	
	


The following ports will changed

	Switch
	Port
	To
	Switch
	Port

	
	
	
	
	

	
	
	
	
	


	Documentation update Sign Off: 2 Pages – To be returned to BAU on completion

Member of: _____________ BAU

NAME: ____________________ Salauddin Ahmed

Date: __31/01/2005 – Signed original kept with BAU Team


Overview of All Weekend Work

Item1: Issues brought forward that require weekend activity.

6 Items brought forward that require weekend activity – please see Item1 for full details

Item2: Break/Fix Snagging

2 Item requires weekend activity – please see Item2 for full details

Item3: Upgrade and relocation of laptop service processors to 1U service processors – Blue Zone RDC and CGC1/2.

The following contains the details of the work to be undertaken over the weekend of the 29th of January 2005 at the Citigroup CGC1 TR1/TR2, CGC2 and RDC 1st and 4th floor sites:

The upgrade and relocation of laptop service processors to 1U cabinet mounted service processors will consist of the following four steps:
1) Pre-requisites checks to ensure 

2) The Upgrade and relocation

3) Post checks to make sure that the Management Work station are capable of communicating with the Service Processors.

4) Post Activity to ensure users details have been transferred and the shut down of the original service processor.

Item4: ISL remediation – Switch16R

The ISL’s between switch 16R and Switch8R are currently installed via temporary fibres on the 4th floor RDC, these will be de-patched and re-patched via the permanent infrastructure.

Required Resource 
Resources presence required: 

	MEMBER OF
	CGC RESOURCE
	RDC RESOURCE

	EMC CE
	Terry Brister
	Terry Brister

	EMC CE
	Tahir Shahid
	Tahir Shahid

	OLIVER CABLING
	Carl Williams
	Paolo Sidoli

	BUSINESS AS USUAL (primary)
	Javed Dad
	Javed Dad

	BUSINESS AS USUAL (secondary)
	David Coles
	David Coles

	APPLIED ENGINEERING
	Graham Rodell
	Graham Rodell

	EMC Project Manager
	Gary Battersby
	Gary Battersby

	EMC SAM
	Paul Belcher
	Paul Belcher

	DCSM
	
	John McBride

	DCSM
	
	Matt Neil

	Citigroup Electrician
	Not allocated until 29/01/05
	Not allocated until 29/01/05

	Citigroup Tile Lifter
	Not allocated until 29/01/05
	Not allocated until 29/01/05


This work is the second of 2 steps in migrating the existing ‘laptop’ service processors to 1U service processors, whilst ensuring the connections behind the firewall.

This document is to be used as a complement of the official project document and not as substitute.

Over All Sign Off

	Item
	Status
	Owner
	Sign off



	Item 1: Items brought forward from previous installations
	See individual items pages 10 & 11
	BAU – Javed Dad
	GR



	Item 2: Break/Fix Snagging
	All completed correct
	BAU – Javed Dad
	GR



	Item 3: Upgrade and relocation of laptop service processors to 1U service processors
	Rolled Back Not completed
	Applied Engineering – Graham Rodell
	GR

	Item4: Switch16R ISL remediation – Temporary fibres to permanent infrastructure. 
	Completed correct
	BAU – Javed Dad
	GR


	Overall Sign Off: 1 Page – To be returned to BAU on completion

Member of: _____________ BAU

NAME: ____________________ Salauddin Ahmed

Date: 31/01/2005 - Signed original kept with BAU Team


Item 1: Items brought forward from previous installations

6 ITEMS BROUGHT FORWARD

	Item  number
	Reference
	Description
	Prerequisites
	Comments
	Resolution

	1-1
	CR:05260070

150105-01
	Migration of Laptop Blue Service processors to 1U SP’s


	Installation of Modem lines in Blue service processor cabinets


	 See Item3
	Not completed in RDC  - Rolled back see found issues #3.

Carried forward in CGC due to no modem lines. RS232 fitted both sites

	1-2
	CR05318352
	Enable dial in reporting for ALL SYMMs (CGC & RDC) See required scripts in comments.


	
	Scripts required for dial in reporting

04D1.00 Remote Connection Established

04D2.00 Remote Connection Rejected

04D4.00 Remote Connection Closed
	Completed RDC except for Symm 2R sid 1227 due to faulty SP. Fault raised by TB.

CGC to be carried out 30/1/05 by remote dial in.

TB Confirmed complete.

	1-3
	CR:05273311
	Migration of Laptop Red Service processors to 1U SP’s


	Installation of Modem lines in Red service processor cabinets
	To be carried forward to 05/02/05


	N/A


	1-4
	ARTS:315542/

315550
	Decommissioning of old management workstations.
	
	Sanuk01 – CGC1 – 73CF – 315542

Sanuk03 – RDC – BR01 – 315550


	Reported completed by JD at 14:00

	1-5
	CR:05318384
	Restricting access to VCMDB


	
	To be carried forward to 05/02/05
	N/A

	1-6
	CR: 05273311

220105-1
	Retrieving nic name information from the old Red service processor, and transferring to the new 1U SP.
	
	Nickname file can be found in, c:\efcdata\emsdata\efc

services\wwnicnames
	Migration instruction failed on RDCBLUEFABRIC so carried forward for RDCREDFABRIC


	Item1 Sign Off: 2 Pages – To be returned to BAU on completion

Member of: _____________ BAU

NAME: ____________________ Salauddin Ahmed

Date: _31/01/2005____ Signed original kept with BAU Team


Item 2: Break/Fix Snagging

	Item Number
	VT/EMC Reference
	Description
	Comments
	Resolution

	2-1
	VT:1671915
	An EMC engineer will be checking and (if necessary) resetting the system clock for connectrix switch 16R
	
	TB reported completed by 20:30

	2-2
	VT:1671991
	Unblocking of ports 88, 86, 92 on Switch14C.
	See appendix J
	Reported complete by JD 15:10


	Item2 Sign Off: 1 Page – To be returned to BAU on completion

Member of: _____________ BAU

NAME: ____________________ Salauddin Ahmed

Date: _31/01/2005____ Signed original kept with BAU Team


Item 3: Upgrade and relocation of laptop service processors to 1U service processors:

Blue Zone in CGC1/2 

Blue Zones in RDC
Work number: 290105-1

Change control number: 050305859/50305929

Item co-ordinator: Carl Williams

Date: 

29th of January 2005

Location:
TR1/TR2

CGC2 3rd floor

RDC 1st floor

RDC 4th floor

Conference Call Number: 0207 986 7934 (pin 7934)

Item 3: Section Checklist

Upgrade and relocation of laptop service processors to 1U service processors

	Section
	Details
	Comments
	Sign Off

	3-1
	Pre-requisites checks.
	RDC only correct CGC no modems lines. CGC installation carried forward

RS232 Cabling fitted in RDC & CGC2
	Graham Rodell

	3-2
	Upgrade and relocation of Blue service processors.
	 Rolled back due to issues outlined in issue list above
	 Graham Rodell

	3-3
	Post checks.
	Rolled back due to issues outlined in issue list above
	Graham Rodell

	3-4
	Post Activity
	 Rolled back due to issues outlined in issue list above
	Graham Rodell
 

	Item 3 completion Sign Off: To be returned to BAU on completion.

Member of: BAU_______ NAME: Salauddin Ahmed______________ Date: _31/01/2005____ Signed original kept with BAU Team 




Section 3-1: Pre-requisites checks
	Step
	Time
	Owner
	Details
	Comment
	Date Due

	1
	Before starting:

29th of January 2005
	Applied Engineering
	Applied engineering will confirm via email that the firewall configuration is setup and functioning successfully as per appendix C


	Applied engineering has received confirmation that the configuration is set up, but this cannot be tested, until installation.
	25/01/2005

	2
	Before starting:

29th of January 2005
	Oliver Cabling
	Oliver Cabling should confirm that there is a connection available for each of the cabinet locations that will be connected to the firewall, as per appendix D
	Survey was carried out on Saturday 08/01/2005 – connections are available in all locations.
	25/01/2005

	3
	Before starting:

29th of January 2005
	Applied engineering
	Applied engineering will confirm there are available Modems and modem lines in the new service processor cabinets.


	VR42020 was raised for temporary installation of 4 analogue extensions, and the installation of 4 x DEL lines. (Extensions to be removed after DEL’s installed) This has been rejected pending a meeting with Patrick Moran – BISO.

Modem in Store room1.

A solution has been suggested to use a redundant DEL for the Blue zone in RDC – but still require the Extensions for CGC. – Pending VT approval.
	 25/01/2005

	4
	Before starting:

29th of January 2005
	Applied engineering
	Applied engineering will confirm with DCSM that the RS232 cables, and installation resource required for the new service processor modem lines is available – CR:05292416


	Email sent 18/01/05 – DCSM will confirm if they have the required cables, installation in CGC2 is pending installation of the analogue extension above.

14:00 29/1/2005 CPW reported DCSM had installed  RDC & CGC2 RS232 by 14:00
	25/01/2005



	5
	Before starting:

29th of January 2005
	Applied engineering
	Applied engineering will confirm with DCSM that there is sufficient power supplies for the new service processor modems.


	There is only 2 modems connected to the power strip in M46 – there is enough room for an additional modem PSU – but more will be need if  other modems are installed
	25/01/2005


Section 3-2: Upgrade and relocation of Blue service processors
	Step
	Time
	Owner
	Details
	Comment



	1
	When section 

3-1 is confirmed and completed. 29th January 2005
	EMC CE
	EMC CE will follow the appendix D and set the IP address, default Gateway and Subnet Mask for each connectrix service processor as required.
	Un-connected service processors may be configured prior to 14:00 – 29th January 2005

CPW report completed by 16:25 

	2
	
	EMC CE
	EMC CE will follow the appendix D and amend the config.properties file in the EFCM folder on each connectrix service processor as per appendix E
	Un-connected service processors may be configured prior to 14:00 – 29th January 2005

CPW report completed by 16:25

	3
	
	EMC CE 
	EMC CE will apply the access client restriction for all 4 management workstation for each service processors. (By IP) – As per appendix D

169.183.26.108 – (eusan-mgt1)

169.186.223.81 – (eusan-mgt2)

169.183.27.90 – (eusan-mgt3)

169.186.223.170 – (eusan-mgt4)
	Un-connected service processors may be configured prior to 14:00 – 29th January 2005

eusan-mgt2 tested correct

eusan-mgt4 was found not to be able to gain a login screen from RDCBLUEFABRIC or RDCBLUESTANDBY on rollback. Did work when tested last week when login screen given for RDCREDFABRIC, so assumed to be break/fix issue with eusan-mgt4. SA agreed to follow-up on Monday.

	4
	
	EMC CE
	EMC CE will amend the new service processor names. 
	RDCBLUEFABRIC

Done



	5
	
	EMC CE 
	EMC CE will copy 

A) users/profiles 

B) ‘nick names’ 

C) zone info from the old service processor, and transfer the information to the new service processors.
	This file was found by carrying out a search on the service processors for “users” and was transferred to the new Service processor via floppy disk – Nick name files are located in c:\efcdata\emsdata\efcservices\wwnicnames
Transfer of zone sets failed and at 19:30 roll-back was implemented. See issue list above.

	6
	14:00 – 29th January 2005
	Business As Usual
	Prior to the Upgrade and relocation work, BAU Will commence weekend zoning work at 14:00.
	

	7
	14:00 – 29th January 2005
	Business As Usual
	Prior to the Upgrade and relocation work, BAU will take a persistent snap shot of the fabric
	BAU will contact Oliver cabling (Via conference line) once complete.

	8
	Aprox 14:30 – 29th January 2005
	Oliver Cabling
	After confirming with BAU that work can be commenced Oliver Cabling will connect the firewall connection to each of the service processor involved in the activity as per appendix D.


	

	9
	
	EMC CE
	EMC CE will configure the new service processors with the 

mail server IP address -162.124.146.243 and the SAN email address -GTUKSANAUTO@IMCEU.EU.SSMB.COM
  
	

	10
	
	EMC CE
	EMC CE Will configure the service processor with the modem details.
	See appendix B

	11
	
	EMC CE
	EMC CE will send a Test email and confirm dial home once the installation is complete
	


Section 3-3: Post checks

	Step
	Time
	Owner
	Details
	Comment



	1.
	When section 

3-2 is confirmed and completed. 29th January 2005
	Business As Usual
	BAU will confirm that all the service processors are manageable by each of the 4 new management workstations:

eusan-mgt1

eusan-mgt2

eusan-mgt3

eusan-mgt4


	 Checked after roll-back on RDCBLUE STANDBY.

eusan-mgt2 correct

eusan-mgt4 Failed see issues list above

eusan-mgt1 & 3 CGC, CSP not upgraded



	2
	
	Business As Usual
	BAU will take a persistent snap shot of the fabric.
	Failed as persistent menu item greyed out, see issue list above.

	3.
	
	Business As Usual
	BAU will check all user and zoning information has been transferred on to the new service processor
	As per step 3-2-5 and appendix F

Zones checked on RDCBLUEFABRIC, SA reported correct


Section 3-4: Post activity

	Step
	Time
	Owner
	Details
	Comments

	1
	When section 

3-3 is confirmed and completed. 29th January 2005
	EMC CE
	EMC CE will shut down the original service processors.


	Due to roll-back new CSP closed down.


Item 4: Remediation of ISL’s between Switch16R and Switch8R

Blue Zones in RDC
Work number: 290105-2

ARTS:315818

Item co-ordinator: Carl Williams

Date: 

29th of January 2005

Location:
RDC 4th floor 

Conference Call Number: 0207 986 7934 (pin 7934)

Item 4: Section Checklist

Remediation of ISL’s between Switch16R and Switch8R
	Section
	Details
	Comments
	Sign Off

	3-1
	Pre-requisites checks.
	 Correct
	 

GR

	3-2
	Remediation of ISL’s between Switch16R and Switch8R
	 Correct
	 

GR

	3-3
	Post checks.
	 Correct
	 

GR

	Item 4 completion Sign Off: To be returned to BAU on completion.

Member of: BAU______ NAME: Salauddin Ahmed_______ Date: 31/01/2005____ Signed original kept with BAU Team 


Section 4-1: Pre-requisites checks
	Step
	Time
	Owner
	Details
	Comment
	Date Due

	1
	Before starting:

29th of January 2005
	Oliver Cabling
	Oliver Cabling will confirm that there is sufficient links available between switch16R Frame panel and Switch8R. Also confirm there are sufficient patch cords.
	Confirmed and Complete – 24/01/05 
	25/01/2005

	2
	Before starting:

29th of January 2005
	Business as usual
	BAU will confirm that all attached hosts are dual pathed to Switch15R/16R.
	Confirmed by JD 19:00
	27/01/2005


Section 4-2: Remediation of ISL’s between Switch16R and Switch8R
	Step
	Time
	Owner
	Details
	Comment



	1
	When section 

4-1 is confirmed and completed. 29th January 2005 – 14:00
	BAU
	BAU will take a persistent snap shot of the Blue Fabric 
	

	2
	
	BAU
	BAU will block the ISL’s between switch16R and 8R, as per appendix G
	Once complete BAU will contact Oliver cabling Via the conference line.

20:35 SA reported all ports blocked.

	3
	
	Oliver Cabling
	Oliver Cabling will de-patch the temporary fibres from switch16R and switch8R, as per appendix G
	

	4
	
	Oliver Cabling
	Oliver Cabling will re-patch the permanent infra structure in to switch16R and 8R.
	20:45 CPW reported complete

	5
	
	Oliver Cabling
	Oliver Cabling will patch the ISL’s via the interlinks as per appendix H
	Once complete Oliver cabling will contact BAU Via the conference line.

	6
	
	BAU
	BAU will unblock the ISL’s between 16R and 8R as per appendix G
	20:45 GR Ops informed of blue fabric re-build which could give errors

20:50 SA unblocked all ports

21:00 GR informed Ops work now completed and fabric should now be actively monitored. Ops reported they had seen error from the Blue Fabric.GR informed them that these will now have stopped and if any more are seen they to be treated as real errors and normal action taken.


Section 4-3: Post checks
	Step
	Time
	Owner
	Details
	Comment



	1
	When section 

4-2 is confirmed and completed. 29th January 2005 
	BAU
	BAU confirm the ISL’s between switch16R and 8R are back online. As per appendix G
	SA reported all back on line. 20:52

	2
	
	BAU
	BAU will take a persistent snap shot of the Blue Fabric 
	Failed see issue section above.


Appendix A: Contact details


	Company/Department
	Title
	Name
	Contact Number 1
	Contact Number 2
	Contact Email

	Citigroup - Applied Engineering
	Work Co-ordinator
	Carl Woolward
	07900 915 024
	020 7500 1104
	carl.woolward@citigroup.com

	Citigroup - Applied Engineering
	Work Co-ordinator
	Graham Rodell
	07813 602 734
	020 7508 9070
	graham.rodell@citigroup.com

	Citigroup - Applied Engineering
	Item Co-ordinator
	Carl Williams
	07966 466 956
	020 7986 5693
	carl.patrick.williams@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Salauddin Ahmed
	07764 823 914
	020 7500 6566
	salauddin.ahmed@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Javed Dad
	07841 429 769
	020 7500 9757
	javed.dad@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	Paul Haynes
	07796 307 355
	020 7500 4972
	paul.haynes@citigroup.com

	Citigroup - BAU
	BAU - On Call Representative
	David Coles
	07934 807 687
	020 7500 9855
	david.peter.coles@citigroup.com

	Citigroup -Oliver Cabling
	Team Leader
	Trevor Whelan
	07835 186 452
	020 7986 2596
	trevor.whelan@citigreoup.com

	Citigroup -Oliver Cabling
	Site Engineer
	Paolo Sidoli
	N/A
	020 7986 9962
	paolo.sidoli@citigroup.com

	Citigroup -Oliver Cabling
	Site Engineer
	Carl Elrick
	N/A
	020 7986 9962
	carl.elrick@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Mark Matthews
	 07979 607 118
	020 7500 8025
	mark.a.matthews@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Kevin Last
	 07778 814 088
	020 7986 2648
	kevin.last@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Matt Neill
	07971 008 665
	020 7500 8025 
	matthew.neill@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Bob Coe
	N/A
	020 7986 2651
	bob.coe@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	John Mc Bride
	07710 419 677
	776754073 - Mobex
	john.mcbride@citigroup.com

	Citigroup – CRS – UK
	CRS
	CRS
	67788
	N/A
	 TBA

	Citigroup – Command centre
	Command Centre
	Command Centre
	62020
	020 7986 2020
	 TBA

	Citigroup - Security - CGC
	Security – CGC
	Security - CGC
	62400
	020 7986 2400
	 TBA

	Citigroup - Security - RDC
	Security – RDC
	Security - RDC
	54393
	020 7500 4393
	 TBA

	EMC
	Project Manager
	Gary Battersby
	07747 765 660
	N/A
	Battersby_Gary@emc.com

	EMC
	SAM
	Paul Belcher
	07730 781 388
	N/A
	Belcher_Paul@emc.com

	EMC
	CE
	Terry Brister
	07713 505 896
	N/A
	brister_terry@emc.com

	EMC
	CE
	PatrickCaborn
	07801 214 303
	N/A
	caborn_patrick@emc.com

	EMC
	TS
	Tahir Shahid
	07802 241 372
	N/A
	shahid_tahir@emc.com

	EMC
	CE
	Dave Manley
	07803 233 383
	N/A
	Manley_David@emc.com

	EMC
	TS
	Ian Grey
	07715 012 248
	N/A
	grey_ian@emc.com

	EMC
	CE
	Chris Hankinson
	07710 362 871
	N/A
	hankingson_chris@emc.com


Appendix B: Cabinet information - RDC

	Red Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	1R
	MC5FJ01954
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	2
	6.01.00.18
	Core
	BX04 - Hub 01/02

	3R
	MC5FJ01953
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	28
	6.01.00.18
	Edge
	BX04 - Hub 04/05

	5R
	MC5FJ07237
	RDC1
	BX04
	MC5CN04024
	RED
	ED-64M
	27
	6.01.00.18
	Edge
	BX04 - Hub 07/08

	7R
	MC5FJ01858
	RDC4
	BU18
	MC5TN01560
	RED
	ED-140M
	26
	6.01.00.18
	Edge
	BX04 - Hub 24

	9R
	MC5FJ01292
	RDC1
	BX04
	MC5CN04024
	RED
	RD-64M
	22
	6.01.00.18
	Edge
	BX04 - Hub 09/10

	11R
	MC5CI01485
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	3
	6.01.00.18
	Core
	BX04 - Hub 17/18

	13R
	MC5CI01684
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	21
	6.01.00.18
	Edge
	BX04 - Hub 15/16

	15R
	MC5IN02551
	RDC4
	M01
	MC5TN01559
	RED
	ED-140M
	4
	6.01.00.18
	Core
	BU18 - Hub 

	17R
	MC5FJ01848
	RDC3
	Z02
	MC5CN04014
	RED
	ED-64M
	20
	6.01.00.18
	Edge
	BX04 - Hub 

	19R
	MC5FJ01848
	RDC1
	BX11
	MC5N07128
	RED
	ED-140M
	19
	6.01.00.18
	Edge
	BX04 - Hub 13/14

	Green RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw91r
	MC5FJ21148
	RDC1
	BX17
	MC5TN01413
	Green
	ED-64M
	3
	6.01.00.18
	rdf
	BX17 - Hub 07/08

	rdfsw93r
	MC5FJ21147
	RDC4
	M02
	MC5TN01412
	Green
	ED-64M
	7
	6.01.00.18
	rdf
	BX17 - Hub 24


	
	
	
	
	
	
	
	
	
	
	

	Blue Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	2R
	MC5FJ02061
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	2
	6.01.00.18
	Core
	BX40 - Hub 01/02

	4R
	MC5FJ02060
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	28
	6.01.00.18
	Edge
	BX40 - Hub 04/05

	6R
	MC5FJ07236
	RDC1
	BX40
	MC5CN04016
	Blue
	ED-64M
	27
	6.01.00.18
	Edge
	BX40 - Hub 07/08

	8R
	MC5FJ02020
	RDC4
	BU26
	MC5TN01562
	Blue
	ED-140M
	26
	6.01.00.18
	Edge
	BX40 - Hub 24

	10R
	MC5FJ01297
	RDC1
	BX40
	MC5CN04016
	Blue
	RD-64M
	22
	6.01.00.18
	Edge
	BX40 - Hub 09/10

	12R
	MC5CI01482
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	3
	6.01.00.18
	Core
	BX40 - Hub 17/18

	14R
	MC5CI01585
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	21
	6.01.00.18
	Edge
	BX40 - Hub 13/16

	16R
	MC5IN02566
	RDC4
	M46
	MC5TN01563
	Blue
	ED-140M
	4
	6.01.00.18
	Core
	BU26 - Hub 

	18R
	MC5FJ02020
	RDC3
	Z44
	MC5CN04016
	Blue
	ED-64M
	20
	6.01.00.18
	Edge
	 

	20R
	MC5IN02562
	RDC1
	BX34
	MC5CN06898
	Blue
	ED-140M
	19
	6.01.00.18
	Edge
	BX40 - Hub 14/15

	Black RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw92r
	MC5FJ21144
	RDC1
	BX33
	MC5TN01409
	Black
	ED-64M
	4
	6.01.00.18
	rdf
	BX33 - Hub 07/08

	rdfsw94r
	MC5FJ21146
	RDC4
	M45
	MC5TN01411
	Black
	ED-64M
	8
	6.01.00.18
	rdf
	BX33 - Hub 24


	DMX/SYMM/CLARION
	
	
	

	DMX/ SYMM
	Serial number
	Location
	Model
	Microcode
	Software
	Modem Details
	
	
	

	1R
	CK284700428
	RDC1
	BX42-44
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	2R
	CK284701227
	RDC1
	BX01-03
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	3R
	CK284701079
	RDC1
	BX06-08
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	4R
	CK284700466
	RDC1
	BX36-38
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	5R
	SA287750107
	RDC1
	BX10
	DMX2000
	5670.73.69
	SYMMIP
	 020 8297 4092
	
	
	

	6R
	SA287750096
	RDC1
	BX19
	DMX2000
	5670.73.69
	SYMMIP
	 020 8297 4093
	
	
	

	7R
	SA287750200
	RDC1
	BX22
	DMX2000
	5670.73.69
	SYMMIP
	 020 8297 4087
	
	
	

	8R
	SA287750442
	RDC1
	BX13
	DMX2000
	5670.73.69
	SYMMIP
	 020 8297 4094
	
	
	

	CX1R
	MSL00040900021
	RDC1
	BX35
	CX600
	?
	?
	 
	
	
	

	9R
	CK287890275
	RDC4
	C04
	DMX3000
	5670.73.69
	SYMMIP
	020 7500 8632
	
	
	

	10R
	CK287890300
	RDC4
	C42
	DMX3000
	5670.73.69
	SYMMIP
	020 7986 9964
	
	
	

	11R
	CK287890293
	RDC4
	F04
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0881
	
	
	


	Service Processors

	Service Processor
	Serial number
	Location
	Model
	IP Address
	Connectrix Manager version
	CEP connection
	Modem Details

	Blue Standby
	 
	RDC4
	M46
	1U
	169.186.192.197
	7.0.2
	srdcfwe13 3/7
	020 7508 0879

	Black Active
	 
	RDC4
	M45
	1U
	169.186.192.68
	7.0.2
	srdcfwe14 3/6
	020 7508 0880

	Blue Active
	 
	RDC1
	BX40
	Laptop
	169.186.192.69
	7.0.1
	srdcfwe10 3/38
	020 8318 0680

	Black Standby
	 
	RDC1
	BX33
	1U
	169.186.192.196 
	7.0.2
	srdcfwe09 3/37
	

	Green Active
	 
	RDC4
	M02
	1U
	 169.186.192.132
	7.0.2
	srdcfwe13 3/2
	020 7500 8738

	Red Active
	 
	RDC4
	M01
	1U
	 169.186.192.133
	7.0.2
	srdcfwe14 3/3
	020 7508 0834

	Green Standby
	 
	RDC1
	BX17
	Laptop
	169.186.192.4
	7.0.2
	srdcfwe10 3/29
	

	Red Standby
	 
	RDC1
	BX04
	1U
	169.186.192.5
	7.0.1
	srdcfwe09 3/30
	020 8318 0509


Appendix B: Cabinet information - CGC

	Red Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	1
	MC5FJ01158
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	1
	6.01.00.18
	Core
	60AN Hub 01/02

	3
	MC5IN02560
	CGC2
	CA95
	MC5TN01558
	RED
	ED-140M
	18
	6.01.00.18
	Edge
	CA95 Hub 07/08

	5
	MC5FJ01267
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	30
	6.01.00.18
	Edge
	60AN Hub 07/08

	7
	MC5FJ01159
	CGC1
	60AN
	MC5CN03485
	RED
	ED-64M
	29
	6.01.00.18
	Edge
	60AN Hub 04/05

	9
	MC5FJ07225
	CGC2
	BW100
	MC5CN03485
	RED
	ED-64M
	25
	6.01.00.18
	Edge
	BW100 Hub 01/02

	11
	MC5FJ01673
	CGC2
	BW100
	MC5CN04635
	RED
	ED-64M
	24
	6.01.00.18
	Edge
	BW100 Hub 03/04

	13
	MC51N01268
	CGC2
	BW100
	MC5CN04635
	RED
	ED-140M
	23
	6.01.00.18
	Core
	BW100 Hub 05/06

	15
	MC5CIN01483
	CGC2
	BW101
	MC5CN07127
	RED
	ED-140M
	20
	6.01.00.18
	Edge
	BW100 Hub 07/20

	Green RDF Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw91C
	MC5FJ21145
	CGC1
	59AN
	MC5TN01410
	Green
	ED-64M
	1
	6.01.00.18
	RDF
	59AN Hub 07/08

	rdfsw93C
	MC5FJ21149
	CGC2
	CA96
	MC5TN01414
	Green
	ED-64M
	5
	6.01.00.18
	RDF
	CA96 Hub 07/08

	
	
	
	
	
	
	
	
	
	
	


	
	
	
	
	
	
	
	
	
	
	

	Blue Fabric

	Switch
	Switch serial number
	Location
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	2
	MC5FJ01182
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	1
	6.01.00.18
	Core
	71CF Hub 01/02

	4
	MC5IN02580
	CGC2
	CB15
	MC5TN01561
	Blue
	ED-140M
	18
	6.01.00.18
	Edge
	CB15 Hub 07/08

	6
	MC5FJ01308
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	30
	6.01.00.18
	Edge
	71CF Hub 07/08

	8
	MC5FJ01183
	CGC1
	71CF
	MC5CN03484
	Blue
	ED-64M
	29
	6.01.00.18
	Edge
	71CF Hub 04/05

	10
	MC5FJ07208
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-64M
	25
	6.01.00.18
	Edge
	CB05 Hub 01/02

	12
	MC5FJ09611
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-64M
	24
	6.01.00.18
	Edge
	CB05 Hub 03/04

	14
	MCF1N01267
	CGC2
	CB05
	MC5CN04634
	Blue
	ED-140M
	23
	6.01.00.18
	Core
	CB05 Hub 07/08

	16
	MC5IN01484
	CGC2
	CB06
	MC5TN06731
	Blue
	ED-140M
	20
	6.01.00.18
	Edge
	CB05 Hub 13/14

	Black RDF Fabric

	Switch
	Switch serial number
	Location
	 
	Connectrix cab
	Fabric
	Model
	Domain ID
	Firmware
	Type
	Hub Port

	rdfsw92C
	MC5FJ21143
	CGC1
	70CF
	MC5TN01408
	Black
	ED-64M
	2
	6.01.00.18
	RDF
	70CF Hub 07/08

	rdfsw94C
	MC5FJ21150
	CGC2
	CB14
	MC5TN01415
	Black
	ED-64M
	6
	6.01.00.18
	RDf
	CB14 Hub 07/08


	DMX/SYMM/CLARION
	
	
	

	DMX/ SYMM
	Serial number
	Location
	Model
	Microcode
	Software
	Modem Details
	
	
	

	1C
	CK284700679
	CGC1
	69AZ
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	2C
	CK284700995
	CGC1
	56AZ
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	3C
	CK284701078
	CGC1
	67BN
	8730
	5567.53.30
	SYMMIP
	 
	
	
	

	4C
	CK284700214
	CGC2
	BW98
	8730
	5567.53.30
	SYMMIP
	020 7516 9101
	
	
	

	5C
	SA287750129
	CGC2
	CB09
	DMX2000
	5670.73.69
	SYMMIP
	020 7516 9095
	
	
	

	6C
	SA287750125
	CGC2
	BW94
	DMX2000
	5670.73.69
	SYMMIP
	020 7516 9097
	
	
	

	7C
	SA287750122
	CGC2
	CB12
	DMX2000
	5670.73.69
	SYMMIP
	020 7519 6812
	
	
	

	8C
	SA287750383
	CGC2
	BW92
	DMX2000
	5670.73.69
	SYMMIP
	020 7516 6803
	
	
	

	9C
	CK287890296
	CGC2
	BC06
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0813
	
	
	

	10C
	CK287890294
	CGC2
	BH100
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0614
	
	
	

	11C
	CK287890298
	CGC2
	AZ07
	DMX3000
	5670.73.69
	SYMMIP
	020 7508 0820
	
	
	

	CX1C
	MSL00040800040
	CGC2
	CA101
	CX600
	 
	 
	 
	
	
	


	Service Processors

	Service Processor
	Serial number
	Location
	Model
	IP Address
	Connectrix Manager version
	CEP connection
	Modem Details

	Blue Standby
	 
	CGC2
	CB15
	1U
	169.186.141.197
	7.0.2
	sol2fwe01 4/10
	 

	Black Standby
	 
	CGC1
	70CF
	1U
	169.186.141.68
	7.0.2
	sol1fwe15 4/10
	 

	Blue Active
	 
	CGC1
	71CF
	Laptop
	169.186.141.69
	7.0.1
	sol1fwe16 4/10
	 

	Black Active
	 
	CGC2
	CB14
	1U
	169.186.141.196
	7.0.2
	sol2fwe02 4/9
	020 7508 0626

	Green Stanby
	 
	CGC1
	59AN
	1U
	169.186.141.4
	7.0.2
	sol1fwe16 4/1
	 

	Red Standby
	 
	CGC2
	CA95
	1U
	169.186.141.133
	7.0.2
	sol2fwe02 4/3
	 

	Green active
	 
	CGC2
	CA96
	1U
	169.186.141.132
	7.0.2
	sol2fwe01 4/2
	020 7508 8025

	Red Active
	 
	CGC1
	60AN
	Laptop
	169.186.141.5
	7.0.1
	sol1fwe15 4/2
	 


Appendix C:

	Command
	Test
	Actual Result
	Expected result
	Additional Comments

	EFCM ConnectrixManager
			
					
	on eusan-mgt1
	Start and login to CGC Red Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Blue Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Green Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Black Fabric
	Connectrix Manager starts, login works and switches can be viewed

					
	on eusan-mgt2
	Start and login to RDC Red Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDC Blue Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDF Green Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDC Black Fabric
	Connectrix Manager starts, login works and switches can be viewed

					
	on eusan-mgt3
	Start and login to CGC Red Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Blue Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Green Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to CGC Black Fabric
	Connectrix Manager starts, login works and switches can be viewed

					
	on eusan-mgt4
	Start and login to RDC Red Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDC Blue Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDF Green Fabric
	Connectrix Manager starts, login works and switches can be viewed

		Start and login to RDC Black Fabric
	Connectrix Manager starts, login works and switches can be viewed

					
		Simultaneously run two sessions on one server to same SP
	Connectrix Manager starts, login works and switches can be viewed

		Simultaneously run two sessions on one server to different SP
	Connectrix Manager starts, login works and switches can be viewed

		Simultaneously run two sessions to single SP on different servers
		Connectrix Manager starts, login works and switches can be viewed
	
			
			
					
	E-mail
	Send test event from CGC Red Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from CGC Blue Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from RDC Red Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from RDC Blue Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from CGC Green Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from CGC Black Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from RDC Green Fabric
	test event e-mail is received by members of *gt uk san auto

		Send test event from RDC Black Fabric
	test event e-mail is received by members of *gt uk san auto


	

	

	

	


Appendix D:

		Firewall Rules
			
						
	CGC
					CSP = Connectrix Service Processor

						
	Source Name
	Source Address
	Destination Name
	Destination Address
	Ports(s)
	Comments

	All CSP CGC
	 
	mailhub-vip.ny.ssmb.com
	162.124.146.243
	smtp (25)
	Outgoing alert Emails from CSP

	All CSP CGC
		All CGC Storage Mgr Serv
		1024-65535
	Outgoing Connectrix Manager traffic

	All CGC Storage Mgr Serv
		All CSP CGC
		1024-65535
	Incoming Connectrix Manager traffic

	All CGC Storage Mgr Serv
		All CSP CGC
		80
	Client side application updates

	All CGC Storage Mgr Serv
		All CSP CGC
		ftp (21)
	Client side application updates

	All CSP CGC
		All CGC Storage Mgr Serv
		575
	Connectrix Manager event notification to client

	All CGC Storage Mgr Serv
		All CSP CGC
		111, 3127, 4023
	ESN Manager & FibreZone bridge communications

						
						
	RDC
					
						
	Source Name
	Source Address
	Destination Name
	Destination Address
	Ports(s)
	Comments

	All CSP RDC
		mailhub-vip.ny.ssmb.com
	162.124.146.243
	smtp (25)
	Outgoing alert Emails from CSP

	All CSP RDC
		All RDC Storage Mgr Serv
		1024-65535
	Outgoing Connectrix Manager traffic

	All RDC Storage Mgr Serv
		All CSP RDC
		1024-65535
	Incoming Connectrix Manager traffic

	All RDC Storage Mgr Serv
		All CSP RDC
		80
	Client side application updates

	All RDC Storage Mgr Serv
		All CSP RDC
		ftp (21)
	Client side application updates

	All CSP CGC
		All CGC Storage Mgr Serv
		575
	Connectrix Manager event notification to client

	All RDC Storage Mgr Serv
		All CSP RDC
		111, 3127, 4023
	ESN Manager & FibreZone bridge communications


	
	
	
	
	
	

	
	
	
	
	
	


	
	
	IP Addresses
	
	

	
	
	
	
	
	

	
	
	
	
	
	

	RDC
	
	
	
	
	

	Management Workstation
	IP Address
	CEP Location
	Cisco
	Card/Port
	Vlan #, Netmask, Default Gateway

	sanuk03-pub
	169.186.201.26
	
	
	
	

	eusan-mgt2
	169.186.223.81
	RDC Floor 1
	 
	 
	 

	eusan-mgt4
	169.186.223.170
	RDC Floor 1
	 
	 
	 

	
	
	
	
	
	

	RDC CSP Floor/Location
	
	
	
	
	

	rdcgreenfabric L4/M02
	169.186.192.132
	4th AX2
	srdcfwe13
	3/2
	42, 255.255.255.192, 169.186.192.129

	rdcblackfabric L4/M45
	169.186.192.196
	4th AX42
	srdcfwe14
	3/6
	43, 255.255.255.192, 169.186.192.193

	rdcredfabric L4/M01
	169.186.192.133
	4th AX42
	srdcfwe14
	3/3
	42, 255.255.255.192, 169.186.192.129

	rdcbluefabric L4/M46
	169.186.192.197
	4th AX2
	srdcfwe13
	3/7
	43, 255.255.255.192, 169.186.192.193

	rdcgreenstdby L1/BX17
	169.186.192.4
	1st BL32
	srdcfwe10
	3/29
	9, 255.255.255.192, 169.186.192.1

	rdcblackstdby L1/BX33
	169.186.192.68
	1st BL02
	srdcfwe09
	3/37
	10, 255.255.255.192, 169.186.192.65

	rdcredstdby L1/BX04
	169.186.192.5
	1st BL02
	srdcfwe09
	3/30
	9, 255.255.255.192, 169.186.192.1

	rdcbluestdby L1/BX40
	169.186.192.69
	1st BL32
	srdcfwe10
	3/38
	10, 255.255.255.192, 169.186.192.65

	For Future Reference
	
	3rd AX2
	srdcfwe11
	
	

	For Future Reference
	
	3rd AX42
	srdcfwe12
	
	

	
	
	
	
	
	 

	Vlan 8 <-> Vlan 53
	
	
	
	
	

	Vlan 9 <-> Vlan 54
	
	
	
	
	

	
	
	
	
	
	 


	CGC
	
	
	
	
	

	Management Workstation
	IP Address
	Location
	Cisco
	Card/Port
	Vlan #, Netmask, Default Gateway

	sanuk01-pub
	169.183.21.22
	
	
	
	

	eusan-mgt1
	169.183.26.108
	CGC2 Floor 3 
	 
	 
	 

	eusan-mgt3
	169.183.27.90
	CGC2 Floor 3 
	 
	 
	 

	
	
	
	
	
	

	CGC CSP
	
	
	
	
	

	cgcgreenfabric L3/CA96
	169.186.141.132
	cgc2 AB51
	sol2fwe01
	4/2
	53, 255.255.255.192, 169.186.141.129

	cgcblackfabric L3/CB14
	169.186.141.196
	cgc2 AB68
	sol2fwe02
	4/9
	54, 255.255.255.192, 169.186.141.193

	cgcredfabric L3/CA95
	169.186.141.133
	cgc2 AB68
	sol2fwe02
	4/3
	53, 255.255.255.192, 169.186.141.129

	cgcbluefabric L3/CB15
	169.186.141.197
	cgc2 AB51
	sol2fwe01
	4/10
	54, 255.255.255.192, 169.186.141.193

	cgcgreenstdby TR1/TR2 59AN
	169.186.141.4
	cgc1 TR4 81CW
	sol1fwe16
	4/1
	8, 255.255.255.192, 169.186.141.1

	cgcblackstdby TR1/TR2 70CF
	169.186.141.68
	cgc1 TR3 40DB
	sol1fwe15
	4/8
	9, 255.255.255.192, 169.186.141.65

	cgcredstdby TR1/TR2 60AN
	169.186.141.5
	cgc1 TR3 40DB
	sol1fwe15
	4/2
	8, 255.255.255.192, 169.186.141.1

	cgcbluestdby TR1/TR2 71CF
	169.186.141.69
	cgc1 TR4 81CW
	sol1fwe16
	4/9
	9, 255.255.255.192, 169.186.141.65

	
	
	
	
	
	

	Vlan 9 <-> Vlan 42
	
	
	
	
	

	Vlan 10 <-> Vlan 43
	
	
	
	
	


	
	
	
	
	
	


Appendix E:
Below are the from address strings for the SP config.properties file. It should be noted that the work currently being undertaken is the first of a 3-phase implementation of a LAN design. 

For RDC

Blue Fabric

EmailFromAddress=Connectrix-service.RDC.BLUE@rdcbluefabric.eur.nsroot.net
For CGC

Red Fabric

EmailFromAddress=Connectrix-service.CGC.BLUE@cgcbluefabric.eur.nsroot.net
Note

Should emails not be received due to non-name resolution by DNS, the name after @ should be deleted and the IP address 162.124.146.243, for example:

 EmailFromAddress=Connectrix-service.RDC.GREEN@162.124.146.243
Appendix F:

If the data cannot be transferred on to the new service processors the following accounts will need to be added:

sa47183 - Salauddin Ahmed - Admin

cc83851 - Chris Calyton - Operator

sh93900 - Stephen Hopkins - Operator

cw93752 - Carl Woolward - Admin

gr40692 - Graham Rodell - Admin

ph47197 - Paul Haynes - Admin

md25176 - Jadev Dad - Admin

cb21507 - Colin Bradley - Operator

dc91175 - David Coles - Admin
Appendix G:

The following ports are ISL’s between Switch16R and 8R, BAU will need to block  the ports on Switch8R prior to remediation work, Oliver Cabling will need to de-patch the temporary cables installed between Switch16R and 8R as below – once complete BAU will need to Unblock these ports.

	Switch16R/Port
	TO
	Switch8R/Port to be blocked

	0
	>>
	19

	8
	>>
	44

	12
	>>
	49

	20
	>>
	56

	24
	>>
	60


Appendix H:

Oliver Cabling will need to de-patch the temporary cables installed between Switch16R and 8R, and re-patch via the permanent infrastructure as below.

	Frame AU30
	TO
	Interlink
	Interlink
	TO
	Cab BU26

	Switch16R/Port
	 
	AU30 - BU26
	BU26 - AU30
	 
	Switch8R

	Port 0
	>>
	Port 18
	Port 18
	>>
	Port 19

	Port 8
	>>
	Port 19
	Port 19
	>>
	Port 44

	Port 12
	>>
	Port 20
	Port 20
	>>
	Port 49

	Port 20
	>>
	Port 21
	Port 21
	>>
	Port 56

	Port 24
	>>
	Port 22
	Port 22
	>>
	Port 60


Appendix J:

	DMX 7C
	WWN
	Switch 14C port
	Comments

	12aA
	5006048449ADFA8B
	88
	

	12bA
	5006048449ADFA9B
	86
	

	12cA
	5006048C49ADFA8B
	92
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