
Storage Optimisation Programme – Weekly Meeting Minutes.

Date: 19th October 2006
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1. General Overview

No update

2. NAS Filer EOL 

· Following the availability of additional storage, SA’s required to perform migrations. This will take 16 weeks and will take us past March-07.  Possible issue as there are currently no resources budgeted to work on this past Q1 2007. SA managers are aware of delay.  Issue to be raised back to Fincon regarding 2 months delay = additional costs.  Recruitment process now at interview stage.

· Netapps have agreed to support out-of-warranty kit until Mar-07, as we are buying new kit.

· 25Tb to be refreshed.

· Project back to Green.

· Schedule slippage from Nov 06 to Jan 07 for implementation of infrastructure and handover to SA’s.  Now trying to implement systems before change freeze, with delivery of kit in the 1st week of November.  GTS will be expected to have the environment ready so that handover to SA’s can take place prior to change freeze.

· PO’s have been raised and faxed to vendors.  Netapps kit ready.  Still on target for 11 Dec to handover to SA’s.

3. NAS Capacity Growth

· Information for NFS layouts now received for Dev, UAT & Prod environments. Delayed due to still awaiting information from Andrew Lock for GTE.  If this remains the case by the end of the week the BPA information will be used instead. 90% of info now received. Handover in 2 wks will be based on information hat has been received.
· Production and COB to be scheduled for end of October.  
· Test environment ready now, Production to be ready for 31 Oct 06
4. SAN Management Tools - London
· Controls Issue:  The required list of required deliverables from controls is now being tracked on the Global call. David forwarded Vivek evidence that ECC needs to be in CSI.  Still being progressed.

· The remaining high level work breakdown structure is now out of date and needs to be re-worked by Kathy and Dave.

· Deployment of pilot agents  - now completed for Sun and Wintel.

· Implementation of formal reporting

· Production acceptance

· Ronya made decision for regional reporting.  Now looking into buying 2 SQL Server 2000 licences to create the environment required to produce the reports.  Testing will also be done locally. Working with P2P to acquire hardware. Quotes received from purchasing for licenses.
· AIX and HP testing has issues – AIX ECC will not work with LPARS. EMC has RPQ ( request price quotation) against this. Colin investigating Vivek & U.S.

· Graham is organising deployment pilot on HP servers.  Requests have been sent to Tomasz in Poland.  Kathy still chasing for movement on HP pilot deployment.

· UNIX servers have a stability issue   Suggested workaround is now to put 2 of the servers into production and keep 2 pre-production, where they can be upgraded to SP4 and monitored for any issues. Kathy chasing. SUN investigating.  Unstable until SP4 upgrade.  None are currently in production due to additional issues.  Upgrading in 2/3 weeks time.

· Work has begun with SA’s for rollout plan. Integration team have written Post-install scripts, which are now being tested.  Colin working on this – going to project boxes initially. No rollout now planned until SP4 upgrade.  David to Speak to Penta regarding the scripts
· Need to also focus on database agent deployment. First step is to identify which servers need DB agent to be deployed to them. Suggestion was to use ConfigDB for UNIX and to speak to Tom for the Wintel servers. Dave has spoken to Paul Cornish but needs to speak to other DBA’s
· SANScreen: Now in production..

· Graham arranging testing for 6 failed logins. No longer required – existing security is sufficient.
5. SAN Management Tools - Germany
· David has also engaged with purchasing on production of statement of work.  Gary has provided a copy to David.  Meeting was held to review.

· Second meeting to kick off design phase to be scheduled with Zerrin, Javed, Gary & Carl.

· Now starting design phase.

· Gary to check statement of work and get back to Dave by end of week.  Now completed – awaiting confirmation of resources from Meerbusch.

6. SAN Symm-5 Retirement
· Phase 1 now complete. Project now handed over to Dave Westcott
· Phase-1 lessons learnt piece now completed.  Kathy has collated and distributed all issues/lessons collected.
· Phase 2 is Storage Hosted Across Multiple Symms (SHAMS!). Further meeting to be scheduled.
· Stack upgrade element is being pushed to 2007.
· Gary to raise a MARS issue for SANStack level issue. Process has started – CAP dates required.  Initiation docs raised

7. Extended Email Storage

· 1st Design meeting held 27 Sep 06.  Requirements docs have been completed by messaging – now to be completed by rest of team before passing back to engineers. Requirements document now in place. With Ian Adams for approval and engineers for comments.  Further design meeting to be set up.

· Need to decide on type of storage to be used. Carl will produce a table showing the cross-function between the two types on the table (NAS or CAS) ready for the design workshop.  Ongoing. Carl advised CAS for compliance – NAS for archiving.  NAS is 100 times faster than CAS. Will possibly require both environments.  Carl to contact U.S retail to compare storage types.  Gary requested that this information be put into a document.  Also requested considerations of how it will interact with exchange 2003 project.

· Statement of work has been agreed by Ian, but not yet approved by purchasing – delayed by procurement. Still querying statement of work. Meetings continue to be held.

· Firm link now in place between email/archiving/exchange 2003 projects.

8. Demand Management

· High-level timelines were originally agreed as follows:

· Definition of requirements of process

· Review the US process (documentation received).

· Gap Analysis

· Definition of new process

· Advertise new process.

· Go live!

· Sessions arranged for next week. 1st As Is session held yesterday. Mainly covering demand management processes. 21 issues raised so far.  Second As Is session held 19/10/06. Completed demand mgmt piece.  Should be session will be held for demand mgmt issues before starting the As Is on the further 2 areas.
· Requirements docs completed and sent to Gary.
9. Storage Reclaim

· A PIF has been written and submitted for an initiative to look at formalising Storage Reclaim processes as an enabler project under the Storage Optimisation programme. It will be formally initiated today.

· Part of As is / Should be sessions.  See update on item 8.
10. Storage BAU Process Re-engineering
· This is required due to the introduction of the new toolsets of SANScreen and ECC, which will potentially fundamentally change the working practices of the SAN BAU team.

· Part of As is / Should be sessions.  See update on item 8.

11. Data Migration
· A PIF has been written for an initiative to look at formalising Data Migration processes as an enabler project under the Storage Optimisation programme.

· The PIF is with Carl to review. David has requested that this be agreed to be submitted by Tuesday 1st August.  Carl has agreed the PIF to proceed.
· Carl has requested a requirements document. This will result from the CRW.
· There are 2 potential products – Softek Replicator & Open Replicator. 
· Not yet initiated – DW to raise.
12. Deployment of low cost storage options
· It was decided to go for DMX-3 rather than Clarion.  It is RAID 5 non-SRDF.
· PAAD has been approved now moving on to promotion of design document. Now 80% complete for distribution to streams.  To be completed this week. 
· First project meeting held with streams.
· EMC have dropped purchase price by $1MM
· Orders in place for cabling, floor strengthening and additional power
· CRW was 2 weeks ago. EMC and streams attended.
· MTE has now been fully approved.
· Brett to provide DW with date as to when low cost storage will be available
· Design documents have been revised and sent out today for approval. Gary & Javed to make some amendments.
· Global procurement have not approved the open scale option. Now resolved – opting for one off payment.  Equipment now delivered. 
· Mid November hand over to BAU. 8 Nov fibre handover from IBM.
· Problems with attendance to meetings.
· No concerns /issues from Carl/Javed.
· One pager to be sent to Frank Bevacqua today on purchasing on demand option.
13. Application Profiling
GB

· Needs to be looked into regarding what applications we have and what can be used on low cost storage.
· Requires work with the business to put a process and scorecarding in place to assist in identification of requirements and suitability.
· Vendors to met with Javed . Further meeting to be scheduled. Dave to attend.
· Brett now clear that this is not a separate project.
· Javed to arrange meeting with EMC. Colin, Brett , Carl and Gary to attend.
· Workflow process needs to fit into MTE.
Other

· No GDCS PSR for this project as yet.

14. Documentum
· Documentum: John Kurau has spoken to David regarding Documentum as a project with Storage Optimisation benefits. Gary and Carl both suggested it should form part of the SO programme – if only from a tracking perspective. Sponsor would be Ian Adams. Gary offered to pilot Documentum for his area. 

· Steve, Dave, Gary & John held a meeting and agreed the approach to be taken - Pilot deployment in TI for 2006 and ongoing small projects in 2007 for the businesses.

· Gary requested bringing this forward again as he has urgent requirements from HR for a document management system.

· Dave Westcott advised Gary that he and Steve Andrews diaries are up to date. Gary to set up a meeting/ demo.  To be set up for 20/10/06.

15. AOB
· David to escalate to PMO management a potential issue regarding the changes to the procurement process as this caused delays and problems to NAS EOL, NAS Capacity, Extended Email and Low Cost Storage projects.

· Detailed notes to be sent to Dave for each internal project effected.  Details still need to be forwarded to Dave.

Next Meeting:  26th October 2006

Location: Room R, 24th Flr, CGC2

Dial In:  01452-586935  pin 643565
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