## Cover Sheet
Citi / HDS Operations Review Meeting Notes
Date | 2010-01-20
Meeting Number | 83
Attendees | Nigel Chilcott (Citi) | NC
| Tim Robinson (Citi) | TR
| David Coles (Citi) | DPC
| Alex Eaton (HDS) | AE
| David Boorman (HDS) | DB
| David Smith (HDS) | DS
| Mike Collins (HDS) | MC
| Steve Twene (HDS) | ST
Distribution
Citi SAN Support dlist
Citi EMEA SPIT dlist
| Gary Battersby (Citi) | GB
| Ade Okusanya (Citi) | AO
| Carl Williams (Citi) | CPW
| Charles Bougon (HDS) | CB
| Jeff King (HDS) | JK
| Jennifer Antenucci (HDS) | JA
| Joseph Higgins (HDS) | JH
| Mike Thompson (HDS) | MT

## File Notes
File Notes |  |  | Open | 25 |  | Title | Citi / HDS Operations Review Meeting Notes
|  |  | Closed | 257 |  | Date | 2010-01-20
|  | Attendee list - see cover sheet | Pending | 9 |  | Number | 83
Ref No | Date Identified | Item Description | Case Number | Owner | Action Taken | Impact | Current Status | Last Updated | Date Closed | Cross ref to | Test | Open | Closed | Pending Closed
Production USP-V
1 | 2008-05-02 | Remote access |  | SM | CPW is arranging firewall change to resolve IP address remote access issue. Going through 3 approval process. Change is happening week commencing 16/06/08. 16-June-08 Change has been requested of external firewall providers. Further 2 week period before change is made. 14-07-2008: Change request has been delayed again. No estimated completion date available. 08-08-08: Firewall change was deployed this week but was unsuccessful. CPW/JB are following up on getting change redeployed. 18-08-2008 Firewall change made again, HDS to test changes SecureWords access to be arranged by JB 29-08-2008: JB & RS will arrange testing of the firewall change today. 08-09-08: Firewall change has been made. JB has partially tested changes. More test required once secondary SVP has been replaced 24-11-08: SM to arrange access to RDC to resolve secondary SVP issue on 29/30-11-08 01-12-08: Change freeze applied by Citi which meant the change request was cancelled. Work rescheduled to 6-7 Dec 05-01-09: SecureWords issue has been resolved and remote access has been tested successfully. | HDS TRC have made a work around until change is completed | Closed |  | 2009-01-05
2 | 2008-06-30 | Remote access - HiTrack RACC via HTTPS |  | CPW | earlier data removed for brevity 21-10-09: Meeting between Citi & HDS held on 16-10. Update due on 23-10-09 25-11-09: Revised specifications are with Citi to approve 06-01-10: Code is scheduled to be released to CATE this week 13-01-10: Code was delivered to CATE as planned 27-01:10: Citi are testing code, no implementation date yet. |  | Open | 2010-10-27
3 | 2008-04-17 | HiTrack fault reporting |  | SM | HDS HiTrack fault reporting using single US Citigroup web proxy to report faults. 14-07-2008: Dependant on firewall change mentioned in item #1 08-09-08 Post firewall changes made in item 1, SM needs to update HiTrack configuration accordingly. 15-09-08: Scheduled for 17-09-08 but is pending Citi emergency change freeze 29-09-08: Not done during SVP replacement due to lack of time. SM will update this remotely and obtain SecureWords details from BAU team 09-10-08: SM has scheduled this work for 10/10/08 03-11-08: Work has been completed |  | Closed |  | 2008-10-03 | 1
4 | 2008-04-17 | EMEA / US Remote Access |  | JB / JD | EMEA HDS Remote access servers configured to only be able to access EMEA arrays. Likewise, US HDS remote access servers can only access US Citigroup HDS arrays. Request to make any to any access available for redundancy.14-07-2008: JB to liaise with JD to resolve. 29-08-2008: JB to liaise with JD to confirm this is no longer required due to this access method being retired at end of 2008 08-09-08: JB has confirmed with JD this action no longer needs to be acted upon |  | Closed |  | 2008-09-15
5 | 2008-05-02 | Two (2) weeks onsite support post go live |  | MC | HDS to supply onsite resource post go-live week commencing 9th June |  | Closed |  | 2008-06-02
6 | 2008-04-11 | ETrust to accept syslog data from HDS environment |  | JB | Citi to configure ETrust to accept syslog data from HDS environment. JB to speak to Fiaz. Configuration successful in test environment. Update to Production ETrust environment scheduled for 30/05/08. ETrust successfully configured week commencing 02 June 2008 | Cannot go in to Production without ETrust accepting data | Closed |  | 2008-06-02
7 | 2008-04-18 | HUR Training for Citi personnel |  | MC / JD | 24-11-08: GB is raising paperwork with Alistair Grant for agreement 01-12-08: GB did not get an opportunity to speak to Alistair Grant. 18-12-08: GB has assured HDS UK Sales Director of PO will be supplied week commencing 22-12-08 23-12-08: No PO received 05-01-09: No PO received 12-01-09: GB has asked MC to provide quote with revised ate to present to Approvals committee on 15-01-09 19-01-09: MC has not been able to obtain update from GB as yet following the meeting on 15-01-09 26-01-09: GB missed approval slot on 15-01-09. MC to chase GB 16-02-09: MC advises PO is due w/c 23-02-09 24-02-09: MC advises PO is due this week 25-03-09: JD advises P2P has been raised. Now with Fincon for approval 03-04-09: JD advises PO approval is with Alistair Grant 26-04-09: JD advises PO is approved and is with Procurement 21-05-09: PO received. Item closed |  | Closed |  | 2009-05-21
8 | 2008-06-16 | Two (2) weeks onsite support post go live |  | MC | In light of delays to allocate systems for HDS storage, Post go-live onsite support has been suspended from COB 16 June 2008 as there is not sufficient work to do. No further requirement for post go live support |  | Closed |  | 2008-07-07 | 5
9 | 2008-05-09 | Installation guide |  | JB / JD / CPW | Installation guide for replicated environment completed. Requires approval from JD / CPW. Awaiting feedback from CPW. Additionally requires input on ETrust. 14-7-2008: JB to chase with CPW |  | Closed |  | 2008-08-08
10 | 2008-06-02 | Process Control Manual |  | ST / TR | earlier data removed for brevity 07-10-09: PCM draft sent to TR. ST continuing familiarisation 14-10-09: Familiarisation ongoing 21-10-09: AO, CPW & SA familiarisation outstanding. TR advised to send final reminder and then close by 30-10-09. 2nd draft of PCM issued by ST. Review of PCM by BAU team required. 04-11-09: ST to send PCM to Juliet McMillan for review. 11-11-09: Document reviewed and accepted. Close item |  | Closed |  | 2009-11-11
11 | 2008-07-14 | Process Control Manual - Activity logging (ETrust) |  | RS / MT | 24-11-08: No progress. AE to raise with GB 01-12-08: AE raised with JD. No progress so far. 09-12-08: Ade Okusanya has taken ownership of this item from Fiaz Mir. AO has escalated to GB to arrange meeting with ETrust team. No date for meeting with ETrust team yet scheduled 26-01-09: No progress. SA to raise with GB due to the compliance implications 16-02-09: SA has received no feedback from GB as yet 25-03-09: Storage team is being audited in July and this could be an issue. JD now owns action. 03-04-09: JD has been liaising with David Ellis of Compliance team to progress this 26-04-09: Sarah Gunn has taken David Ellis' role. No further progress 21-05-09: Citi are actively working on the issue. Will call on HDS when required 04-06-09: AO requested dial-in to FDC/RDC with exact date and time 11-06-09: Completed 09-06-09 |  | Closed |  | 2009-06-11
12 | 2008-05-02 | Citi HDS weekly storage review meeting with BAU team |  | SA | Citi to confirm attendance of HDS at weekly storage review meeting on Monday at 12pm. Meeting will have to be separate from EMC. SA / JD to confirm timing. 02/06 Meeting will be at 12:45pm on Monday. SA to issue meeting invite. 16-June-08 Meeting invite sent by SA |  | Closed |  | 2008-06-16
13 | 2008-05-02 | Citi HDS weekly storage review meeting with Integration team |  | JD | JD to issue meeting invite for integration team. Understood to be at 10:30am on Monday mornings. 07-July-2008: Meetings arranged with JD |  | Closed |  | 2008-07-14
14 | 2008-04-18 | SVP activity logging |  | JB | Can all activity on the SVP be tracked in a tamper proof log. JB to detail what data is sent to syslog server. JB to liaise with Fiaz to investigate what information is reconciled with ETrust. JB to confirm syslog data is mapped to ETrust data. 02 June 2008: JB awaiting information from Fiaz Mir. 07-July-2008: FM is to speak to Piotra today to obtain information. 14-7-2008: Every detail is logged and hence no detail is required from Piotra. |  | Closed |  | 2008-07-28
15 | 2008-05-16 | HDS Service Catalogue |  | JD / SA | Service Catalogue for HDS storage requires definitions and impacts of selecting HDS storage. Examples include UAT being non-replicated but PRD being replicated. 16-June-08: Service catalogue has been sent to ST & JD for review. 07-July-2008: SA advised not required now. |  | Closed |  | 2008-07-14
16 | 2008-06-16 | HDS Service Catalogue - replicated storage |  | MC / JA | MC to arrange conference call with JA and Gary Johnson regarding service catalogue for replicated environments. |  | Closed |  | 2008-07-28 | 14
17 | 2008-12-23 | SecureWords Token Access |  | SM / RS | Citi supplied SecureWords Tokens are only intermittently providing access. HDS & Citi working to resolve access 05-01-09: SecureWords access resolved and tested |  | Closed |  | 2009-01-05
18 | 2009-04-03 | Dial-in Audit |  | RS / SA | Citi have requested HDS to dial-in to EMEA USP-Vs to permit Citi to check the dial-in access is recorded. HDS completed the dial-in access. Citi to confirm the dial-in has been recorded 26-04-09: Awaiting feedback from SA. RS to chase 21-05-09: Merged with item 11 |  | Closed |  | 2009-05-21
19 | 2009-04-03 | Dial-in Access by Customer Engineers |  | ST / SA | earlier data removed for brevity 04-11-09: New safe word cards are not providing full access to USP-V network. ST to follow up with Simon McDermaid 18-11-09: SM is not aware of the previous issue. ST to raise with Sal Ahmed 25-11-09: ST raised with SA. SA has requested additional ACLs required for USP-V access 02-12-09: SA has provided additional ACLs. One card works correctly, 1 card does not. SA to follow up 09-12-09: Changes required by SA still open 16-12-09: ST to chase SA 06-01-10: ST tested cards from SA. All working fine. Close item |  | Closed |  | 2010-01-06
20 | 2009-06-04 | HTnM installation |  | RS | Installation of Tuning Manager at RDC 6.0 failed. RS & TR working with support to resolve issue 11-06-09: Case escalated to factory in Japan 08-07-0: Installation completed |  | Closed |  | 2009-07-15
21 | 2009-07-29 | Antivirus installation on USP-V 18850 SVPs |  | DB / ST | earlier data removed for brevity 14-10-09: EPO being rolled out to SVPs this week 21-10-09:EPO rolled out was incompatible version. A new version was applied to 75189 successfully Further installations ongoing. 04-11-09: TR advises to run without EPO structure until issue can be resolved 11-11-09: Various work undertaken. See case # EUC1080221 for further details 18-11-09: AV is applied to SVPs in RDC. FDC SVPs ongoing 25-11-09: SVP fail-over required to take dump for analysis. Will be combined with ucode upgrade work 02-11-09: ST has raised with HDS support to investigate why SVPs are rebooting. 16-12-09: AV installation complete. Close item |  | Closed |  | 2009-12-16
22 | 2009-07-29 | Certification of v6.2 software suite |  | AE | earlier data removed for brevity 18-11-09: CATE are awaiting packaging of 6.2 applications to allow certification 02-12-09: TR to raise with CATE 06-01-10: HTSM is certified but dependant on other 6.2 components 13-01-10: AE to confirm with JH 20-01-10: HRpM 6.2 is not certified. AE to confirm interoperability of HDvM 6.2 with HRpM 6.0 27-01-10: CATE have advised March/April timeframe for certification of HRpM v6.2. NC will raise with CATE management at their meeting due on 28-01-10. AE confirmed interoperability of v6.2 and v6.0. |  | Open | 2010-01-27
23 | 2009-09-23 | Site access |  | Information Only | Delays in responding to the san.support@citi.com email address is causing delays to HDS customer engineers access to Citi data centres. 30-09-09: DPC has raised this with BAU team 07-10-09: ST had to chase access for CE access to RDC 21-10-09: Recent requests have been dealt with promptly. Close item |  | Closed |  | 2009-10-21
24 | 2009-09-30 | Statistics for thin volumes |  | ST / TR | TR advises usage statistics for volumes provided from the CLI are not thin aware. ST to confirm this is addressed in HDvM 6.2 07-10-09: HDvM 6.2 provides more data but not all which is required. ST & TR to document required data for PER 11-11-09: Citi advised to park until return of TR from vacation 02-12-09: TR will look in to this during change freeze 06-01-10: TR has obtained preliminary stats. Ongoing. 20-01-10: TR advises this is on hold |  | Open | 2010-01-20
25 | 2009-10-07 | HSCR demo |  | AE | TR has requested demonstration of Hitachi Storage Capacity Reporter 21-10-09: Demo agreed to, TR to obtain list of attendees. Demo will be in December during change free 04-11-09: AE to resend email requesting a date to TR 11-11-09: Provisional date of 09-12-09 18-11-09: Demo invitations sent to GB & TR 06-01-10: Demo took place on 14-12-09. AE to follow up with GB 20-01-10: AE has chased GB to no avail. 27-01-10: All agreed to close this item. |  | Pending | 2010-01-27
26 | 2009-10-14 | Capacity in RDC |  | TR | Additional capacity in RDC is urgently required. TR putting a number of options together. An amount of capacity may move from FDC to RDC 11-11-09: Storage RFP issued. Close item |  | Closed |  | 2009-11-11
27 | 2009-10-14 | CLI workshop |  | AE | TR has requested a CLI workshop like the one that was run in Texas. Preference would be the same instructor 21-10-09: TR advised to schedule training for December during change freeze. DPC to provide list of BAU attendees 04-11-09: AE to send reminder to DPC 18-11-09: DPC advises whole BAU team should attend. 25-11-09: Advised should add Projects to invitation 02-12-09: Course will now be run by UK instructor. Janice Wright (HDS UK training co-ord) is arranging 06-01-10: AE to chase up. 20-01-10: Janice Wright is arranging with Citi |  | Open | 2010-01-20
28 | 2009-11-11 | Remote Access for Charles Bougon |  | DB / ST | Remote access for RDC secondary CE (Charles Bougon) to be arranged 18-11-09: DB/ST to arrange training for CB 09-12-09: Pencilled in for 16-12-09. DS / CB to confirm 16-12-09: Date changed to 21-12-09 due to CB on leave 06-01-10: Training postponed due to poor weather conditions. New date TBC. 20-01-10: training completed |  | Closed |  | 2010-01-20
29 | 2009-11-11 | Environment overview |  | ST / AE | Citi have requested an overview of the current HDS environment for the BAU team to improve their understanding of it. 18-11-09: ST & AE have made draft agenda. To be agreed with Citi 02-12-09: Schedule for during change freeze, AE to resend agenda to BAU team. 09-12-09: morning of 16-02-09 pencilled in. 16-12-09: Overview run. Close item |  | Closed |  | 2009-12-16
30 | 2010-01-20 | USP-V microcode issue |  | DB / TR | An issue with USP-V microcode has been identified with regard to notification of PSU failures. DB will arrange patch of the EMEA USP-V to address the issue 20-01-10: DB to liaise with TR to schedule. Pencilled in for 06-02-10 27-01-10: TR to liaise with DB to confirm 06-02-10 |  | Open | 2010-01-27 |  | 190
30 | 2010-01-20 | Network & Server Performance |  | ST / TR | Replication configuration has to be completed in several stages with a data refresh between each stage. Each refresh takes approximately 50 minutes to run. The whole process of allocating replicated storage can take a whole days effort. This could be worked around by allowing Device Manager visibility of remote arrays but Citi network security does not allow this. The benefit of allowing remote visibility would reduce the fault tolerance of the Device Manager configuration. Citi to investigate network and server performance to improve refresh times. |  | Open | 2010-01-20
31 | 2010-01-20 | EPO Antivirus |  | TR / DB | EPO antivirus installation caused the Service Processor (SVP) to be unavailable (both primary and standby). This was a conflict with Citi's antivirus process which has now been resolved. This will be a problem with new SVPs because the Citi antivirus team need to register the EPO install within 30 minutes of connection to the network. Citi to investigate whether it is possible to exempt SVPs from EPO. 27-01-10: TR confirmed SVPs cannot be excluded from EPO |  | Pending | 2010-01-27
Cisco SAN deployment
32 | 2009-11-18 | Cisco Deployment in CGC |  | Information Only | Citi have verbally committed to purchase Cisco MDS9509/9513 SAN fabric from HDS - thank you 09-12-09: PO received. Close item |  | Closed |  | 2009-12-09
33 | 2009-11-18 | Project personnel |  | Information Only | Citi have advised Paul Haynes and Ade Okusanya will be leading the project from Citi 02-12-09: TR will assist on project whilst AO is on vacation |  | Open | 2009-12-02
34 | 2009-11-18 | Deliveries to CGC1 & CGC2 |  | DB | CPW advises a site survey to be undertaken w/c 23-11-09 of CGC1 and CGC2 25-11-09: Confirmed for 27-11-09 02-12-09: Site survey completed |  | Closed |  | 2009-12-09
35 | 2009-11-18 | HiTrack |  | AO / TR | AO advises Citi will use RDC instance of HiTrack Monitor for hardware fault reporting of the equipment in CGC 25-11-09: AO advises a HiTrack server will be deployed in CGC in contrast to previous information 16-12-09: No progress. AE to chase AO 20-01-10: AO advises HiTrack is installed. DB to provide Site IDs for CGC1 & CGC2 27-01-10: SiteIDs provided to AO |  | Open | 2010-01-27
36 | 2009-11-18 | Delivery of Cisco line cards from DE |  | CPW / DB | CPW & DB to agree on delivery details of the unused line cards from DE 25-11-09: DB to provide serial numbers of line cards to CPW/AO 06-01-10: DB to liaise with PH. 13-01-10: PH has confirmed there is no requirement to move line cards from DE to UK. PH to reconfirm with CPW upon his return from vacation. 27-01-10: Agreed to close item |  | Pending | 2010-01-27
37 | 2009-12-09 | Installation of equipment |  | PH | DB to arrange with PH the installation of equipment once delivered 06-01-10: All installed except for 2 x 9513 remaining 13-01-10: PH advises work is scheduled for eng of January 27-01-10: HDS Engineering resource required for 06-02-10. DB to liaise with PH |  | Open | 2010-01-27
38 | 2009-12-09 | Delivery details |  | DB | DB to provide details of drivers and vehicle to Citi for deliveries to CGC 16-12-09: 1st part of Delivery completed |  | Closed |  | 2009-12-16
39 | 2009-12-16 | Power cables |  | AE | AE to provide to PH power cable details of Cisco equipment in CGC2 06-01-10: Details provided. |  | Closed |  | 2010-01-06
40 | 2009-12-16 | Delivery details - part 2 |  | DB / MC | DB/MC to provide delivery date and driver details for 2nd Cisco delivery to PH 06-01-10: Details provided and delivery completed |  | Closed |  | 2010-01-06
41 | 2010-01-06 | IP Details |  | DB / PH | IP address details required by DB. 27-01-10: Details provided. Close item |  | Pending | 2010-01-27
42 | 2010-01-20 | Cisco License Keys |  | DB | PH advises he is not in possession of the Cisco license keys 27-01-10: DB is working with PH to obtain these |  | Open | 2010-01-27
43 | 2010-01-06 | Remaining items |  | DB / PH | Power up of 9509s - complete Physical installation of 2 x 9513s HiTrack installation Cisco license keys |  | Open | 2010-01-20
"Urgent storage" requirements
44 | 2009-12-02 | Urgent storage capacity |  | Information Only | Citi have given verbal commitment to HDS for the purchase of additional capacity on USP-Vs RDCHDS03 (78378) and FDCHDS03 (78398) |  | Closed |  | 2009-12-16
45 | 2009-12-02 | Engineering resource |  | DB | DB to confirm CE availability for weekend of 12/13 Dec 16-12-09: Installation completed |  | Closed |  | 2009-12-16
46 | 2009-12-09 | Build Configuration Document |  | ST | DB / ST to provide BCD to Citi for review 16-12-09: ST to provide updated BCD to TR 06-01-10: BCD completed |  | Closed |  | 2010-01-06
47 | 2010-01-06 | License keys |  | ST | ST to apply license keys to FDCHDS03 & RDCHDS03 frames 13-01-10: Change request has been made. 20-01-10: Frame licenses complete. HiCommand licenses outstanding 27-01-10: Licenses keys completed. |  | Pending | 2010-01-27
Work over previous period
48 | 2008-06-09 | 7-8th June : None |  | DS | No works 7th-8th June 2008 |  | Closed |  | 2008-06-16
49 | 2008-06-16 | 14-15th June : None |  | DS | No works 14th-15th June 2008 |  | Closed |  | 2008-06-30
50 | 2008-06-30 | 21-22nd & 28-29th June : None |  | DS | No works 14th-15th June 2008 |  | Closed |  | 2008-07-07
51 | 2008-07-07 | 5t-6th July : None |  | DS | No works |  | Closed |  | 2008-07-14
52 | 2008-07-14 | 12-13th July : Additional capacity for VMware |  | DS | Total of 17TB allocated |  | Closed |  | 2008-07-28
53 | 2008-07-28 | 19-20th &26-27th July : None |  | DS | No works |  | Closed |  | 2008-08-08
54 | 2008-08-08 | 2nd-3rd August: None |  | DS | No works |  | Closed |  | 2008-08-18
55 | 2008-08-18 | 9-10 & 16-17 August: None |  | DS | No works |  | Closed |  | 2008-08-29
56 | 2008-08-29 | 23-24 August: None |  | DS | No works |  | Closed |  | 2008-09-08
57 | 2008-09-08 | 6-7 September: None |  | DS | No works |  | Closed |  | 2008-09-15
58 | 2008-09-15 | 13-14 September: None |  | DS | No works |  | Closed |  | 2008-09-22
59 | 2008-09-22 | 20-21 September: None |  | DS | No works |  | Closed |  | 2008-09-29
60 | 2008-09-22 | 27-28 September: None |  | DS | No works |  | Closed |  | 2008-10-09
61 | 2008-10-09 | 4-7 October: None |  | DS | No works |  | Closed |  | 2008-10-13
62 | 2008-10-13 | 11-12 October: None |  | DS | No works |  | Closed |  | 2008-10-20
63 | 2008-10-20 | 18-19 October: None |  | DS | No works |  | Closed |  | 2008-10-29
64 | 2008-10-29 | 25-26 October: None |  | DS | Additional capacity allocated. Remaining capacity of 8.35TB |  | Closed |  | 2008-11-03
65 | 2008-11-03 | 1-2 November: None |  | DS | No works |  | Closed |  | 2008-11-10
66 | 2008-11-10 | 8-9 November: None |  | DS | No works |  | Closed |  | 2008-11-17
67 | 2008-11-17 | 15-16 November: None |  | DS | No works |  | Closed |  | 2008-11-24
68 | 2008-11-24 | 22-23 November: None |  | DS | No works |  | Closed |  | 2008-12-01
69 | 2008-12-01 | 29-30 November: 2TB allocation |  | DS | 2TB of capacity allocated |  | Closed |  | 2008-12-09
70 | 2008-12-09 | 6-7 December: 1.5TB allocation |  | DS | 1.5TB of capacity allocated |  | Closed |  | 2008-12-18
71 | 2008-12-18 | 13-14 December: None |  | DS | No works |  | Closed |  | 2008-12-23
72 | 2008-12-23 | 13-14 December: None |  | DS | No works |  | Closed |  | 2009-01-05
73 | 2009-01-05 | 20-21 & 27-28 December: None |  | SA | No works |  | Closed |  | 2009-01-12
74 | 2009-01-12 | 10-11 January: None |  | SA | No works |  | Closed |  | 2009-01-19
75 | 2009-01-19 | 17-18 January: Microcode applied |  | DS | 60-04-04 microcode applied to USP-V 18850 & 18779 |  | Closed |  | 2009-01-26
76 | 2009-01-26 | 24-25 January: None |  | DS | No works |  | Closed |  | 2009-02-02
77 | 2009-02-02 | 31 January - 01 February: Egg installation |  | DS | Cisco physical installation. No BAU allocations |  | Closed |  | 2009-02-09
78 | 2009-02-09 | 07-08 February: None |  | DS | No works |  | Closed |  | 2009-02-16
79 | 2009-02-16 | 14-15 February: No HDS works. DWDM works |  | DS | DWDM works undertaken successfully by Citi. |  | Closed |  | 2009-02-24
80 | 2009-02-24 | 21-22 February: Microcode upgrade |  | DS | USP-V 75189 upgraded to 60-04-04 |  | Closed |  | 2009-03-26
81 | 2009-03-26 | 21-22 March: Allocations |  | DS | USP-V 75189 Additional capacity allocated. Remaining free space of 92GB |  | Closed |  | 2009-04-03
82 | 2009-04-03 | 28-29 March: None |  | DS | No works |  | Closed |  | 2009-04-26
83 | 2009-04-26 | 11,12, 18,19 April: None |  | DS | No works |  | Closed |  | 2009-05-21
84 | 2009-05-21 | Disk replacement - USP-V 18850 |  | MT | 300GB/15K disk replaced in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-05-21
85 | 2009-06-04 | Disk replacement - USP-V 18850 | EUC1004939 | MT | 300GB/15K disk replaced in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-06-04
86 | 2009-06-11 | None |  | DS | No works |  | Closed |  | 2009-06-11
87 | 2009-07-08 | Disk replacement - USP-V 18850 | EUC1022367 | MT | 300GB/15K disk replaced in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-07-08
88 | 2009-07-08 | DKA replacement - USP-V 18850 | EUC1019966 | MT | Preventative replacement of a DKA in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-07-08
89 | 2009-07-15 | Disk replacement - USP-V 18850 | EUC 1027163 | MT | 300GB/15K disk replaced in USP-V 18850 |  | Closed |  | 2009-07-15
90 | 2009-07-15 | HiTrack dial home - USP-V 18850 | EUC 1028216 | MT | USP-V failed to dial-home. See open case |  | Closed |  | 2009-07-15
91 | 2009-07-22 | 18-19 July |  | DS | No works |  | Closed |  | 2009-07-22
92 | 2009-09-02 | 26/8 - 02/9 |  | DB | Disk replacement |  | Closed |  | 2009-09-02
93 | 2009-09-09 | 03/09-09/09 |  | DB | No works |  | Closed |  | 2009-09-09
94 | 2009-09-16 | 10/09-16/09 |  | DB | Standby SVP failure HiTrack alert. CE confirmed no fault found |  | Closed |  | 2009-09-16
95 | 2009-09-23 | 17/09-23/09 | EUC 1061279 | DB | 300GB/15K Disk replacement in USP_V 18850 |  | Closed |  | 2009-09-23
96 | 2009-09-30 | 24/09-30/09 |  | DB | No works |  | Closed |  | 2009-09-30
97 | 2009-10-07 | 01/10-07-10 | EUC1067834 | DB | 300GB/15K Disk replacement in USP_V 18850 |  | Closed |  | 2009-10-07
98 | 2009-10-14 | 08/10-14/10 |  | DB | No works |  | Closed |  | 2009-10-14
99 | 2009-10-21 | 15/10-21/10 |  | DB | Standby SVP replacement |  | Closed |  | 2009-10-21
100 | 2009-11-04 | 21/10-04/11 |  | DB | SVP AV resolution |  | Closed |  | 2009-11-04
101 | 2009-11-11 | 04/11-11/11 |  | DB | SVP work as discussed in ref# 21 |  | Closed |  | 2009-11-11
102 | 2009-11-18 | 11/11-18/11 |  | DB | SVP work |  | Closed |  | 2009-11-18
103 | 2009-11-25 | 18/11-25/11 |  | DB | SVP work ongoing |  | Closed |  | 2009-11-25
104 | 2009-12-02 | 25/11-02/12 |  | DB | 1) ucode upgrade on RDVHDS03 & FDCHDS03 completed successfully 2) SVP work ongoing |  | Closed |  | 2009-12-02
105 | 2009-12-09 | 02/12-09/12 |  | DB | 1) ucode upgrade on RDCHDS01,2 & FDCHDS02 completed successfully High I/O on Egg system on RDCHDS02 2) SVP in FDC replaced |  | Closed |  | 2009-12-09
106 | 2009-12-16 | 09/12-16/12 |  | DB | Installation work on FDCHDS03 & RDCHDS03 |  | Closed |  | 2009-12-16
107 | 2010-01-06 | 16/12-06/01 |  | DB | No works |  | Closed |  | 2010-01-06
108 | 2010-01-13 | 06/01-13/01 |  | DB | Disk replacement in FDC |  | Closed |  | 2010-01-13
109 | 2010-01-20 | 13/01-20/01 |  | DB | No works |  | Closed |  | 2010-01-20
110 | 2010-01-27 | 20/01-27/01 |  | DB | Standby SVP replacement in FDC & disk replacement |  | Pending | 2010-01-20
Upcoming work
111 | 2008-06-09 | 14-15th June : Project Jupiter |  | SA | First allocation of storage once in to production. Dependant on server patching tasks being complete. |  | Closed |  | 2008-07-14
112 | 2008-06-16 | 21-22nd June : None |  | SA | No works 21st-22nd June 2008 |  | Closed |  | 2008-06-30
113 | 2008-06-30 | 5-6th July : None |  | SA | No works 5th-6th July 2008 |  | Closed |  | 2008-07-07
114 | 2008-07-07 | 12-13th July : None |  | SA | Remaining Jupiter environment data and additional VMware requirements |  | Closed |  | 2008-07-14
115 | 2008-07-14 | 19-20th July : None |  | SA | Additional VMware requirements aprox 5TB |  | Closed |  | 2008-07-28
116 | 2008-07-28 | 2-3rd August : 2TB per month (total 10TB) will be allocated to VMware environment |  | SA | Additional VMware requirements 2TB per month 08-09-08: Requirements have reduced due to slower take up of VMware environment. |  | Closed |  | 2008-10-13
117 | 2008-08-08 | Allocations per 28-07-08 are confirmed |  | SA | Allocations per 28-07-08 are confirmed |  | Closed |  | 2008-08-29
118 | 2008-08-18 | Potential 1TB allocation |  | SA | Potential 1TB allocation 08-09-08: Not allocated |  | Closed |  | 2008-09-15
119 | 2008-09-08 | 13-14 Sept: None |  | DPC | No scheduled works |  | Closed |  | 2008-09-15
120 | 2008-09-15 | 20-21 Sept: None |  | DPC | No scheduled works. Emergency change freeze in place |  | Closed |  | 2008-09-22
121 | 2008-09-22 | 28-29 Sept: None |  | SA | No scheduled works. Emergency change freeze extended |  | Closed |  | 2008-09-29
122 | 2008-09-22 | 28-29 Sept: None |  | SA | No scheduled works. End of quarter change freeze 09-10-08: End of quarter change freeze ended. |  | Closed |  | 2008-10-13
123 | 2008-10-09 | 11-12 October: None |  | SA | Two allocations of 5TB proposed 13-10-08: 1 of 5TB allocation likely on weekend of 18-20 October 20-10-08: No storage allocated previous weekend, 5TB possible 25/26-10-08 29-10-08: VMware provision now delayed |  | Closed |  | 2008-10-29
124 | 2008-10-29 | 1-2 November: None |  | SA | Further non-VMware allocations pending 03-11-08: further allocations will be made on an as needed basis |  | Closed |  | 2008-11-03
125 | 2008-11-03 | 8-9 November: None |  | SA | Further allocations will be made on an as needed basis |  | Closed |  | 2008-11-03
126 | 2008-11-10 | 15-16 November: None |  | SA | No allocations planned |  | Closed |  | 2008-11-10
127 | 2008-11-17 | 22-23 November: None |  | SA | No allocations planned |  | Closed |  | 2008-11-17
128 | 2008-11-24 | 29-30 November: None |  | SA | No allocations planned |  | Closed |  | 2008-11-24
129 | 2008-12-01 | 6-7 December: None |  | SA | No allocations planned |  | Closed |  | 2008-12-01
130 | 2008-12-09 | 13-14 December: None |  | SA | No allocations planned |  | Closed |  | 2008-12-09
131 | 2008-12-18 | 20-21 December: None |  | SA | No allocations planned |  | Closed |  | 2008-12-18
132 | 2008-12-23 | 27-28 December: None |  | DC | No allocations planned |  | Closed |  | 2008-12-23
133 | 2009-01-05 | 10-11 January: None |  | SA | No allocations planned |  | Closed |  | 2009-01-05
134 | 2009-01-12 | 17-18 January: None |  | SA | No allocations planned |  | Closed |  | 2009-01-12
135 | 2009-01-19 | 24-25 January: Egg installation |  | SA | Egg installation phase 1 work |  | Closed |  | 2009-01-19
136 | 2009-01-26 | 31 January - 01 February: Egg installation |  | SA | Egg Cisco installation. No BAU allocations planned |  | Closed |  | 2009-01-26
137 | 2009-02-02 | 07-08 February: None |  | SA | No allocations planned |  | Closed |  | 2009-02-02
138 | 2009-02-09 | 14-15 February: None |  | SA | No allocations planned |  | Closed |  | 2009-02-09
139 | 2009-02-16 | 21-22 February: Microcode upgrade |  | SA | No allocations planned 60-04-04 upgrade on USP-V Serial 75189 24-02-09: Completed |  | Closed |  | 2009-02-24
140 | 2009-02-24 | 28-29 February: Microcode upgrade |  | SA | No allocations planned |  | Closed |  | 2009-02-24
141 | 2009-03-26 | 28-29 March: On going Egg allocations |  | JD | On going Egg allocations 26-04-09 - all allocations complete |  | Closed |  | 2009-04-26
142 | 2009-04-03 | 4-5 April: None |  | JD | No allocations planned |  | Closed |  | 2009-04-26
143 | 2009-04-26 | Upgrade of USP-V 18850 |  | JD | Installation of L1 DKU 21-05-09: Installation complete |  | Closed |  | 2009-05-21
144 | 2009-05-21 | Formatting of 2 Parity groups |  | MT | Formatting of 2 parity groups in USP-V 18850. Format complete |  | Closed |  | 2009-06-04
145 | 2009-06-11 | 13-14 June: None |  | DS | No work planned |  | Closed |  | 2009-06-11
146 | 2009-07-08 | London phase 2 project |  | All | See detailed London phase 2 project section 16-09-09: project completed |  | Closed |  | 2009-09-16
147 | 2009-09-02 | London phase 2 project - drive changes |  | All | change of 146GB to 300GB disk drives in FDC & RDC 16-09-09: work completed |  | Closed |  | 2009-09-16
148 | 2009-09-23 | 23/09-30/9: None |  | DPC | No work planned |  | Closed |  | 2009-09-23
149 | 2009-09-30 | 1/10-7/10: None |  | DPC | No work planned |  | Closed |  | 2009-09-30
150 | 2009-10-07 | 8/10-14/10: None |  | DPC | VIO allocation allocations ST has requested AIX specialist technical support 21-10-09: ST has had call with AIX specialist 04-11-09: VIO work under way. Close item |  | Closed |  | 2009-11-04
151 | 2009-11-04 | 4/11-11/11: None |  | DPC | No work planned |  | Closed |  | 2009-11-04
152 | 2009-11-11 | 11/11-18/11 |  | DPC | SVP / AV ePO ongoing work |  | Closed |  | 2009-11-11
153 | 2009-11-18 | 18/11-25/11 |  | ST | Logical Group Recovery for HDvM & SVP ongoing work |  | Closed |  | 2009-11-18
154 | 2009-11-25 | 25/11-02/12 |  | DB | 60-05-xx microcode upgrade on USP-Vs 78378 & 78398 02-12-09: upgrade completed |  | Closed |  | 2009-12-02
155 | 2009-12-02 | 25/11-02/12 |  | DB | 60-05-xx microcode upgrade on USP-Vs 18850, 18779 and 75189 09-12-09: upgrade completed |  | Closed |  | 2009-12-09
156 | 2009-12-09 | 09/12-16/12 |  | DB | upgrade of RDCHDS03 and FDCHDS03 with additional disk capacity |  | Closed |  | 2009-12-16
157 | 2009-12-16 | 16/12-06/01 |  | DB | None planned |  | Closed |  | 2009-12-16
158 | 2010-01-06 | 06/01-13/01 |  | DB | None planned |  | Closed |  | 2010-01-06
159 | 2010-01-13 | 13/01-20/01 |  | DB | None planned |  | Closed |  | 2010-01-13
160 | 2010-01-20 | 20/01-27/01 |  | DB | Disk replacement & SVP replacement |  | Pending | 2010-01-20
161 | 2010-01-27 | 27/01-03/02 |  | DB | SVP replacement |  | Open | 2010-01-27
HDS Announcements / Engineering updates
162 | 2008-05-09 | HDS has announced Hitachi Storage Command Suite v6. |  | AE | AE to provide details to SA/JD. AE provided details on 03/06/2008 |  | Closed |  | 2008-06-09
163 | 2008-06-16 | HDS has announced VTL enhancements for Mainframe environments |  | AE | SA provided contact details for MF StorEng leader as being David Kelvin |  | Closed |  | 2008-06-16
164 | 2008-07-07 | End of life announcements |  | AE | 1) 750GB SATA drive for USP-V & USP-VM and 2) High performance NAS platform 2000 series |  | Closed |  | 2008-07-14
165 | 2008-08-29 | HDS announcements |  | AE | 1) Qualification testing completed with the IBM® z10 mainframe server and Hitachi Universal Storage Platform V & VM 2) Hitachi Dynamic Provisioning (HDP) feature enhancements; Online DP-VOL capacity expansion, TrueCopy pair between DP-VOL and a standard volume, HUR pair between DP-VOL and a standard volume. Minimum microcode 60-03-24-00/00. 3) Hitachi Dynamic Link Manager (HDLM) Advanced 6.0.1 for Windows and Linux introduces new load balancing algorithms based on “least I/O” and “least block” queuing of I/O operations. 4) HUR 3 data centre pass-thru solution eliminating the requirement for data storage at the intermediate site. |  | Closed |  | 2008-09-15
166 | 2008-09-22 | HDS announcements - VMware SRM |  | AE | VMware site recovery manager for USP/USP-V/USP-VM/NSC55 announced. Details sent to Citi by AE |  | Closed |  | 2008-09-22
167 | 2008-09-29 | General Availability Hitachi Data Discovery for Microsoft SharePoint version 2.0. |  | AE | AE to send details of Hitachi Data Discovery for Microsoft SharePoint version 2.0. 09-10-08: AE sent details of HDDS for SharePoint |  | Closed |  | 2008-10-09
168 | 2008-09-29 | Tech-alert: Microcode issue with K series disk drives |  | DS | HDS have advised Citi of a tech alert affecting the USP-V with K series disk drives. USP-V serial 75189 in RDC is affected by this issue. The recommendation is to upgrade the USP-V microcode to 60-03-07. This microcode is not on the Citi certification schedule at present 29-10-08: DS to liaise with SA to arrange upgrade of USP-V 75189. weekend of 8/9-11-08 pencilled in for this work 03-11-08: SM has confirmed work will be undertaken on 08-11-08 from noon. SA to raise change request and access for SM + 1 other. HDS to confirm upgrade methodology to be used. 10-11-08: Upgrade of microcode failed see case EUC905185 24-11-08: Upgrade successful on 23-11-08 |  | Closed |  | 2008-11-24
169 | 2008-10-13 | HDS announcements - AMS2000, Encrypting BEDs, 450GB 15K RPM disks, Rackless USP-VM |  | AE | HDS have announced the following products: AMS2000 - new modular family of products Encrypting Back-End directors for USP-V/VM 450GB 15K disks for USP-V/VM Rackless USP-VM |  | Closed |  | 2008-10-13
170 | 2008-11-03 | HDS announcements - HDvM simulator |  | AE | HDS have announced HDvM simulator. SA has requested a copy of this. 10-11-08: AE has downloaded iso image but needs to provide to SA on DVD 9-12-08: AE has provided DVD to SA |  | Closed |  | 2008-12-09
171 | 2008-12-01 | HDS Modular Session |  | AE | HDS are running a Modular lunch and learn session for Citi on 3rd December. BAU and SPIT teams are welcome. |  | Closed |  | 2008-12-09
172 | 2008-12-01 | HDS announcements - Cisco & HCAP StorFlashes |  | AE | HDS have announced availability of: 1) Cisco 8Gbs modules for 9500 directors. 2) HCAP v2.6 which includes compression and other new abilities |  | Closed |  | 2008-12-09
173 | 2008-12-18 | HDS announcements - EBEDs, SSDs, AMS2500, HDP |  | AE | HDS have announced availability of: 1) AMS2500 modular storage array 2) 73GB & 146GB flash drives (SSDs) for USP-V/VM 3) Encrypting Back-End Directors for USP-V/VM 4) HDP zero page space reclamation |  | Closed |  | 2008-12-18
174 | 2008-12-23 | HDS announcements - End of Sale of certain disk drives |  | AE | HDS have announced end of sale of 73GB disk drives for USP-V/VM & AMS and 750GB SATA disk drives for AMS |  | Closed |  | 2008-12-23
175 | 2009-02-16 | HDS announcements - 60-04-13 microcode |  | AE | 60-04-13 for USP-V/VM which has 1 high level counter-measure with regard to DKU un-installation |  | Closed |  | 2009-02-16
176 | 2009-02-24 | HDS announcements - GA of HDS software products |  | AE | GA of Device Manager, Tiered Storage Manager, Replication Manager v6.1 |  | Closed |  | 2009-02-24
177 | 2009-03-26 | HDS announcements - AMS withdrawal from marketing |  | AE | Withdrawal from marketing of AMS200, 500 & 1000 from 30-06-09 |  | Closed |  | 2009-03-26
178 | 2009-03-04 | HDS announcements - 9910/60 support |  | AE | Extension of support of 9910 & 9960 support. Not relevant to Citi EMEA as they do not possess any of these arrays |  | Closed |  | 2009-04-03
179 | 2009-03-04 | HDS announcements - HDS UK Management Organisation |  | MC | Darren Barker has been appointed Regional Sales Director for UK Enterprise South region which includes Citi. Warren Duke remains as UK Sales Director and will continue his engagement with Citi |  | Closed |  | 2009-04-03
180 | 2009-04-26 | StorFlashes |  | AE | Various StorFlashes sent to Citi |  | Closed |  | 2009-04-26
181 | 2009-04-26 | USP-V microcode v05 |  | AE | v05 Microcode due to be GA'ed in June. Offers some HDP enhancements 15-07-09: v05 GA'ed on 10-07-09 |  | Closed |  | 2009-07-15
182 | 2009-04-26 | HDS StorFlash |  | AE | GA of Device Manager (HDvM) & Tiered Storage Manager (HTsM) version 6.2 |  | Closed |  | 2009-07-22
183 | 2009-09-02 | HDS StorFlash |  | AE | End-of-life process for certain Modular disk drives |  | Closed |  | 2009-09-02
184 | 2009-09-02 | HDS StorFlash |  | AE | Hitachi NAS GA announcements |  | Closed |  | 2009-09-09
185 | 2009-10-21 | HDS StorFlash |  | AE | GA of upgrades to HSCR & HSVR. Very limited availability of certain disks on USP storage. EMEA does not have USP arrays. |  | Closed |  | 2009-10-21
186 | 2009-10-21 | HDS StorFlash |  | AE | GA of 400GB SSD disks for USP-V and HDP enhancements for AMS |  | Closed |  | 2009-11-04
187 | 2009-11-18 | Cisco fabric for CGC |  | AE | Citi have verbally committed to purchase Cisco MDS9509/9513 SAN fabric from HDS - thank you |  | Closed |  | 2009-11-18
188 | 2009-11-25 | HDS StorFlash |  | AE | GA of Hitachi Content Platform v3.0 |  | Closed |  | 2009-11-25
189 | 2010-01-06 | HDS StorFlash |  | AE | GA of 3 HiCommand v6.3 products |  | Closed |  | 2010-01-06
190 | 2010-01-13 | USP-V microcode issue |  | AE | An issue with USP-V microcode has been identified with regard to notification of PSU failures. DB will arrange patch of the EMEA USP-V to address the issue 20-01-10: Moved to Production USP-V section |  | Closed |  | 2010-01-20
191 | 2010-01-27 | USP-V microcode issue |  | AE | A performance issue with 60-06-06 microcode has been identified when using HDP pools. Citi have not certified 60-06-06 code so does not apply to EMEA estate |  | Pending | 2010-01-27
Citigroup Announcements / Global Data Centre Strategy
192 | 2008-06-02 | Partial change freeze is in place for equities due to a COB test |  | Information Only | 09/06 change freeze finished due successful COB test |  | Closed |  | 2008-06-09
193 | 2008-06-09 | SRDF/A on FDC/RDC infrastructure is due to go live on 20 June 2008 |  | Information Only |  |  | Closed |  | 2008-06-09
194 | 2008-06-16 | Change freeze for 1 week at end of quarter due. Exact dates not known at the meeting |  | Information Only |  |  | Closed |  | 2008-06-30
195 | 2008-06-30 | None |  | Information Only |  |  | Closed |  | 2008-07-07
196 | 2008-07-07 | None |  | Information Only |  |  | Closed |  | 2008-07-14
197 | 2008-07-14 | None |  | Information Only |  |  | Closed |  | 2008-07-28
198 | 2008-07-28 | None |  | Information Only |  |  | Closed |  | 2008-08-08
199 | 2008-08-08 | BAU will be taking on Cisco + SRDF support on 22-08 and SRDF/Star mid-September |  | Information Only |  |  | Closed |  | 2008-08-29
200 | 2008-08-08 | COB Test in September |  | Information Only | COB test of RDC fail-over to CGC scheduled for 13-09-08 15-09-08: COB test completed successfully |  | Closed |  | 2008-09-22
201 | 2008-08-29 | None |  | Information Only |  |  | Closed |  | 2008-09-08
202 | 2008-09-08 | None |  | Information Only |  |  | Closed |  | 2008-09-15
203 | 2008-09-15 | Emergency change freeze |  | DPC | Emergency change freeze until 7am 18-09-08 |  | Closed |  | 2008-10-09
204 | 2008-09-15 | Quarter end change freeze |  | SA | Scheduled quarter end change freeze from 26-09-08 to 04-10-08 29-09-08: Quarter end change freeze will run to 06-10-09 inclusively. 09-10-08: Quarter end change freeze finished as scheduled |  | Closed |  | 2008-10-13
205 | 2008-10-13 | Frankfurt Data Centre |  | SA | Flexcube application has been brought online in the Frankfurt Data Centre |  | Closed |  | 2008-10-13
206 | 2008-10-29 | Christmas change freeze |  | Information Only | Christmas change freeze will be from 15-12-08 to 08-01-09 inclusive |  | Closed |  | 2009-01-05
207 | 2008-11-10 | None |  | Information Only |  |  | Closed |  | 2008-11-10
208 | 2008-11-17 | None |  | Information Only |  |  | Closed |  | 2008-11-17
209 | 2008-11-24 | None |  | Information Only |  |  | Closed |  | 2008-11-24
210 | 2008-12-01 | None |  | Information Only |  |  | Closed |  | 2008-12-01
211 | 2008-12-09 | None |  | Information Only |  |  | Closed |  | 2008-12-09
212 | 2008-12-18 | None |  | Information Only |  |  | Closed |  | 2008-12-18
213 | 2008-12-23 | None |  | Information Only |  |  | Closed |  | 2008-12-23
214 | 2009-01-05 | None |  | Information Only |  |  | Closed |  | 2009-01-05
215 | 2009-01-12 | None |  | Information Only |  |  | Closed |  | 2009-01-12
216 | 2009-01-19 | None |  | Information Only |  |  | Closed |  | 2009-01-19
217 | 2009-01-26 | BAU & SPI teams location |  | Information Only | BAU & SPI teams will be moving to Lewisham in February. Exact date tbc 02-02-09: Date confirmed as 20-02-09 16-02-09: Date postponed until March 26-03-09: teams have moved to Lewisham |  | Closed |  | 2009-03-26
218 | 2009-02-09 | None |  | Information Only |  |  | Closed |  | 2009-02-09
219 | 2009-03-26 | IXE proposal |  | Information Only | Location of IXE Point-in-Time copy is proposed to be changed to FDC 04-06-09: IXE point-in-time is to be located in RDC 08-07-09: IXE project awarded to HDS. Item closed |  | Closed |  | 2009-07-08
220 | 2009-04-03 | CGC2 data centre space reclamation |  | CPW | Citi are considering freeing data-centre capacity within CGC2. There may be an opportunity for HDS to provide equipment and expertise to assist in this requirement. Detailed requirements and scope due 2 weeks' time 22-07-09: Meeting held 15-07-09 22-09-09: CPW enquired to the progress of this. AE advised HDS are awaiting a RFP from Citi for this and the Tech Refresh. CPW to chase GB 09-09-09: MC advises RFP is scheduled to be released week commencing 14-09-09 11-11-09: RFP received. Close item |  | Closed |  | 2009-11-11
221 | 2009-06-11 | Storage team audit |  | Information Only | Citi Project and Operations teams are being audited. JD will be in Warsaw for 1 week commencing 22-06-09 07-08-09: Audit scheduled to finish 10-07-09 15-07-09: Closing at request of JD |  | Closed |  | 2009-07-08
222 | 2009-07-29 | Tech Refresh data |  | AE | Citi are providing revised host and capacity data for tech refresh project. Additionally project is combined with CGC2 exit project 02-09-09: TR has provided requested information |  | Closed |  | 2009-09-02
223 | 2009-09-16 | London phase 2 project |  | Information Only | London phase 2 project completed and delivered 1 day early |  | Closed |  | 2009-09-16
224 | 2009-09-30 | Change freeze |  | Information Only | Change freeze until 23:59 on 06-10-09 07-10-09: change freeze complete |  | Closed |  | 2009-10-07
225 | 2009-10-07 | Christmas Change freeze |  | Information Only | Change freeze 14/12/09 until 07/01/10 13-01-10: Change freeze complete |  | Closed |  | 2010-01-13
226 | 2010-01-06 | SAN Manager |  | Information Only | Nigel Chilcott has been appointed as SAN Manager |  | Closed |  | 2010-01-06
227 | 2010-01-20 | 2010 change freeze dates |  | NC | NC to advise of 2010 change freeze dates 27-01-10: NC has provided dates |  | Pending | 2010-01-27
228 | 2010-01-27 | 2010 change freeze dates |  | Information Only | EMEA PROVISIONAL 2010 QUARTER END FREEZE DATES: Q1 - 29th March to 5th April Q2 - 28th June to 5th July Q3 - 27th September to 5th October |  | Open | 2010-01-27
Open cases
229 | 2008-05-07 | SVP performance with antivirus | EUC 825203 | DS / SM | slow performance of USP-V SVP when Citi's McAfee antivirus scan. HDS advise Citi of exceptions rules to apply to prevent performance issues. 09/06/08 SA advises to close case as resolution is dependant on Citi changing AV rules. 30/06/08 Specific issue has been identified by Citi / HDS. AE to provide details. 14-7-2008 AE has provided details. JB to work with David Coles to resolve. 28-7-2008: David Smith and Simon McDermaid to liaise with David Coles to arrange implementation of new McAfee policies on SVPs 08-09-08: Updated AV policies applied by SM | Very slow performance of SVPs | Closed |  | 2008-09-08
230 | 2008-08-18 | Standby SVP fail | EUC 869594 | SM | 29-09-08: SM attempted to resolve this matter last week and was unsuccessful. SM has been made aware of a microcode fix to address this issue. The fix is included in the next CATE certified microcode (60-03-06). SA agreed to have the 2nd SVP as a cold standby which can be deployed should there be an issue with the primary SVP. 09-10-08: Still pending approval of 60-03-07 microcode. SM to arrange collection of surplus SVPs held at Citi premises 29-10-08: Pending update from DS/SM for date of work 03-11-08: The 3 SVPs have been collected from RDC. The additional SVP at CGC is yet to be collected 10-11-08: Additional SVP at CGC is no on Citi asset register. RS to liaise with CPW to resolve. 17-11-08: RS to take SVP offsite to return to HDS 24-11-08: SVP taken offsite and returned to HDS. SM to arrange secondary SVP installation now microcode upgrade has been completed 01-12-08: SM to deploy secondary SVP on 6-7/12 |  | Closed |  | 2008-12-01
231 | 2008-11-10 | USP-V 75189 microcode upgrade | EUC 905185 | DS / SM | When upgrading USP-V # 75189 the procedure failed. SM took dumps and the cause is being analysed. DS to advise SA of progress. No outage to data has been caused by this. SVP issue was resolved with cabling resolution. See RCA sent to SA. SM to upgrade Microcode on 22/23-11-08 24-11-08: Microcode upgrade completed 23-11-08 |  | Closed |  | 2008-11-24 | 167
232 | 2009-01-27 | 75189: Hi-Track USP V/VM SIMSTANDBY SVP FAIL | EUC941983 | DS | HiTrack SIM alert from USP-V 75189 received. No fault found, case closed | Sev 3 | Closed |  | 2009-02-02
233 | 2009-02-24 | 18850 Hi-Track USP V/VM RIO PATH CLOSED | EUC955650 | DS | HiTrack SIM alert from USP-V 18850 received. Citi confirmed FCIP issues causing issue. Case closed | Sev 2 | Closed |  | 2009-02-24
234 | 2009-02-24 | 18850 Hi-Track USP V/VM RIO PATH CLOSED | EUC956303 | DS | HiTrack SIM alert from USP-V 18850 received. Citi confirmed FCIP issues causing issue. Case closed | Sev 2 | Closed |  | 2009-02-24
235 | 2009-03-26 | 18850 Hi-Track USP V/VM RIO PATH CLOSED | Various | Information Only | Several HiTrack SIM alerts from USP-V 18850 received. Citi confirmed FCIP issues causing issue. Case closed |  | Closed |  | 2009-03-26
236 | 2009-03-26 | HiTrack for Cisco | EUC964298 | DS | HiTrack Monitor v3.9 which is managing the Cisco Directors dial home working intermittently 03-04-09: Cisco's dialling home successfully |  | Closed |  | 2009-04-03
237 | 2009-03-26 | HBSM cases |  | Information Only | HBSM cases removed at the request of JD |  | Closed |  | 2009-03-26
238 | 2009-04-03 | Disk replacement - USP-V 18850 | EUC974998 | DS | 300GB/15K disk replaced in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-04-03
239 | 2009-04-26 | Cisco Power supply failure | EUC986145 | DS / MT | HiTrack alert for failed Cisco power supply. Pending investigation by Citi SAN Support team |  | Closed |  | 2009-05-21
240 | 2009-05-21 | Disk replacement - USP-V 18850 | EUC990258 | DS / MT | 300GB/15K disk replaced in USP-V 18850 (Replicated RDC loan system) |  | Closed |  | 2009-05-21
241 | 2009-06-04 | Tuning Manager installation | EUC1002299 | RS | See case above - case closed |  | Closed |  | 2009-07-08 | 20
242 | 2009-06-04 | Dial-in-test | EUC1007831 | DS / MT | Dial-in test by HDS UK |  | Closed |  | 2009-06-04
243 | 2009-06-11 | HiTrack Cisco alert | EUC1009758 | DS / MT | Automated alert HiTrack Monitor had lost communication with Cisco Director. Appeared to be temporary blip, communication has been restored |  | Closed |  | 2009-06-11
244 | 2009-09-02 | Disk replacement - USP-V 18850 | EUC1048639 | DB | 300GB/15K disk replaced in USP-V 18850 |  | Closed |  | 2009-09-02
245 | 2009-09-02 | HiTrack Health check | EUC1050861 | DB | HiTrack failed to dial-home alert at RDC. Caused by system error HDS. |  | Closed |  | 2009-09-02
246 | 2009-09-09 | No open cases |  | DB |  |  | Closed |  | 2009-09-09
247 | 2009-09-16 | No open cases |  | DB |  |  | Closed |  | 2009-09-16
248 | 2009-09-23 | HDvM Java | EUC 1061506 | DB | Java memory issue 30-09-09: ST working with HDS support. Memory on VM was increased which did not correct issue 07-10-09: Server has been rebooted and problem has not reoccurred. Monitor 14-10-09: Issue has reoccurred. ST has raised with ETRC 21-10-09: ETRC advised of fix but this causes issues to Citi's operational procedures. ST to document issue. 18-11-09: ST has documented issue. AE to raise PER 25-11-09: Moved to PER section. Item closed |  | Closed |  | 2009-11-25
249 | 2009-09-23 | HRpM Time-out | EUC 1045806 | DB | HRpM timeouts when creating pair relationship 30-09-09: Issue resolved but cause still pending investigation 07-10-09: No fault found due to logs having wrapped. Case will be reopened should issue reoccur |  | Closed |  | 2009-10-07
250 | 2009-09-23 | HTsM migration termination | SD 2825503 | DB | Unable to terminate HTsM migration once it has commenced 30-09-09: on going investigation with HDS & CATE 07-10-09: Chris Clayton attempted to recreate issue but was unable to do so. Ongoing 21-10-09: CC has recreated the issue. With HDS support. 11-11-09: Ongoing. CC requested information about cache verification 25-11-09: ongoing investigation between CC and HDS 09-12-09: Reallocated to another support specialist 13-01-10: Case closed |  | Closed |  | 2010-01-13
251 | 2009-11-11 | HiTrack RIO alert | EUC1085751 | DB | Remote I/O path failure HiTrack alert received. Issue was caused by SAN zoning issues. Case closed |  | Closed |  | 2009-11-11
252 | 2009-11-18 | SVP fail-over | EUC1087867 | DB | SVP fail-over |  | Closed |  | 2009-11-18
253 | 2009-11-18 | HRpM and ISR | EUC1087394 | ST | Replication Manager and In-System Replication bundle 25-11-09: ST to raise PER 09-12-09: PER raised |  | Closed |  | 2009-12-09 | 285
254 | 2009-12-02 | HDvM refresh | EUC1095396 | DB | HDvM required restart of HDvM services following ucode upgrade |  | Closed |  | 2009-12-02
255 | 2009-12-02 | SVP on FDCHDS03 | EUC1096926 | DB | Failed SVP on FDCHDS03 09-12-09: SVP replaced |  | Closed |  | 2009-12-09 | 286
256 | 2009-12-16 | HTnM failure | EUC1100618 | DB | HTnM RAID agent intermittent failures 06-01-10: Issue resolved. Case closed |  | Closed |  | 2010-01-06
257 | 2010-01-06 | HDD failure | EUC1111882 | DB | Disk failure on USP-V 78398 13-01-09: Disk replaced |  | Closed |  | 2010-01-13
258 | 2010-01-13 | Performance on MS SQL cluster | EUC1112457 | DB | Cluster performance issue on MS Windows SQL server 27-01-10: Issue identified with specific version of PowerPath. Citi advise they will be testing with VxDMP | Sev 3 | Open | 2010-01-27
259 | 2010-01-13 | HRpM crash | EUC1115120 | DB / ST | Replication Manager crash when creating new pairs 27-01-10: HRpM v6.2 is not affected by this issue. HRpM v6.0 is having a patch created to address issue. ETA TBA. ST to confirm certification with CATE HRpM SME | Sev 2 | Open | 2010-01-27
260 | 2010-01-20 | Standby SVP failure | EUC1118219 | DB | Standby SVP failure in FDC 27-01-10: SVP replaced but replacement was brought down by EPO definitions |  | Open | 2010-01-27
Product Enhancement Requests (PERs)
261 | 2009-09-16 | PER #1 |  | AE | Security implications in using the Physical view setup within HDvM as a provisioning tool - There are currently security implications in Citi in using the Physical view setup within HDvM as a provisioning tool. The limitations are: 1. Post Zoning operation – The ability to scan the storage array to determine if a new WWN is now available an example is IBM in their SVC product perform a ‘svcinfo lshbaportcandidate’ . This lists all available WWNs on said port. 2. WWN Nickname – No option or feature within GUI to add WWN Nickname other than by CLI 3. Modify HSD or WWN - No option or feature within GUI to modify HSD or WWN (Nickname) other than by CLI 09-09-09: PER raised 16-09-09: moved to PER section" 23-09-09: Confirmed this will be addressed in HDvM v7 07-10-09: HDS took away to consider at the meeting on 06-10-09 |  | Open | 2009-10-07
262 | 2009-09-16 | PER #2 |  | AE | HiCommand CLI through HDvM Server - plain text password is stored in the command line. HDS do support a single properties file but not separate properties file for the 12 different Citi people that will be running the scripts. Can Citi have the ability to specify the properties file in the command line so this can scale for more than 1 user? 07-10-09: HDS took away to consider at the meeting on 06-10-09 |  | Open | 2009-10-07
263 | 2009-09-16 | PER #3 |  | AE | The password in the properties file is stored in plain text. Is it possible to encrypt this? It is understood this is coming in the next version of HDvM but will this be back-ported? 07-10-09: HDS took away to consider at the meeting on 06-10-09 |  | Open | 2009-10-07
264 | 2009-09-16 | PER #4 |  | AE | Replication Manager has a separate DB to HDvM. When a host is added to a HDvM instance a refresh of HRpM is required, along with the remote site HDvM and HRpM instances. So, there's 4 refreshes each time a batch of hosts are added. Also, would like to be able to fine tune DB refresh times more than present options. 07-10-09: HDS took away to consider at the meeting on 06-10-09 |  | Open | 2009-10-07
265 | 2009-09-23 | PER Forum |  | JH | TR requested a PER forum with CATE to discuss at a global level PERs with all the appropriate stakeholders and SMEs involved. JH to arrange with CATE 07-10-09: Call occurred on 06-10-09 which TR attended 09-12-09: Further call on 08-12-09 which TR attended |  | Open | 2009-12-09
266 | 2009-11-25 | PER #5 | EUC 1061506 | AE | Java memory issue |  | Open | 2009-11-25 |  | 248
AOB
267 | 2008-05-09 | Empty frame for drive erasure |  | MC / AE | 9/5 Can HDS supply a frame to accommodate faulty drives to be erased? 09 June 2008: HDS does not require faulty drives to be returned by Citi. SA asked HDS to confirm this in writing. 07-July-08 AE provided email copy of the statement to SA |  | Closed |  | 2008-07-14
268 | 2008-08-08 | Capacity on Demand pricing model |  | MC | Citi enquired about a capacity on demand pricing model for HDS storage. MC to investigate 15-09-08: COD pricing model is being incorporated in to proposals for IXE and Array consolidation |  | Closed |  | 2008-09-15
269 | 2008-09-22 | E-Trust |  | FM | Migration of the current E-Trust environment from UAT to Production failed and caused the UAT environment to fail too. FM working to resolve 20-10-08: FM advises ETrust is working albeit slowly. FM advises the issue is not HDS related and to close item |  | Closed |  | 2008-10-20
270 | 2008-11-03 | PCM Review |  | SA | Quarterly review of PCM to ensure details are up to date and correct 10-11-08: RS to add German contact details. 24-11-08: German details obtained. RS to update PCM 01-12-08: RS has made changes. RS will burn to CD and deliver to SA for review 18-12-08: PCM delivered to SA for review 05-01-09: Item closed with agreement from Citi |  | Closed |  | 2009-01-05
271 | 2008-10-17 | Delivery of spare parts |  | Information Only | Delivery of spare parts of RDC proved troublesome recently. SA advises the parts should be addressed to the CE at either their own premises or the CE be onsite at the data centre when delivery of parts is scheduled. |  | Closed |  | 2008-11-24
272 | 2009-01-05 | HiTrack |  | DS | HiTrack in RDC is not able to dial-home to HDS. HDS are remotely access the USP-V in RDC manually to ensure no failed parts. The same issue has occurred on the FDC USP-V HiTrack instance. HDS are working with Citi to resolve the issue. 19-01-09: Pending firewall change scheduled for 19-01-09 26-01-09: Firewall changed applied. RDC completed, FDC pending further firewall change. FDC item transferred to Egg action items |  | Closed |  | 2009-01-26
273 | 2009-01-12 | Power Connectivity |  | DS | Citi have requested inspection of power connectivity of the USP-Vs in FDC & RDC 19-01-09: Issue has been raised with Corporate & RSD 26-01-09: RDC site manager is satisfied with power connectivity. Awaiting confirmation FDC site manager is too. 02-02-09: Citi UK are happy with connectivity. Awaiting confirmation from Citi DE 16-02-09: Meeting in German between HDS & Citi scheduled for 19-02-09 26-03-09: Pending feedback from Citi Germany. 03-04-09: Pending inspection by Citi DE data centre team 26-04-09: FDC cover installed and inspected by Citi. FDC complete. Inspection of RDC to be undertaken by Citi 21-05-09: JD advised issue is closed |  | Closed |  | 2009-05-21
274 | 2009-03-26 | RAID 6 certification |  | AE | Citi have requested whether RAID 6 is CATE certified on USP-V platform 03-04-09: RAID 6 is under consideration by CATE for certification. 21-05-09: RAID 6 6+2 is certified. RAID 6 14+2 is not certified |  | Closed |  | 2009-05-21
275 | 2009-03-26 | Software included within VPA agreement |  | MC / AE | Citi have requested confirmation of what software components are included with VPA priced configurations 03-04-09: HDS have advised JD of what is included with VPA agreement. HDP & HTSM are not included. |  | Closed |  | 2009-04-26
276 | 2009-03-26 | Certified disks |  | AE | Citi have requested confirmation of which disks are CATE certified within the USP-V 03-04-09: 1TB SATA disks are certified, 450GB FC disks are pending certification. JD asked for confirmation whether 1TB SATAs are in use elsewhere within Citi 26-04-09: 1TB SATA disks have not been deployed in Citi |  | Closed |  | 2009-04-26
277 | 2009-03-26 | List of top 10 components replaced |  | DB | Citi have requested a list of the top 10 items replaced and the case severity these are given. Additionally can case severity be changed automatically 26-04-09: List supplied to JD 26-08-09: I will integrate this into the agreed monthly reporting format. 09-09-09: DB advises first report due week commencing 14-09-09 23-09-09: Monthly report issued 30-09-09: TR feedback was positive to the report. AE advised format my slightly change due to it being rolled up in to a global report for Citi senior management 07-10-09: September report due next week 14-10-09: September report issued 04-11-09: DB advises October report due w/c 09-11-09 18-11-09; DB awaiting APC data. Report will be issued without APAC data this week 25-11-09: November report issued by DB. Close item and create new monthly report item |  | Closed |  | 2009-11-25
278 | 2009-02-02 | HDvM upgrade |  | RS | RS & Time Robinson upgraded HDvM from v5.7 to v6 in RDC. HTsM was also deployed. Host DRSA10 |  | Closed |  | 2009-02-02
279 | 2009-07-15 | SATA loan |  | MC / TR | JA & MC agreed to explore the possibility of loaning Citi a 6+2 Raid group of 1TB SATA disks 16-09-09: MC to follow-up with pricing. Citi advise this is likely to be installed in to net-new USP-V in RDC (serial # 78378) 23-09-09: TR to investigate possible customers for this disk 30-09-09: Pricing will be provided to TR this week - confirmed by AE 07-10-09: TR has passed on pricing to GB. TR advised to close item |  | Closed |  | 2009-10-07
280 | 2009-07-15 | Value Add |  | DB | JD raised the item of Value Add from the Citi Account Team. Details to follow 29-07-09: JD supplied examples of value add activities he would like HDS to offer. These include reports and bi- weekly brain-storming meetings. DB to follow up with JD upon return from vacation 26-08-09: discussed how I will demonstrate reporting examples and start sending these out on a monthly basis. This will include the hardware replacement summary. 09-09-09: DB advises first report due week commencing 14-09-09 23-09-09: Monthly report issued 07-10-09: September report due next week. Close item as is duplicate of item 210 |  | Closed |  | 2009-10-07
281 | 2009-08-26 | FTP |  | DB | An FTP site needs to be available to upload / download data. 09-09-09: FTP site has been provided. Item complete |  | Closed |  | 2009-09-09
282 | 2009-09-02 | Clarify alerts |  | AE | Add emea.spit@citi.com to HDS Clarify alerts 09-09-09: emea.spit@citi.com added to Clarify alerts dlist. Item complete |  | Closed |  | 2009-09-09
283 | 2009-09-02 | Issue 004 - Security implications in using the Physical view setup within HDvM as a provisioning tool |  | AE | AE to raise PER with respect to:- There are currently security implications in Citi in using the Physical view setup within HDvM as a provisioning tool. The limitations are: 1. Post Zoning operation – The ability to scan the storage array to determine if a new WWN is now available an example is IBM in their SVC product perform a ‘svcinfo lshbaportcandidate’ . This lists all available WWNs on said port. 2. WWN Nickname – No option or feature within GUI to add WWN Nickname other than by CLI 3. Modify HSD or WWN - No option or feature within GUI to modify HSD or WWN (Nickname) other than by CLI 09-09-09: PER raised 16-09-09: moved to PER section |  | Closed |  | 2009-09-16
284 | 2009-09-09 | Security Pass |  | TR | DB & MC have requested security passes for Riverdale House 30-09-09: DPC hopes to have approval of the passes by end of the week 07-10-09: DPC has advised MC is not permitted a pass. DB's pass is in progress 21-10-09: DB's pass has progressed. DPC following up 18-11-09: DB's pass is ready for collection 13-01-09: TR will arrange for collection of security pass. |  | Open | 2010-01-13
285 | 2009-11-11 | Replication issue |  | ST | ST raised a potential PER or case with regard to HRpM and In-System Replication. ST to document issue. 18-11-09: Close item as case EUC1087394 opened |  | Closed |  | 2009-11-11
286 | 2009-03-26 | Quarterly replacement summary in comparison to other Citi regions |  | DB | Citi have requested replacement summary for EMEA in comparison to APAC & Americas. Included in monthly report. Citi agreed to close item |  | Closed |  | 2009-10-21
287 | 2009-12-09 | New Starter training for DB |  | DB | DB to complete new starter training 06-01-10: Training completed |  | Closed |  | 2010-01-06
288 | 2010-01-06 | Initial training for Nigel Chilcott |  | AE | NC has requested a meeting with ST & AE for some initial training on the HDS environment at Citi 13-01-09: Meeting completed |  | Closed |  | 2010-01-13
289 | 2010-01-27 | Planning information |  | AE / DB | NC has requested data around planned microcode releases etc. AE & DB to provide provisional dates for these. |  | Open | 2010-01-27
290 | 2010-01-27 | Buffer capacity |  | MC | NC requested information on how buffer capacity will be charged for. MC to provide details. TR enquired whether it would be possible to ship empty DKU cabinets for future disk expansion. MC to investigate. |  | Open | 2010-01-27
291 | 2009-11-25 | Monthly report |  | DB | Monthly report on hardware and software cases to be issued by DB |  | Recurring | 2009-11-25
292 | 2010-01-27 | Next meeting |  | All | Scheduled for 12:00 03-02-10 @ Riverdale House. |  | Recurring | 2010-01-27
Formulas:
Last Updated = [Date Identified]

## Closed sections
File Notes |  |  | Open | 0 |  | Title | Citi / HDS Operations Review Meeting Notes
|  |  | Closed | 24 |  | Date | 2010-01-20
|  | Attendee list - see cover sheet | Pending | 0 |  | Number | 83
Ref No | Date Identified | Item Description | Case Number | Owner | Action Taken | Impact | Current Status | Last Updated | Date Closed | Cross ref to | Test | Open | Closed | Pending Closed
Replication Certification
1 | 2008-06-09 | No open items for replication certification. HUR is certified with Citi |  |  |  |  | Closed |  | 2008-06-16
Loan Replication USP-Vs
2 | 2008-06-16 | Loan replication USP-V installation date |  | SM / RS | 20-10-08: Citi have advised delivery is likely to be during week commencing 10-11-08 29-10-08: Delivery date has been changed to week commencing 17-11-08 03-11-08: HDS to confirm exact delivery day in week of 17-11-08 delivery will be 10-11-08: FDC 19-11 and RDC 18-11 confirmed. HDS to provided exact delivery details to Citi. SM to attend RDC site on delivery date and power up. 17-11-08: FDC power-up will be 23-11-08, RDC power-up will be 23-11-08 or 30-11-08 24-11-08: Delivery of loan equipment to RDC & FDC was made last week. Both frames were powered up on 22/23-11-08. No SAN or LAN connectivity at present 01-12-08: Awaiting RDC microcode downgrade to 60-03-06 by SM 09-12-08: SM has scheduled to undertake this on 13-12-08 18-12-08: Microcode on RDC USP-V downgraded successfully. Secondary SVP will be deployed 20/21-12-08 23-12-08: Secondary SVP installed at RDC on 20-12-08. RDC USP-V SAN ports are connected but are not logging in to fabric. SM / DS to confirm BCD has been applied to USP-V 05-01-09: RDC USP-V can be seen on fabric and BCD applied |  | Closed |  | 2009-01-05 | 8
3 | 2008-09-15 | Management Servers - SOE access |  | JB | RS and JB require Citi network access for management server build / config - Access is required to progress the project post installation and power on of USPVs - CPW has submitted the requests and a response is pending Citi security / networking 22-09-08: RS has received his login. RS will test this week 29-09-08: RS has successfully tested his login. JB has received his login but not tested it yet 09-10-08: JB to liaise with Paul Haynes to arrange a time to obtain login details. 13-10-08: JB has received and tested his login |  | Closed |  | 2008-10-13
4 | 2008-09-15 | Management Servers - SAN connectivity |  | RS/AO | 09-12-08: RDC; awaiting confirmation from Citi fibre patching has been completed. FDC; awaiting Citi resource. CPW has escalated 09-12-08: IP connectivity broken out to new item 05-01-09: RDC awaiting testing by CPW or AO. FDC awaiting fabric being made ready. 12-01-09: RDC firewall issues are preventing testing of testing by CPW/AO 19-01-09: Firewall changes due on 21-01-09 26-01-09: FDC array not physically cabled to fabric. Firewall changes due 21-01-09 were applied and successful 02-02-09: FDC fabric connected. Pending AO to test 09-02-09: FDC fabric test completed |  | Closed |  | 2009-02-09 | 5
5 | 2008-09-15 | Management Servers - IP connectivity |  | RS/SM | 09-12-08: RDC; SM to connect on 13/14-12-08. FDC; physically connected. CPW to confirm connectivity test completed 18-12-08: FDC; USP-V visible in HDvM. RDC; awaiting network configuration on 20/21-12-08 05-01-09: RDC configured but awaiting testing. 12-01-09: RDC firewall issues are preventing testing 19-01-09: Pending firewall changes due on 21-01-09 26-01-09: Firewall changes applied and were successful. |  | Closed |  | 2009-01-26 | 4
6 | 2008-09-15 | Management servers (Windows and Solaris required in FDC |  | RS / TR | 20-10-08: FM chasing JD daily for Solaris servers. FM to liaise with SA regarding using COB host for familiarisation phase 29-10-08: Citi advise there will be no management servers at FDC until go-live 17-11-08: JD received push-back on these servers. MC to raise with GB. 24-11-08: RS to liaise with JD on behalf of MC 01-12-08: RS is liaising with CPW to use EMC Solaris Management server 09-12-08: Windows; VMware VM scheduled for Jan/Feb 09. Solaris; Ready 16-02-09: Scheduled for end of March 25-03-09: VMware date - end of March 03-04-09: System being built 04-04-09. Should be available 2 weeks after this. 26-04-09: Systems built. Pending HDS toolset being installed. 21-05-09: Potential deployment of Production data in FDC on HDS storage. Management servers will need to be ready prior to going in to Production 04-06-09: HDvM installation complete |  | Closed |  | 2009-06-04 | 3
7 | 2008-09-15 | Management servers (Windows & Solaris) required in RDC |  | RS/CPW | 29-09-08: Solaris resource is now unavailable due to paternity leave. FM is working with David Westcott to secure another resource. 20-10-08: RS has escalated to JD 29-10-08: Existing Windows COB management server will be used for Windows. Solaris server is pending update from Citi Solaris team 03-11-08: Solaris system has been allocated. Windows system; SA has approved change of role of existing Windows mgmt COB server 10-11-08: Pending build date from Solaris team 17-11-08: RS chased FM, no status update 24-11-08: FM will advise RS on status on 25-11-08 01-12-08: Awaiting confirmation from CPW on go live date for Windows and Solaris familiarisation servers. At least 1 week delay, which will delay BAU familiarisation to week commencing 22-12-08 09-12-08: Windows; SA resource is required to migrate production to UAT. CPW has escalated. Solaris; Ready 02-02-09: Windows server is now ready |  | Closed |  | 2009-02-02 | 2
8 | 2008-09-15 | Microcode level on replicated USP-Vs |  | RS/JH | Microcode 60-30-06 has been proposed for the loan USP-V frames. Confirmation has been given by CPW that this is acceptable. RS to confirm with JH that CATE have certified this level. 29-09-08: JH has confirmed Gary Johnson has given go ahead to deploy 60-03-06 on the HUR loaner frames. |  | Closed |  | 2008-10-29
9 | 2008-04-04 | Global loan agreement |  | MC | Global loan agreement supplied to Citi with UK Law amendment. JD to confirm progress with Erica Jeffers. Amendments to agreement requested by Sascha Bender on 14/05 Updates supplied to Erica Jeffers and Sascha Bender. Citi will not be in a position to accept the HUR loan equipment until mid-July at the earliest. 16-June-08 MC to email details to SA to allow SA to follow this up. 30/06/08 Germany agreement completed. UK agreement has been reviewed & amended by Citi legal team and returned to HDS legal team for review. 07-July-2008:Amendments agreed to by HDS legal. MC to supply signed copies to Citi Procurement. 28-07-2008: AE has provided additional information requested by Citi Procurement. Pending signature by Citi now. 08-08-08: Citi requested modifications to the loan agreement which are with HDS legal. It is hoped this will be completed by COB 08-08 29-08-2008: Loan agreement was completed 18-08-2008. |  | Closed |  | 2008-09-08
10 | 2008-10-09 | Access to Aperture and Virtual Change |  | RS / JD | RS to ask for permission to access Aperture and Virtual Change systems 13-10-08: RS awaiting on JD 10-11-08: SA provided details of Mystic system to RS 17-11-08: RS to work with SA on access to Mystic 24-11-08: Infoman system is the system required. RS to liaise with JD to gain access. 01-12-08: HDS personnel unable to be added to groups for change / VT viewing since non-HDS information would be visible. Alternate solution is that HDS can request updates from Citi on status of changes / VT's. |  | Closed |  | 2008-12-01
11 | 2008-12-18 | Replication Familiarisation Commencement Critical Path Items |  | All | Critical Path Items preventing commencement of Replication Familiarisation: None |  | Closed |  | 2009-03-26
12 | 2009-05-21 | HiTrack USP-V (FDC) |  | CPW / RS | Firewall changes required to permit dial-home of FDC USP-V serial 18779 11-06-09: German CE dialled in on 09-06-09 and verified configuration to be correct. Configuration retest scheduled for w/c15-06-09 with Citi networks team 08-07-09: 2nd dial-in test with CPW & RS to be scheduled 15-07-09: Issue is identified as routing. CPW advised the issue is with Network Infrastructure team 26-08-09: Routing issue identified. Fixed, item can be closed off |  | Closed |  | 2009-08-26 | 18
Egg Deployment
13 | 2009-01-05 | Egg capacity |  | Information Only | Citi have purchased 100TB of capacity for USP-V serial 18850 (RDC HUR loaner) for Egg. |  | Closed |  | 2009-03-26
14 | 2009-01-12 | Installation Planning Meeting |  | AE | SA has asked to attend the IP meeting for the Egg upgrade 19-01-09: IP meeting took place 16-01-09 |  | Closed |  | 2009-01-26
15 | 2009-01-19 | Egg installation phase 1 |  | DS | Rotation of USP-V #18850 through 180 degrees, installation of R1 DKU & additional DKAs due on 24/25-01-09 26-01-09: Phase 1 work completed |  | Closed |  | 2009-01-26
16 | 2009-01-26 | Egg installation phase 2 |  | MT | Installation of DKU L1 and remaining disks pending removal of Symmetrix 11R by Citi 16-02-09: All hosts are now removed from Sym 11R. Decommissioning scheduled for end of March 25-03-09: Symm 11R in the process of being erased prior to de-installation 03-04-09: Symm 11R now powered down. RS to liaise with Simon Gibbs on progress of removal 26-04-09: Installation of L1 DKU scheduled for 02-05-09 21-05-09: Installation completed. 2 parity groups require formatting to complete installation 04-06-09: Parity group format complete |  | Closed |  | 2009-06-04
17 | 2009-01-26 | Egg installation - Cisco |  | CPW | Installation of 2 x Cisco MDS9513 in to Citi racking scheduled for 28-01-09 09-02-09: Installation completed |  | Closed |  | 2009-02-09
18 | 2009-01-26 | Egg installation - HiTrack USP-V (FDC) |  | RS / CPW | Configuration HiTrack for RDC USP-V (18850) is complete. Configuration of FDC USP-V (18779) is pending firewall change 02-0209: Pending firewall change. ETA 4 weeks 26-02-09: Firewall change scheduled for end of March 25-03-09: Firewall changes still pending 03-04-09: Firewall changes scheduled for 04-04-09 26-04-09: Firewall change made but dial-home access still not working 21-05-09: Moved to Production USP-V notes section |  | Closed |  | 2009-05-21
19 | 2009-01-26 | Egg installation - HiTrack Cisco |  | AO | Deployment & configuration of HiTrack Monitor server for Cisco HiTrack fault reporting 24-02-09: AO to install HiTrack Monitor 3.9 to monitor Cisco directors 25-03-09: HiTrack has been installed and configured. Confirm next meeting Cisco's are dialling home consistently 03-04-09: Cisco units are successfully dialling home daily. |  | Closed |  | 2009-04-03
20 | 2009-02-09 | Egg go live |  | AE / JD | Citi have advised go-live for Egg is 23-02-09 25-03-09: JD to advise of new go-live date 03-04-09: Still to be confirmed 21-05-09: 25-05-09 current go-live date but is unlikely to be achieved 11-06-09: Potential go-live already occurred. To follow-up with JD 08-07-09: Egg is now live |  | Closed |  | 2009-07-08
21 | 2009-02-09 | Egg Critical Path items |  | All | Critical Path Items preventing Egg deployment going in to Production: 1) None - system is Production ready |  | Closed |  | 2009-04-03
London Phase 2 / Poland Migrations Project
22 | 2009-07-08 | Critical path items for London Phase 2 / Poland migrations project |  | All | 1) Process control manual |  | Closed |  | 2009-09-16 | 1
23 | 2009-07-08 | Critical path items for London Phase 2 / Poland migrations project |  | All | 2) HiTrack in Frankfurt |  | Closed |  | 2009-08-26 | #REF!
24 | 2009-07-08 | v05 microcode certification |  | AE | v05 Microcode due to be GA'ed in June. Offers some HDP enhancements. AE to provide details of enhancements to JD 15-07-09: AE provided information to JD |  | Closed |  | 2009-07-15 | 0
25 | 2009-07-08 | Dependency of HiCommand v6.2 products |  | AE | AE to confirm the inter-dependency of HDvM, HTsM and HRpM versions 6.0 and 6.2 15-07-09: AE confirmed inter-dependency rules |  | Closed |  | 2009-07-15