SAN-BAU Weekend Work plan – 14th February 2009


SAN Weekend work plan:  14th February 2009

SAN Work Co-ordinator: Andy Johnstone 

PIT Work Co-ordinator: Ade Okusanya and Carl Williams

Consisting of: 

· ZONING AND LUN MASKING WORK FOR UK/DE
· UNASSIGN STORAGE - FDCM EBA STEP2
· ISSAC CONTINUITY OF BUSINESS (COB) TEST
· GCOT - SAN RETIREMENT/DECOMMISSION
· ESTABLISH FLEXLNA BCVS IN FDC - flexlna_3452_3544_A
· CONVERT T4 OPEN STORAGE TO T4 CLOSED STORAGE
· MICROCODE UPGRADE ON STORAGE FRAMES
· SAN RECLAIM - EQSMART5,6,7,8,9,10P

· SAN RECLAIM - EQKDB1,2P EQKDBAP1,2P
· NON-270GB DISKS TO BE REMOVED FROM ESX SVRS
Locations:
EDC/IXE/CGC/RDC/FDC

SAN Team members on site:

· Andy Johnstone (D) +442075007242

· Group Line: +44 (20) 7500 9686 or xt. 5-9686

PIT Team Members on Site

· Ade Okusanya +44 2075005552

· Carl Williams +44 2079865693
Conference Call Number: Freephone UK 0800 096 6674 DE 0800 096 6674 Pl 008001112878
Conference Code: 
0207 477 2477 (participant #  786012, Leader Pin # 4106)
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Version Control

	Date
	Version
	Reason for Change

	02/06/09


	020609_v1.0
	1st Draft

	
	
	

	
	
	

	
	
	

	
	
	

	
	
	


1.0 Work Overview/Control Log

	Item Number – Description
	Reference: RFC/VT/AP
	Date of Scheduled work
	Status
	Signed Off as complete

	ZONING AND LUN MASKING WORK FOR UK/DE
	Various Aperture Tickets
	14/02/09
	
	

	UNASSIGN STORAGE - FDCM EBA STEP2

For aperture 90205072242, 90205065725, 90205072856
	RFC 10807603
	14/02/09
	
	

	ISSAC CONTINUITY OF BUSINESS (COB) TEST

Cob test on group issac_3452_3544_A
	RFC 10768832
	14/02/09
	
	

	GCOT - SAN RETIREMENT /DECOMMISSION

For Aperture 81212085618
	RFC 10774269
	14/02/09
	
	

	ESTABLISH FLEXLNA BCVS IN FDC

Establish Group  flexlna_3452_3544_A
	RFC 10793826
	14/02/09
	
	

	CONVERT T4 OPEN STORAGE TO T4 CLOSED STORAGE

Run script prepared by Paul Haynes.
	RFC 10803713
	14/02/09
	
	

	MICROCODE UPGRADE ON STORAGE FRAMES

Microcode upgrade on Storage frames DMX1/2/4E and DMX1/2/4X
	RFC 10808819
	14/02/09
	
	

	SAN RECLAIM - EQSMART5,6,7,8,9,10P

See Forsythe reclaim in Appendix Matrix
	RFC 10811347
	14/02/09
	
	

	SAN RECLAIM - EQKDB1,2P EQKDBAP1,2P

See Forsythe reclaim in Appendix Matrix
	RFC 10811327
	14/02/09
	
	

	NON-270GB DISKS TO BE REMOVED FROM ESX SVRS

Incorrect sized luns supplied last year to be removed 
	RFC 10820966
	14/02/09
	
	

	
	
	
	
	

	Overall Sign Off: 1 Page – To be returned to BAU on completion

Member of: SAN-BAU 

NAME: 

Date: 


Issues Found

Log of all issues found during weekend activities

	ITEM NUMBER
	ISSUE
	FOLLOW UP ACTION
	OWNER
	STATUS

	
	
	
	
	

	
	
	
	
	

	
	
	
	
	


Section 1.1  : Pre-requisites checks

	SPECIFIC PRE-REQUISITES

	Step
	Owner
	Details
	Comment
	Date Due
	Complete

	1. 5
	Business As usual
	DE Zone sets prepared
	See Weekend Schedule
	
	

	2. 6
	Business As usual
	UK Zone sets prepared
	See Weekend Schedule
	
	

	3. 7
	Business As Usual
	BAU COB TESTS Agreed
	See Weekend Schedule
	
	

	PRE-REQUISITE STATUS
	SELECTION

	Pre-Requisites complete – Proceed with work
	

	Pre-Requisites not complete – Postpone work
	

	EMEA SAN BAU Manager
Salauddin Ahmed

Date: 


Section 2.0: 
SAN BAU and PIT Weekend Work

	Step
	Time
	Owner
	Details
	Comment
	Applicable Appendix

	1. 
	14:00 
	BAU
	BAU Weekend Work – UK and DE Zoning
	 
	

	2. 
	14:00
	BAU
	Other work (See weekend Schedule for details)
	
	

	EMEA SAN BAU Manager - Sign off: 

Salauddin Ahmed

Date: 


Section 2-1: Post Implementation Review
	

	Step
	Owner
	Details
	Comment
	Date Due
	Complete

	1. 
	BAU


	BAU Weekend Work – UK and DE Zoning
	
	
	

	2. 
	BAU
	Other work (See weekend Schedule for details)
	
	
	

	
	

	EMEA Regional Storage and Backup Manager – Sign off.

Gary Battersby

Date: 


Contact List  

And escalation points with grey background, Gary Battersby details included if Salauddin and Javed, are unavailable 

	Company/Department
	Title
	Name
	Contact Number 1
	Contact Number 2
	Contact Email

	Citigroup – SAN
	Head of EMEA Open Storage
	Garry Battersby
	07724 333 312
	020 7500 3838
	Gary.battersby@citi.com

	Citigroup – BAU
	Team Leader SAN BAU
	Salauddin Ahmed
	07764 823 914
	020 7500 6566
	Salauddin.Ahmed@citi.com

	Citigroup – PIT
	Team Leader PIT
	Javed Dad
	07841 429 769
	020 7500 9757
	Javed.Dad@citi.com

	Citigroup – Command centre
	Command Centre
	Command Centre
	Xt 62020
	020 7986 2020
	 Operations, London

	Citigroup – BAU
	BAU – On Call Representative
	Paul Haynes
	07796 307 355
	020 7500 9686
	paul.haynes@citigroup.com 

	Citigroup – BAU
	BAU – On Call Representative
	David Coles
	07834 807 687
	020 7500 9686
	david.peter.coles@citigroup.com 

	Citigroup – BAU
	BAU – On Call Representative
	Tim Robinson
	07920 447 481
	020 7500 9686
	tim1.robsinson@citigroup.com 

	Citigroup – BAU/PIT
	BAU
	Thomas Weise
	00491723092778
	0049 213274523
	Thomas.weise@citigroup.com

	Citigroup – BAU
	BAU
	Krishnam Raju
	+65 64262830
	+65 93377459
	krishnam.raju.vathsavai@citi.com

	Citigroup – PIT
	PIT
	Carl Williams
	07966 466 956
	020 7986 5693
	carl.patrick.williams@citigroup.com

	Citigroup – NTSATS Projects
	EMEA Engineer
	Tom Hollinghurst
	02075006326
	
	Tom.hollinghurst@citigroup.com

	Citigroup –Oliver Cabling
	Team Leader
	Trevor Whelan
	07835 186 452
	020 7986 2596
	trevor.whelan@citigreoup.com

	Citigroup –Oliver Cabling
	Site Engineer
	Paolo Sidoli
	N/A
	020 7986 9962
	paolo.sidoli@citigroup.com

	Citigroup –Oliver Cabling
	Site Engineer
	Carl Elrick
	N/A
	020 7986 9962
	carl.elrick@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Mark Matthews
	 07979 607 118
	020 7500 8025
	mark.a.matthews@citigroup.com

	Citigroup – DCSM – UK
	DCSM Manager
	Kevin Last
	 07778 814 088
	020 7986 2648
	kevin.last@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Matt Neill
	07971 008 665
	020 7500 8025 
	matthew.neill@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	Bob Coe
	N/A
	020 7986 2651
	bob.coe@citigroup.com

	Citigroup – DCSM – UK
	DCSM Representative
	John Mc Bride
	07710 419 677
	776754073 – Mobex
	john.mcbride@citigroup.com

	Citigroup – CRS – UK
	CRS
	CRS
	67788
	N/A
	 EMC CSA

	Citigroup – Security – CGC
	Security – CGC
	Security – CGC
	62400
	020 7986 2400
	 EMC CSA

	Citigroup – Security – RDC
	Security – RDC
	Security – RDC
	54393
	020 7500 4393
	 EMC CSA

	EMC
	SAM
	Graham Rodell
	07920 594 708
	N/A
	Rodell_Graham@emc.com

	EMC
	CE
	Terry Brister
	07713 505 896
	N/A
	brister_terry@emc.com

	EMC
	CE
	Patrick Caborn
	07801 214 303
	N/A
	caborn_patrick@emc.com

	EMC
	CE
	Jochen Terhaag
	00491774252592
	0049 213274522
	Terhaag_jochen@emc.com

	Faktor2
	Lead Engineer
	Stephan Klesel
	00491732935707
	
	

	Citigroup – DCSI – UK
	DCSI Representative
	Ghazanfur Ali
	86864
	07951 488 935
	

	Citigroup – DCSI – UK
	DCSI Representative
	Anthony Carrelo
	62568
	07985 198 797
	

	Citigroup – DCSI – UK
	DCSI Representative
	Michael Curtis
	62568
	07795 053 926
	

	Citigroup – DCSI – UK
	DCSI Representative
	Aaron Fitt-Boyland
	54073
	07921 875 818
	

	Citigroup – DCSI – UK
	DCSI Representative
	Ray Gray
	87269
	07811 714 662
	

	Citigroup – DCSI – UK
	DCSI Representative
	Trevor Hawkins
	58179
	07976 854 113
	

	Citigroup – DCSI – UK
	DCSI Representative
	Linton Nelson
	50246
	07739 785 239
	

	Citigroup – DCSI – UK
	DCSI Representative
	Chris Quinn
	62568
	07957 575 077
	

	Citigroup – DCSI – UK
	DCSI Representative
	Jason Walsh
	50911
	07713 166 270
	


Appendix Matrix

	APPENDIX
	Comment
	Attachment

	A


	PIT Weekend Work plan Over View 
	
[image: image1.wmf]"Weekend Change 

Summary140209_0.2.doc"




	B
	SAN Weekend work sheet – UK/DE 
	
[image: image2.wmf]"Host Workplan 

14-02-09.xls"




	C
	SAN Weekend Zone Cleanup (BAU activity) 
	NA

	D
	Forsythe reclaim
	
[image: image3.wmf]"Forsythe Reclaims 

14-02-09.xls"





1/10

_1296040833.xls
Sheet1

				CR: 10803713										Reclaims for Saturday 14th Feb 2009

				SYMMETRIX

				Hostname / Zone Alias		Site		Red				Blue				Storage		Symm #		Red				Blue				Device #s		Total		Request		NOTES		QA by

								Sw/Prt		HBA WWN		Sw/Prt		HBA WWN		required		required		FA		sw/pt		FA		sw/pt		required		Space		Number

				DISK REMOVES

				emcbrap1						50060b0000389822  
 50060b00003897cc				50060b0000389820 
  50060b00003897ce				1808										01A7,01AB				VR3887293		Tier-1 to Tier-3		PH

				emcbrac1						50060b0000389506   
50060b00003894e6				50060b0000389504   
50060b00003894e4				1820										01A7,01AB				VR3887293		Tier-1 to Tier-3		PH

				emcbrdp1						50060b00003896be
50060b00003896bc				50060b000038960c   
50060b000038960e				1136										0040,0041,0042,0043,0044,0045,0046,0047,0048,0049,004A,004B,004C,004D,004E,004F,0050,0051,0052,0053
0054,0055,0056,0057,0058,0059,005A,005B,005C,005D,005E,005F,0060,0061,0062,0063,0064,0065,0066,0067
0068,0069,006A,006B,006C,006D,006E,006F,0070,0071,0072,0073,0074,0075,0076,0077,0078,0079,007A,007B
007C,007D,007E,007F,0080,0081,0082,0083				VR3881362		Tier-1 to Tier-3		PH

				emcbrdc1						50060b00003897c4
50060b00003895a0				50060b00003895a2
50060b00003897c6				1081										0040,0041,0042,0043,0044,0045,0046,0047,0048,0049,004A,004B,004C,004D,004E,004F,0050,0051,0052,0053
0054,0055,0056,0057,0058,0059,005A,005B,005C,005D,005E,005F,0060,0061,0062,0063,0064,0065,0066,0067
0068,0069,006A,006B,006C,006D,006E,006F,0070,0071,0072,0073,0074,0075,0076,0077,0078,0079,007A,007B
007C,007D,007E,007F,0080,0081,0082,0083				VR3881362		Tier-1 to Tier-3		PH

				emibbsp1						50060b000024fbea				50060b00003053be				1136										06E7,06E8,06E9,06EA,06EB,06EC,06ED,06EE,06EF,06F0,06F1,06F2,06F3,06F4,06F5,06F6,06F7,06F8
06F9,06FA,06FB,06FC,06FD,06FE,06FF,0700,0701				VR3880559		Remove server		PH

				emibbsc1						50060b0000251836				50060b000024fbf0				1081										06E7,06E8,06E9,06EA,06EB,06EC,06ED,06EE,06EF,06F0,06F1,06F2,06F3,06F4,06F5,06F6,06F7,06F8
06F9,06FA,06FB,06FC,06FD,06FE,06FF,0700,0701				VR3880559		Remove server		PH

				emibbsp2						50060b000024fbfc				50060b0000305d52				581										04E5,04E9,04ED,04F1,04F5,04F9,04FD,0501,0505,0509,050D,0511,0515,0519,051D,0521,0525,0529
052D,0531,0535,0539,053D,0541,0545,0549				VR3880559		Remove server		PH

				emibbsc2						50060b0000305d62				50060b0000305d64				587										04E5,04E9,04ED,04F1,04F5,04F9,04FD,0501,0505,0509,050D,0511,0515,0519,051D,0521,0525,0529
052D,0531,0535,0539,053D,0541,0545,0549				VR3880559		Remove server		PH

				eqkdb1p						10000000c9756a76				10000000c9756c23				603										0BF1,0BF5,0BF9,0BFD,0C01,0C05,0C09,0C0D,0C11,0C15,0C19,0C1D,0C21,0C25,0C29,0C2D,0C31,0C35,0C39,0C3D,0C41,0C45
0C49,0C4D,0C51,0C55,0C59,0C5D,0C61,0C65,0C69,0C6D,0C71,0C75,0C79,0C7D,0C81,0C85,0C89,0C8D,0C91,0C95,0C99,0C9D
0CA1,0CA5,0CA9,0CAD,0CB1,0CB5,0CB9,0CBD,0CC1,0CC5,0CC9,0CCD,0CD1,0CD3,0CD5,0CD7,0CD9,0CDB,0CDD,0CDF				VR3872048		Tier-2 to Tier-4		PH

				eqkdb2p						10000000c97565ed				10000000c97569a8				603										0BF1,0BF5,0BF9,0BFD,0C01,0C05,0C09,0C0D,0C11,0C15,0C19,0C1D,0C21,0C25,0C29,0C2D,0C31,0C35,0C39,0C3D,0C41,0C45
0C49,0C4D,0C51,0C55,0C59,0C5D,0C61,0C65,0C69,0C6D,0C71,0C75,0C79,0C7D,0C81,0C85,0C89,0C8D,0C91,0C95,0C99,0C9D
0CA1,0CA5,0CA9,0CAD,0CB1,0CB5,0CB9,0CBD,0CC1,0CC5,0CC9,0CCD,0CD1,0CD3,0CD5,0CD7,0CD9,0CDB,0CDD,0CDF				VR3872048		Tier-2 to Tier-4		PH

				eqkdbap1p						10000000c952fb20				10000000c952fbb4				603										0BF1,0BF5,0BF9,0BFD,0C01,0C05,0C09,0C0D,0C11,0C15,0C19,0C1D,0C21,0C25,0C29,0C2D,0C31,0C35,0C39,0C3D,0C41,0C45
0C49,0C4D,0C51,0C55,0C59,0C5D,0C61,0C65,0C69,0C6D,0C71,0C75,0C79,0C7D,0C81,0C85,0C89,0C8D,0C91,0C95,0C99,0C9D
0CA1,0CA5,0CA9,0CAD,0CB1,0CB5,0CB9,0CBD,0CC1,0CC5,0CC9,0CCD,0CD1,0CD3,0CD5,0CD7,0CD9,0CDB,0CDD,0CDF				VR3872048		Tier-2 to Tier-4		PH

				eqkdbap2p						10000000c952fca2				10000000c952fd7f				603										0BF1,0BF5,0BF9,0BFD,0C01,0C05,0C09,0C0D,0C11,0C15,0C19,0C1D,0C21,0C25,0C29,0C2D,0C31,0C35,0C39,0C3D,0C41,0C45
0C49,0C4D,0C51,0C55,0C59,0C5D,0C61,0C65,0C69,0C6D,0C71,0C75,0C79,0C7D,0C81,0C85,0C89,0C8D,0C91,0C95,0C99,0C9D
0CA1,0CA5,0CA9,0CAD,0CB1,0CB5,0CB9,0CBD,0CC1,0CC5,0CC9,0CCD,0CD1,0CD3,0CD5,0CD7,0CD9,0CDB,0CDD,0CDF				VR3872048		Tier-2 to Tier-4		PH

				eqsmart5p						10000000c97428e9				10000000c9754299				2839										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				eqsmart6p						10000000c9743c8c				10000000c97460cb				2839										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				eqsmart7p						10000000c9742cf5				10000000c97540c0				2839										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				eqsmart8p						10000000c9743cc2				10000000c9743d82				2838										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				eqsmart9p						10000000c9743d7d				10000000c9742915				2838										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				eqsmart10p						10000000c9743d66				10000000c9743d6c				2838										0058,005C,0060,0064,0068,00D8,00DC,00E0,00E4,00E8				VR3872026		Tier-1 to Tier-3		PH

				lonmsmth						50060b00000b585c				50060b00000b5790				293										0265,0269,026D,0271,0275,0279,027D,0281				VR3886368		Tier-2 to Tier-4		PH

				tcgppdb2u						10000000c969b296				10000000c9653d40				602										0CA7,0CA9,0CAB,0CB3,0CB5,0CB7,0CCF,0EF5				VR3882206		Tier-2 to Tier-4		PH

				tcgppdb2u						10000000c969b296				10000000c9653d40				300										0C5D,0C61				VR3882206		Tier-2 to Tier-4		PH

				tcgppdb2u						10000000c969b296				10000000c9653d40				2819										02DE,02DF,02E0,02E1,02E2,02E3				VR3882206		Tier-2 to Tier-4		PH

				tcgppdb3u						10000000c9699fd8				10000000c9654212				602										0CA7,0CA9,0CAB,0CB3,0CB5,0CB7,0CCF,0EF5				VR3882206		Tier-2 to Tier-4		PH

				tcgppdb3u						10000000c9699fd8				10000000c9654212				300										0C5D,0C61				VR3882206		Tier-2 to Tier-4		PH

				tcgppdb3u						10000000c9699fd8				10000000c9654212				2819										02DE,02DF,02E0,02E1,02E2,02E3				VR3882206		Tier-2 to Tier-4		PH

				uksecprsd57						10000000c93bcc0d				10000000c93bcd46				1811										00D3,00D7,00DB,00DF,00E3,00E7,00EB,00EF,00F3,00F7,00FB,01A5,01A9,01AD,01B1,01B5,01B9,01BD,01C1,01C5,
01C9,01CD,01D1,01D5,01D9,01DD,01E1,01E5,01E9,01ED,01F1,01F5,01F9,01FD,0201,0205,0209,020D,0211,0215,
0219,021D,0221,0237,0239,023B,023D,023F,0241,0243,0245,0247,0249,024B,024D,024F,0251,0253,0255,0257,
0259,025B,025D,025F,0261,0263,0265,0267,0269,026B,026D,026F,0271,0273,0275				VR3881084		Tier-1 to Tier-3		PH

				uksecdrsd57						10000000c93bcd5b				10000000c93bcd0a				1819										00D3,00D7,00DB,00DF,00E3,00E7,00EB,00EF,00F3,00F7,00FB,01A5,01A9,01AD,01B1,01B5,01B9,01BD,01C1,01C5,
01C9,01CD,01D1,01D5,01D9,01DD,01E1,01E5,01E9,01ED,01F1,01F5,01F9,01FD,0201,0205,0209,020D,0211,0215,
0219,021D,0221,0237,0239,023B,023D,023F,0241,0243,0245,0247,0249,024B,024D,024F,0251,0253,0255,0257,
0259,025B,025D,025F,0261,0263,0265,0267,0269,026B,026D,026F,0271,0273,0275				VR3881084		Tier-1 to Tier-3		PH

				weuflxpr						50060b000024166e   
50060b00002416b4				50060b00002422fe   
50060b000024230a				1136										015D,015E,015F,0160,0161,0162,0163,0164,0165,0166,0167,0168,0169,016A,016B,016C,016D,016E,016F,0170
0171,0172,0173,0174,0175,0176,0177,0178,0179,017A,017B,017C,017D,017E,017F,0180,0181,0182,0183,0184
0185,0186,0187,0188,0189,018A,018B,018C,018D,018E,018F,0190,0191,0192,0193,0194,0195,0196,0197,0198
0199,019A,019B,019C,019D,019E,019F,01A0,01A1,01A2,01A3,01A4,01A5,01A6,01A7,01A8,01A9,01AA,01AB,068F
0690,0691,0692,0693,0694				VR3881371		Tier3 reclaim (not used)		PH

				weuflxco						50060b00002422f0   
50060b00002419c4				50060b00002416a6   
50060b0000241680				1081										015D,015E,015F,0160,0161,0162,0163,0164,0165,0166,0167,0168,0169,016A,016B,016C,016D,016E,016F,0170
0171,0172,0173,0174,0175,0176,0177,0178,0179,017A,017B,017C,017D,017E,017F,0180,0181,0182,0183,0184
0185,0186,0187,0188,0189,018A,018B,018C,018D,018E,018F,0190,0191,0192,0193,0194,0195,0196,0197,0198
0199,019A,019B,019C,019D,019E,019F,01A0,01A1,01A2,01A3,01A4,01A5,01A6,01A7,01A8,01A9,01AA,01AB,068F
0690,0691,0692,0693,0694				VR3881371		Tier3 reclaim (not used)		PH

				ukebuuasd69						10000000c93805b3				10000000c935e7c7				96										018B,018F				VR3879645		Server decomm		PH

				ukebuuasd69						10000000c93805b3				10000000c935e7c7				953										0A4C,0A50				VR3879645		Server decomm		PH

				engclus1d						10000000c94916bd				10000000c94917c0				602										1,150,149				VT18764575		Server decomm		PH

				engclus2d						10000000c9491649				10000000c94916e8				602										1,150,149				VT18764575		Server decomm		PH

				EXTRA WORK
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Sheet1

														General SAN Workplan for Saturday 14th February 2009

														Zones		Added		Removed		Members				Added		Removed

														CGC Red		7		0		CGC Red				14		0

														CGC Blue		7		0		CGC Blue				14		0

														RDC Red		4		103		RDC Red				9		207

														RDC Blue		9		4		RDC Blue				19		9

				SYMMETRIX

				Hostname / Zone Alias		Site		Red				Blue				Storage		Symm #		Red				Blue				Device #s		Total		Request		NOTES		QA by

								Sw/Prt		HBA WWN		Sw/Prt		HBA WWN		required		required		FA		sw/pt		FA		sw/pt		required		Space		Number

				Server / Zone RENAMES

				Zone & Disk ADDS

				tiwebcd3lnp		RDC				10000000C9743A05				10000000C97B9021		200		3720		3c0				14c1				346:34b				081002040547				AR

				tiwebcd3ffp		FDC				10000000C97BD631				10000000C97B9021		200		3810		3c0				14c1				346:34b				081009041122				AR

				gcdwbocd1euc		FDC				10000000C97C3184				10000000C97CDB85		250		3564		4c0				13c1				02f8:02ff				090120120732				AR

				ZONE REMOVES

				DISK ADDS

				TCCARSDB1P		CGC										Local														66		090211090219		VR3893148		AJ

				TCCARSDB1C		RDC										Local														66		090211090454		VR3893167		AJ

				TCCARSDB1U		RDC										Local														66		090211085451		VR3885318		AJ

				TCCARSDB1D		RDC										Local														66		090211085127		VR3885296		AJ

				DISK REMOVES

				FDCGTSEBAWD01C		FDC				10000000c9743e39				10000000c9743aa8				3544										035C		34		90205072242		RFC 10807603		AJ

				RDCGTSEBAWD01P		RDC				10000000c973c068				10000000c973c289				3452										035C		34		90205065725		RFC 10807603		AJ

				FDCGTSEBAWD01U		FDC				10000000c9743bb9				10000000c9743b0d				3564										032B		34		90205072856		RFC 10807603		AJ

				TCDSCAIROUA81		RDC				10000000c95a9f05				10000000c95a9eed				1065										0508,0509		66		81212085618		RFC 10774269		AJ

				cmbesxwf0101p		FDC				10000000c9743d85				10000000c9743d3b				602												920		RFC 10820966				AJ

				cmbesxwf0102p		RDC				10000000c9742cee				10000000c974283c				602												920		RFC 10820966				AJ

				cmbesxwf0103p		RDC				10000000c974284b				10000000c9742846				602												920		RFC 10820966				AJ

				cmbesxwf0104p		RDC				10000000c9742ce8				10000000c9742ce7				602												920		RFC 10820966				AJ

				cmbesxwf0105p		RDC				10000000c9675251				10000000c9759b9e				602												920		RFC 10820966				AJ

				cmbesxwf0106p		RDC				10000000c9758433				10000000c9752921				602												920		RFC 10820966				AJ

				cmbesxwf0107p		RDC				10000000c9742856				10000000c9742859				602												920		RFC 10820966				AJ

				cmbesxwf0201p		RDC				10000000c9759cd5				10000000c9758846				602												1380		RFC 10820966				AJ

				cmbesxwf0202p		RDC				10000000c9752984				10000000c9759c23				602												1380		RFC 10820966				AJ

				cmbesxwf0203p		RDC				10000000c9759b80				10000000c97526cb				602												1380		RFC 10820966				AJ

				cmbesxwf0204p		RDC				10000000c9758253				10000000c9753a46				602												1380		RFC 10820966				AJ

				cmbesxwf0205p		RDC				10000000c975ada7				10000000c9759d35				602												1380		RFC 10820966				AJ

				cmbesxwf0206p		RDC				10000000c975a176				10000000c97533d9				602												1380		RFC 10820966				AJ

				cmbesxwf0207p		RDC				10000000c9759e33				10000000c975825f				602												1380		RFC 10820966				AJ

				Symm Configure

				RFC 10807603		UNASSIGN STORAGE - FDCM EBA STEP2																				AJ

				RFC 10620703		SAN ADDITION UKEBUPRSD97																				AJ		Information only

				RFC 10789684		SAN ADDITION UKGTSPRSD28/UKGTSDRSD28																				AJ		Information only

				RFC 10765087		FXFOXGZAP1C RECONFIGURE ECC																				AJ		Information only

				RFC 10768832		ISSAC CONTINUITY OF BUSINESS (COB) TEST																				AJ

				RFC 10774269		GCOT - SAN RETIREMENT/DECOMMISSION																				AJ

				RFC 10793826		ESTABLISH FLEXLNA BCVS IN FDC - flexlna_3452_3544_A																				AJ

				RFC 10798425		SCSU 4.4_C5 INSTALLATION ON UKINFRA-PROD																				AJ		Information only

				RFC 10798905		UAT - TCNCSDEV2 - REMOVE ASSIGNED STORAGE																				AJ		Issue raised

				RFC 10803713		CONVERT T4 OPEN STORAGE TO T4 CLOSED STORAGE																				AJ

				RFC 10816819		CONFIGURE-RDF SWITCHES - RELATED T0 DWDM RFC																				AJ		Information only

				RFC 10808819		MICROCODE UPGRADE ON STORAGE FRAMES																				AJ

				RFC 10811347		SAN RECLAIM - EQSMART5,6,7,8,9,10P																				AJ

				RFC 10811327		SAN RECLAIM - EQKDB1,2P EQKDBAP1,2P																				AJ

				RFC 10804708		ZEUS DATABASE SERVER MIGRATION																				AJ		Information only

				RFC 10821339		DCSM WEEKEND SERVER INSTALLATION/MOVES																				AJ		Information only

				RFC 10820966		NON-270GB DISKS TO BE REMOVED FROM ESX SVRS																				AJ
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Storage Projects and Integration Team - Weekend Change Summary 




14 February 2009



Storage Team Contacts


Carl Williams 


Mobile: +44 (0)7966 466 956



SAN Projects & Integration


Javed Dad
Mobile: +44 (0) 7841 429 769

SAN Projects & Integration – Escalation Contact


Salauddin Ahmed

Mobile: +44 (0)7590 688 935



SAN BAU – Escalation Contact


Other Citi


Piotr Zdunek


Mobile: +48 (0)697 080 689



Network Transport (WAN)



Sharad Gohil









Network Transport (WAN)


Peter Fielding









Network Campus


Dylan Kelly









Infrastructure


Rich Dunn









Infrastructure


Vendor Contact

Qasim Mohammed

Mobile: +44 (0)
78235 32 951



EMC – Site Engineer


Graham Rodell


Mobile: +44 (0)
79205 94 708



EMC – Site Engineer 


EMC call centre


+44 (0) 870 6000300




EMC Duty SAM


List of scheduled work:


· Change of settings on RDF McData switches - 10816819


· Move of DWDM ISL links to new circuits - 10781267

Overview:


· RFC - 10816819 - Change of settings on RDF McData switches


BB Credits will be set to 60 on the DWDM ISL's


Open trunking licences to be applied to all RDF switches in question - confirmed - this feature is available.


Set and apply the conjestion threshold to 60% on the DWDM ISL's


Event notification will be set for back pressure, unresolved conjestion


Low BB Credit Threshold will be set to 50% (30 Credits)


· RFC – 10781267 – Movement of DWDM circuits from O&P to S&T circuits

Symping tests are scheduled to take place before the RDF switch change, pre and post moves.


Supporting Information


RDF fabrics are made up of the following switches:
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		RDC Black RDF Fabric



		Switch

		Switch serial number

		Location

		Connectrix cab

		Fabric

		Model

		Domain ID

		Local IP Address

		Firmware

		Type



		rdfsw92r

		MC5FJ21144

		RDC1

		BX33

		MC5TN01409

		Black

		ED-64M

		4

		10.201.7.1

		9.00.00.76

		rdf



		rdfsw94r

		MC5FJ21146

		RDC4

		M45

		MC5TN01411

		Black

		ED-64M

		8

		10.204.7.1

		9.00.00.76

		rdf



		RDC Green RDF Fabric



		Switch

		Switch serial number

		Location

		Connectrix cab

		Fabric

		Model

		Domain ID

		Local IP Address

		Firmware

		Type



		rdfsw91r

		MC5FJ21148

		RDC1

		BX17

		MC5TN01413

		Green

		ED-64M

		3

		10.201.7.1

		9.00.00.0

		rdf



		rdfsw93r

		MC5FJ21147

		RDC4

		M02

		MC5TN01412

		Green

		ED-64M

		7

		10.204.7.1

		9.00.00.0

		rdf



		CGC Black RDF Fabric



		Switch

		Switch serial number

		Location

		Connectrix cab

		Fabric

		Model

		Domain ID

		IP

		Firmware

		Type



		rdfsw92c

		MC5FJ21143

		TR1/2

		70CF

		MC5TN01408

		BLACK

		ED-64M

		2

		169.186.141.79

		9.00.00.76

		RDF



		rdfsw94c

		MC5FJ21150

		CGC2

		CB14

		MC5TN01415

		BLACK

		ED-64M

		6

		169.186.141.225

		9.00.00.76

		RDF



		CGC Green RDF Fabric



		Switch

		Switch serial number

		Location

		Connectrix cab

		Fabric

		Model

		Domain ID

		IP

		Firmware

		Type



		rdfsw91c

		MC5FJ21145

		TR1/2

		59AN

		MC5TN01410

		GREEN

		ED-64M

		1

		169.186.141.21

		9.00.00.76

		RDF



		rdfsw93c

		MC5FJ21149

		CGC2

		CA96

		MC5TN01414

		GREEN

		ED-64M

		5

		169.186.141.163

		9.00.00.76

		RDF





DWDM ISL are connected via the following ports:


Green Fabric

RDC end: 

CGC end:


Switch 93R Port 28 
Switch 93C Port 28


Switch 93R Port 24
Switch 93C Port 24


Switch 91R Port 28
Switch 91C Port 28

Black Fabric

RDC end: 

CGC end:


Switch 94R Port 28 
Switch 94C Port 28


Switch 94R Port 24
Switch 94C Port 24


Switch 92R Port 24
Switch 92C Port 24

The Links will be moved in the following order



CGC end: 


RDC end:


1) Switch 93C Port 24

Switch 93R Port 24


2) Switch 93C Port 28 
Switch 93R Port 28


3) Switch 91C Port 28

Switch 91R Port 28


20-30 MIN PAUSE


4) Switch 94C Port 24

Switch 94R Port 24


5) Switch 94C Port 28 
Switch 94R Port 28


6) Switch 92C Port 24

Switch 92R Port 24

Approximate schedule is as follows:


SATURDAY


12:00 - 
Post checks on RDF switches/links, counter clear - Green Fabric


12:30 - 
Post checks on RDF switches/links, counter clear - Black Fabric


13:00 - 
Symmping test


13:30 - 
Increase BB Credit and enable O/T on DWDM ISL's - Green Fabric


14:00 - 
Increase BB Credit and enable O/T on DWDM ISL's - Black Fabric


14:30 - 
Symmping test


15:00 - 
Move links 1,2,3 (in that order!)



Monitor links/Through-put


15:30 - 
Move links 4,5,6 (in that order!)



Monitor links/Through-put


16:00 - 
Symmping test



Monitor links/Through-put


MONDAY


16:00 – Application Batch commences



Monitor links/Through-put



Symmping test
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0


			RDC																								Reference															CGC


			San switch /port			link			link			link			link			UNDER FLOOR LINKS			UNDER FLOOR LINKS			DWDM switch/port			Move #			WAN Team ref - Old Circuit			WAN Team ref - New Circuit			WAN Team Doc Ref			Move #			DWDM switch/port			UNDER FLOOR LINKS			link			San switch /port


			sw93r 24			4th/1st port35			1st/4th port35			BU01-Q35-PRT01			Q35-BU01-PRT01			>>>>>			>>>>>			P/RDC/3 card15 client			1			P/CGC2/3, OCI 4 <--> P/RDC/3, OCI 6			T/CGC2/5, slot 17,18 PORT 1 <--> T/RDC/5, slot 1,2 PORT 1			O and P tab Index no. 110			1			Confirmed by infrastructure									sw93c 24


			sw93r 28			4th/1st port36			1st/4th port36			BU01-Q35-PRT02			Q35-BU01-PRT02			Q35-1 to Q06-1			Q06-1 to Q35-1			O/RDC/4 card4 client			2			O/CGC2/4, OCI 15 <--> O/RDC/4, OCI 4			S/CGC2/5, slot 1,2 PORT 7 <--> S/RDC/5, slot 17,18 PORT 7			Not Documented			2			Confirmed by infrastructure									sw93c 28


			sw91r 28			>>>>>			>>>>>			BU01-Q35-PRT03			Q35-BU01-PRT03			>>>>>			>>>>>			P/RDC/2 card3 client			3			P/CGC2/2, OCI 16 <--> P/RDC/2, OCI 8 			S/CGC2/5 slot 1,2 PORT 1 <--> S/RDC/5, slot 17,18 PORT 1
T/CGC2/5, slot 1,2 PORT 7 <--> T/RDC/5, slot 17,18 PORT 7			O and P tab Index no. 109			3			Confirmed by infrastructure									sw91c 28


			sw91r 24			>>>>>			>>>>>			BU01-Q35-PRT04			Q35-BU01-PRT04			Q35-1 to Q06-2			Q06-1 to Q35-2			NOT CONNECTED			n/a			n/a			n/a			n/a			n/a												sw91c 24


			San switch /port			link			link			link			link			UNDER FLOOR LINKS			UNDER FLOOR LINKS			DWDM switch/port			Move #			WAN Team ref - Old Circuit			WAN Team ref - New Circuit			WAN Team Doc Ref			Move #			DWDM switch/port			UNDER FLOOR LINKS			link			San switch /port


			sw94r 24			4th/1st port35			1st/4th port35			BU43-Q06-PRT01			Q06-BU43-PRT01			>>>>>			>>>>>			O/RDC/3 card15 client			4			O/CGC2/3, OCI 4 <--> O/RDC/3, OCI 6 			T/CGC2/5, slot 1,2 PORT 7 <--> T/RDC/5, slot 17,18 PORT 7
S/CGC2/5, slot 1,2 PORT 1 <--> S/RDC/5, slot 17,18 PORT 1			O and P tab Index no. 108			4			Confirmed by infrastructure									sw94c 24


			sw94r 28			4th/1st port36			1st/4th port36			BU43-Q06-PRT02			Q06-BU43-PRT02			Q35-1 to Q06-4			Q06-1 to Q35-4			P/RDC/4 card15 client			5			P/CGC2/4, OCI 4 <--> P/RDC/4, OCI 15			T/CGC2/5,slot 17,18 PORT 7 <--> T/RDC/5, slot 1,2 PORT 7			Not Documented			5			Confirmed by infrastructure									sw94c 28


			sw92r 28			>>>>>			>>>>>			BU43-Q06-PRT03			Q06-BU43-PRT03			Q35-1 to Q06-3			Q06-1 to Q35-3			NOT CONNECTED			n/a			n/a			n/a			n/a			n/a												sw92c 28


			sw92r 24			>>>>>			>>>>>			BU43-Q06-PRT04			Q06-BU43-PRT04			>>>>>			>>>>>			O/RDC/1 card16 client			6			O/CGC2/1, OCI 3 <--> O/RDC/1, OCI 7 			S/CGC2/5, slot 17,18 PORT 7 <--> S/RDC/5, slot 1,2 PORT 7			O and P tab Index no. 107			6			Confirmed by infrastructure									sw92c 24
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SAN FC200 Moves


			


						RFC 10781267 -  SWING 6 X FC200 SAN CNX ACROSS TO "S" AND "T" SUNDAY 14th February 2009


			Sequence:


			1			Circuit 4: Move Cabling on CGC / RDC 2Gig FC 04  across to CGC2/RDC FC200 SAN 004.


						Switch name sw93r 24									Switch name sw93c 24


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						P/RDC/3, OCI 15 CLIENT SIDE			T/RDC/5, MOTR 1/2, Port 1 SC to LC Cable						P/CGC2/3, OCI 4  CLIENT SIDE			T/CGC2/5, MOTR 17/18 Port 1  SC to LC Cable


			2			Circuit 5: Move Cabling on CGC / RDC 2Gig FC 05  across to CGC2/RDC FC200 SAN 005


						Switch name sw93r 28									Switch name sw93c 28


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						O/RDC/4, OCI 4 CLIENT SIDE			S/RDC/5, MOTR 17/18, Port 7 SC to LC Cable						O/CGC2/4, OCI 15 CLIENT SIDE			S/CGC2/5, MOTR 1/2 Port 7  SC to LC Cable


						Black Fabric									Black Fabric


			3			Circuit 3: Move Cabling on CGC / RDC 2Gig FC 03  across to CGC2/RDC FC200 SAN 002.


						Switch name sw91r 28									Switch name sw91c 28


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						P/RDC/2, OCI 3 CLIENT SIDE			T/RDC/5, MOTR 17/18, Port 7 SC to LC Cable						P/CGC2/2, OCI 16 CLIENT SIDE			T/CGC2/5, MOTR 1/2 Port 7  SC to LC Cable


			4			Circuit 2: Move Cabling on CGC / RDC 2Gig FC 02  across to CGC2/RDC FC200 SAN 003.


						Switch name sw94r 24									Switch name sw94c 24


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						O/RDC/3, OCI 15 CLIENT SIDE			S/RDC/5, MOTR 17/18, Port 1 SC to LC Cable						O/CGC2/3, OCI 4 CLIENT SIDE			S/CGC2/5, MOTR 1/2 Port 1  SC to LC Cable


			5			Circuit 6: Move Cabling on CGC / RDC 2Gig FC 06  across to CGC2/RDC FC200 SAN 006


						Switch name sw94r 28									Switch name sw94c 28


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						P/RDC/4, OCI 15 CLIENT SIDE			T/RDC/5, MOTR 1/2, Port 7 SC to LC Cable						P/CGC2/4, OCI 4  CLIENT SIDE			T/CGC2/5, MOTR 17/18, Port 7  SC to LC Cable


						Green Fabric									Green Fabric


			6			Circuit 1: Move Cabling on CGC / RDC 2Gig FC 01  across to CGC2/RDC FC200 SAN 001.


						Switch name sw92r 24									Switch name sw92c 24


						Current Shelf / OCI / Port at RDC			NEW Shelf / OCI / Port at RDC						Current Shelf / OCI / Port at CGC2			NEW Shelf / OCI / Port at CGC2


						O/RDC/1, OCI 16 CLIENT SIDE			S/RDC/5, MOTR 1/2, Port 7 SC to LC Cable						O/CGC2/1, OCI 3 CLIENT SIDE			S/CGC2/5, MOTR 17/18 Port 7  SC to LC Cable











