## Sheet1
General SAN Workplan for Saturday 14th November 2009
[6 empty] | Zones | Added | Removed | Members |  | Added | Removed
[6 empty] | CGC Red | 0 | 0 | CGC Red |  | 0 | 0
[6 empty] | CGC Blue | 0 | 0 | CGC Blue |  | 0 | 0
[6 empty] | RDC Red | 0 | 0 | RDC Red |  | 0 | 0
[6 empty] | RDC Blue | 0 | 0 | RDC Blue |  | 0 | 0
SYMMETRIX
| Hostname / Zone Alias | Site | Red |  | Blue |  | Storage | Symm # | Red |  | Blue |  | Device #s | Total | Request | NOTES | QA by
|  |  | Sw/Prt | HBA WWN | Sw/Prt | HBA WWN | required | required | FA | sw/pt | FA | sw/pt | required | Space | Number
Server / Zone RENAMES
Zone & Disk ADDS
ZONE REMOVES
DISK ADDS
| gcdsgsyb1c |  |  | 10000000C9706372 |  | 10000000C9725D9A | star | 3550 | [5 empty] | 66 | 091110061548 | RFC 11854631 | AJ
| gcdsgsyb2c |  |  | 10000000C979150C |  | 10000000C97B1756 | star | 3550 | [5 empty] | 330 | 091110061730 | RFC 11854631 | AJ
| gcdsgsyb1p |  |  | 10000000C96B3E50 |  | 10000000C96C626D | star | 3471/3336 | [5 empty] | 66 | 091105080031 | RFC 11854631 | AJ
| gcdsgsyb2p |  |  | 10000000C97C85B7 |  | 10000000C9790F07 | star | 3471/3336 | [5 empty] | 330 | 091105080234 | RFC 11854631 | AJ
DISK REMOVES
decommission | ukebuprsd95 | RDC |  | 10000000c95ede9c |  | 10000000c95edea8 | Tier 3 | 2839 | 8b0 |  | 9a0 |  | 09B9,09BA,09BB,09BC |  | 091028090305 | RFC 11860797 | KR
decommission | ukebudrsd95 | CGC |  | 10000000c957881d |  | 10000000c957920d |  | 2838 | 8b0 |  | 9a0 |  | 09B9,09BA,09BB,09BC |  | 091028085503 |  | KR
decommission | ukgtsprsa03 | RDC |  | 10000000c9474ccc |  | 10000000c9474ccd | Tier 3 | 2839 | 7b0 |  | 10a0 |  | 0A93,0A94,0A95 |  | 091028070421 |  | KR
decommission | ukgtsdrsa03 | CGC |  | 10000000c9337326 |  | 10000000c952ee5e |  | 2838 | 7b0 |  | 10a0 |  | 0A93,0A94,0A95 |  | 091028074251 |  | KR
decommission | ldneqtsadn500 | CGC |  | 10000000c95e9b69 |  | 10000000c95e9b68 | Tier 1 | 0603 | 7b0 |  | 10a0 |  | 0821,0825,0829 |  | 0910231013261 |  | KR
decommission | ldneqtsadn600 | RDC |  | 10000000c95ead5c |  | 10000000c95ead5d |  | 0596 | 7b0 |  | 10a0 |  | 0821,0825,0829 |  | 091023101644 |  | KR
decommission | uksecdrsd29 | RDC |  | 10000000c93802c7 |  | 10000000c938052a | Tier 3 | 2839 | 10c0 |  | 7c0 |  | 0AEE,0AEF,0AF0,0AF1,0AF2,0AF3,0AF4,0AF5,0AF6,0AF7,0AF8,0AF9,0AFA,0AFB,0AFC,0AFD,0AFE,0AFF |  | 091006112435 |  | KR
"forsythe" | enetrnu1 | CGC |  | 50060b0000251e64 |  | 50060b000024fc00 | Tier 3 | 298 |  |  |  |  | 0201,0205,0209,020D,0211,0215,0219,021D,0221,0599,059D,05A1,05A5,05A9,05AD,05B1,05B5,05B9,05BD,05C1,05C5,05C9,05CD,05D1,05D5,05D9,05DD |  | VR5079817 |  | DPC
"forsythe" | enetrnu1 | CGC |  | 50060b0000251e64 |  | 50060b000024fc00 | Tier 3 | 877 |  |  |  |  | 01E1,01E5,01E9,01ED,01F1,01F5,01F9,01FD,0201,0211,0213,0215,0217,0219,021B,021D,021F,0435,0437,0439,043B,043D,043F,0441,0443,077B,077F,0885,0887,0889,088B |  | VR5079817 |  | DPC
"forsythe" | enetrnu1 | CGC |  | 50060b0000251e64 |  | 50060b000024fc00 | Tier 3 | 940 |  |  |  |  | F3A,F3B,F3C,F3D,F3E |  | VR5079817 |  | DPC
"forsythe" | l2kmsmt0 | RDC |  | 50060b00001df02e |  | 50060b00001df150 | Tier 3 | 200 |  |  |  |  | 0203,0207 |  | VR5070496 |  | DPC
"forsythe" | l2kmsmt0 | RDC |  | 50060b00001df02e |  | 50060b00001df150 | Tier 3 | 1808 |  |  |  |  | 03DD,03E1 |  | VR5070496 |  | DPC
"forsythe" | emeflxci | RDC |  | 50060b000024e804 |  | 50060b00002506fa | Tier 4 | 1868 |  |  |  |  | 930 LUNS |  | VR5076560 |  | DPC
unused lun removal | cmbesxsf0401p | RDC |  | 10000000c96ff409 |  | 10000000c96ff40e |  | 3452 | 14a0 |  | 3a1 |  | 0803,080B,0813,081B |  | 091027062554 | RFC 11807227 | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0402p | RDC |  | 10000000c96ff39b |  | 10000000c9714d01 | [8 empty] | 091027064326 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0403p | RDC |  | 10000000c96ff789 |  | 10000000c9714b6d | [8 empty] | 091027064601 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0404p | RDC |  | 10000000c96ff395 |  | 10000000c9714b53 | [8 empty] | 091027064749 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0405p | RDC |  | 10000000c9714bbb |  | 10000000c96ff3a8 | [8 empty] | 091027065029 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0406p | RDC |  | 10000000c9711e5c |  | 10000000c971208f | [8 empty] | 091027065358 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0407p | RDC |  | 10000000c9712256 |  | 10000000c9712252 | [8 empty] | 091027065535 |  | KR | wait confirmation from SA to start remove on Saturday
unused lun removal | cmbesxsf0408p | RDC |  | 10000000c9711cb3 |  | 10000000c9711fa4 | [8 empty] | 091027065715 |  | KR | wait confirmation from SA to start remove on Saturday
Symm Configure
EXTRA WORK
| RFC 11860797 | UNUSED SAN REMOVALS AND DECOMMISSIONS | [9 empty] | KR | details are in above "DISK REMOVES"
| RFC 11807227 | FI EMEA - REMOVE 1TB OF PROD ESX STORAGE | [9 empty] | KR | details are in above "DISK REMOVES"; wait confirmation from SA to start remove on Saturday
| RFC 11821718 | PERFORM DISK REMOVES AS PER VR SYSTEM | [9 empty] | KR | Paul Haynes to send the details and will need to be done on Saturday after 14:00hrs
| RFC 11854578 | VTM FOR LONDON 2 CORP_CONS PROD SERVERS | [9 empty] | KR | fyi only
| RFC 11727847 | GOLIVE RFC FOR SMART II AIX SERVERS | [9 empty] | KR | fyi only
| RFC 11860177 | TIVPCGC1 VTM PATCH / COB TEST | [9 empty] | KR | split 09:00AM, establish 11:00AM
| RFC 11860206 | DCSM SERVER DECOMMISSION - 14TH NOVEMBER | [9 empty] | AJ | See below
| RFC 11838708 | UPGRADE DE CENTERA ARRAYS CENTRA* 4.0.2 | [9 empty] | AJ | fyi only
| RFC 11807107 | SP3 PATCHING SMI ZURICH - split establish | [9 empty] | AJ | 09:00 - 13:00
| RFC 11834296 | MOTO UK, US NG COB TEST - splt and establish | [9 empty] | AJ | 12:15 - 17:30
| RFC 11838761 | UPGRADE PL CENTERA ARRAYS CENTRA* 4.0.2 | [9 empty] | AJ | fyi only
| RFC 11847406 | BLK SWCH PRTS REMVE CABLING TO 7C/R & ERASE | [9 empty] | AJ | Block ports
| RFC 11847548 | BLK SWCH PRTS REMVE CABLING TO 11C & ERASE | [9 empty] | AJ | Block ports
| RFC 11854528 | FI EMEA - REMOVE ONE DISK FROM FIIMCAP1EUP/C | [9 empty] | AJ | FYI OS removal only this weekend
| RFC 11854631 | SRDF RECONSTRUCTION FOR TRADEBUS - STAR additions | [9 empty] | AJ | Star disk adds
| RFC 11812486 | RECONFIGURE PORT CHANNEL T2 MEER & IXE PHASE1 | [9 empty] | AJ | fyi only
| RFC 11860870 | GCDSGSYB1P/2P/1C/2C - MAP STAR DISKS | [9 empty] | AJ | AS above - Duplicate
| RFC 11860965 | FIRMWARE UPDATE FOR WRDC XP24K- SENATOSKA | [9 empty] | AJ | fyi only
| RFC 11857247 | SP3 PATCHING SMI FRANKFURT | [9 empty] | AJ | sat 09:00 - May go to Sunday
| RFC 11857127 | SP3 PATCHING SFE NCT | [9 empty] | AJ | sat 09:00 - May go to Sunday
| RFC 11832372 | JFP GR, ES, BE PROD BACKEND DATABASE PATCH | [9 empty] | TW
| RFC 11833169 | JFP PROD GERMANY BACKEND DATABASE UPGRADE
| RFC 11833260 | JFP PROD UK BACKEND DATABASE UPGRADE
| RFC 11833367 | JFP PROD PORTUGAL/ITALY DATABASE UPGRADE
| RFC 11833419 | JFP PROD NORDICS DATABASE UPGRADE
| RFC 11837996 | JFP PROD IPB EMEA DATABASE UPGRADE
| RFC 11832372 | JFP GR, ES, BE & ICARD, CBOL BACKEND DB PATCH
| RFC 11847894 | ATLANTIS ANNUAL COB INVOCATION 15-NOV-2009 -I
| 91104113433 | LDNCTISTRP001 | Null | 25 CANADA SQUARE
| 91027094859 | UKEBUPRSD75 | Null | 25 CANADA SQUARE
| 91104095551 | LDNCTISTRF011 | Null | 33 CANADA SQUARE
| 91104113629 | LDNCTISTRT003 | Null | 33 CANADA SQUARE
| 91104063447 | OLIBIGIP1 | Null | 33 CANADA SQUARE
| 91104063021 | OLIBIGIP2 | Null | 33 CANADA SQUARE
| 91106101737 | UKEBUPRSD01 | Null | 33 CANADA SQUARE
| 91106113953 | UKSECPRSD20 | Null | 33 CANADA SQUARE
| 91106111959 | UKSECPRSD21 | Null | 33 CANADA SQUARE
| 91106112814 | UKSECUASD21 | Null | 33 CANADA SQUARE
| 91106112814 | UKSECUASD21 | Null | 33 CANADA SQUARE
| 91106112814 | UKSECUASD21 | Null | 33 CANADA SQUARE
| 91106112814 | UKSECUASD21 | Null | 33 CANADA SQUARE
| 91106114627 | UKSECUASD25-NEW | Null | 33 CANADA SQUARE
| 91008052739 | EUENGHP1 | Null | 66 MOLESWORTH STREET
| 91007094208 | LDNFTPSW002 | Null | 66 MOLESWORTH STREET
| 91023092117 | CLONERDC | Null | 66 MOLESWORTH STREET
| 91023091849 | OLDSMTE | Null | 66 MOLESWORTH STREET
| 91023091438 | OLDSMTE | Null | 66 MOLESWORTH STREET
| 91023091642 | OLDSMTE | Null | 66 MOLESWORTH STREET
| 91023044407 | RD-ENTTIC1-TIB | Null | 66 MOLESWORTH STREET
| 91104095001 | LDNCTISTRF010 | Null | 66 MOLESWORTH STREET
| 91104095959 | LDNCTISTRF012 | Null | 66 MOLESWORTH STREET
| 91104112304 | LDNCTISTRF019 | Null | 66 MOLESWORTH STREET
| 91104112507 | LDNCTISTRF020 | Null | 66 MOLESWORTH STREET
| 91104112651 | LDNCTISTRF022 | Null | 66 MOLESWORTH STREET
| 91104112851 | LDNCTISTRF023 | Null | 66 MOLESWORTH STREET
| 91104113031 | LDNCTISTRF024 | Null | 66 MOLESWORTH STREET
| 91104094709 | LDNCTISTRF009 | Null | 25 CANADA SQUARE
| 911041132411 | LDNCTISTRF030 | Null | 25 CANADA SQUARE
| 91106055820 | LDNCTISTRF031 | Null | 66 MOLESWORTH STREET
| 91103070444 | FICITIVAP1C | Null | 66 MOLESWORTH STREET
| 91029093121 | EXUKCMBC03 | Null | 66 MOLESWORTH STREET
| 91029093121 | EXUKCMBC03-SUB1 | Null | 66 MOLESWORTH STREET
| 91029093121 | EXUKCMBC03-SUB2 | Null | 66 MOLESWORTH STREET
| 91029093121 | EXUKCMBC03-SUB3 | Null | 66 MOLESWORTH STREET
| 91029091754 | EXUKCMBC04 | Null | 66 MOLESWORTH STREET
| 91029091754 | EXUKCMBC04-SUB1 | Null | 66 MOLESWORTH STREET
| 91029091754 | EXUKCMBC04-SUB2 | Null | 66 MOLESWORTH STREET
| 91029091754 | EXUKCMBC04-SUB3 | Null | 66 MOLESWORTH STREET
| 91029092501 | EXUKCMBC05 | Null | 66 MOLESWORTH STREET
| 91029092501 | EXUKCMBC05-SUB1 | Null | 66 MOLESWORTH STREET
| 91029092501 | EXUKCMBC05-SUB2 | Null | 66 MOLESWORTH STREET
| 91029092501 | EXUKCMBC05-SUB3 | Null | 66 MOLESWORTH STREET
| 91028094640 | EXUKFE01 | Null | 66 MOLESWORTH STREET
| 91029064729 | EXUKFE03 | Null | 66 MOLESWORTH STREET
| 91029064941 | EXUKFE04 | Null | 66 MOLESWORTH STREET
| 91030092120 | RDC-1-J-EXP4000 | Null | 66 MOLESWORTH STREET
| 91106102144 | UKEBUDRSD09 | Null | 66 MOLESWORTH STREET
| 91106101027 | UKEBUDRSD64 | Null | 66 MOLESWORTH STREET
| 91106101425 | UKEBUUASD64 | Null | 66 MOLESWORTH STREET
| 91106114313 | UKSECDRSD20 | Null | 66 MOLESWORTH STREET
| 91106112314 | UKSECDRSD21 | Null | 66 MOLESWORTH STREET
| 91106111209 | UKSECDRSD26 | Null | 66 MOLESWORTH STREET
| 91103113319 | EXUKMB22 | Null | 25 CANADA SQUARE
| 91103113319 | EXUKMB22-SUB1 | Null | 25 CANADA SQUARE
| 91027090742 | LDNCTISF050 | Null | 66 MOLESWORTH STREET
GDCS
| 90904024527 | CGCSGC10 | Null | 25 CANADA SQUARE
| 90904024919 | CGCSGC11 | Null | 25 CANADA SQUARE
| 90904025231 | CGCSGC12 | Null | 25 CANADA SQUARE
| 90904025430 | CGCSGC13 | Null | 25 CANADA SQUARE
| 90904025622 | CGCSGC14 | Null | 25 CANADA SQUARE
| 90904025757 | CGCSGC15 | Null | 25 CANADA SQUARE
| 90904031543 | CGCSGC16 | Null | 25 CANADA SQUARE
| 90904031737 | CGCSGC17 | Null | 25 CANADA SQUARE
| 90904032444 | CGCSGC18 | Null | 25 CANADA SQUARE
| 91029064421 | EXUKFE02 | Null | 25 CANADA SQUARE
| 91103101609 | EXUKMB03 | Null | 25 CANADA SQUARE
| 91103101609 | EXUKMB03-SUB1 | 25 CANADA SQUARE
| 91103103142 | EXUKMB04 | Null | 25 CANADA SQUARE
| 91103103142 | EXUKMB04-SUB1 | 25 CANADA SQUARE
| 91103104002 | EXUKMB07 | Null | 25 CANADA SQUARE
| 91103104002 | EXUKMB07-SUB1 | 25 CANADA SQUARE
| 91103104458 | EXUKMB08 | Null | 25 CANADA SQUARE
| 91103104458 | EXUKMB08-SUB1 | 25 CANADA SQUARE
| 91103102731 | EXUKMB09 | Null | 25 CANADA SQUARE
| 91103102731 | EXUKMB09-SUB1 | 25 CANADA SQUARE
| 911031118001 | EXUKMB18 | Null | 25 CANADA SQUARE
| 911031118001 | EXUKMB18-SUB1 | 25 CANADA SQUARE
| 91103112159 | EXUKMB19 | Null | 25 CANADA SQUARE
| 91103112159 | EXUKMB19-SUB1 | 25 CANADA SQUARE
| 91103112700 | EXUKMB20 | Null | 25 CANADA SQUARE
| 91103112700 | EXUKMB20-SUB1 | 25 CANADA SQUARE
| 91103113018 | EXUKMB21 | Null | 25 CANADA SQUARE
| 91103113018 | EXUKMB21-SUB1 | 25 CANADA SQUARE
| 91104100159 | LDNCTISTRF017 | 25 CANADA SQUARE
| 91104111624 | LDNCTISTRF018 | 25 CANADA SQUARE
| 91028082353 | UKEBUDRSA96 | 25 CANADA SQUARE
| 91106100526 | UKEBUPRSD64 | 25 CANADA SQUARE
| 90923091832 | UKSECPRSD78 | 25 CANADA SQUARE
| 91106111549 | UKSECUASD26 | 25 CANADA SQUARE