## HPNA Project
ID | Task Name | Sub Task | Start Date | End Date | Status | Comments
1 | Project plan assumptions |  | 2015-05-21
2 | Architecture and infrastructure designs |  | 2015-05-21 | 2015-06-08
3 | SAN Inventory |  | 2015-05-22 | 2015-06-08
4 | Discovery Activities |  | 2015-06-07 | 2015-08-30
5 | FID Creation |  | 2015-05-11 | 2015-05-29 | Completed
6 | produce APAC's Naming prefix to HPNA |  | 2015-05-25 | 2015-06-05 | Completed
7 | HPNA access to APAC SAN L3 team |  | 2015-05-25 | 2015-06-30
8 | Cisco | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
9 |  | HPNA FID Integration with Cisco |  |  | Completed
10 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
11 |  | connectivity Testing |  |  | Completed
12 |  | Discovery schedule 1 (HK) | 2015-06-07 | 2015-06-21 | Completed
13 |  | Discovery schedule 2 (SG) | 2015-06-28 | 2015-07-12 | Completed
14 |  | Discovery schedule 3 | 2015-07-19 | 2015-08-02
15 |  | Discovery schedule 4
16 |  | Discovery schedule 5
17 |  | Discovery schedule 6
18 |  | Discovery schedule 4 | 2015-08-09 | 2015-08-23
19 | EMC Symmetrix VMAX | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
20 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
21 |  | HPNA FID Integration with Symauth |  |  | Pending
22 |  | connectivity Testing |  |  | failed | because of Symauth disabled
23 |  | HPNA package installation |  |  | Completed
24 |  | Symauth - enable | 2015-09-01 | 2015-09-15 | Pending
25 |  | Discovery schedule 1 (HK) | 2015-06-14 | 2015-06-28
26 |  | Discovery schedule 2 (SG) | 2015-07-05 | 2015-07-19
27 |  | Discovery schedule 3 | 2015-07-26 | 2015-08-09
28 |  | Discovery schedule 4 | 2015-08-16 | 2015-08-30
29 | VNX File | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
30 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
31 |  | HPNA FID Integration with VNX |  |  | Completed
32 |  | connectivity Testing |  |  | Completed
33 |  | Discovery schedule 1 (HK) | 2015-06-07 | 2015-06-21
34 |  | Discovery schedule 2 (SG) | 2015-06-28 | 2015-07-12
35 |  | Discovery schedule 3 | 2015-07-19 | 2015-08-02
36 |  | Discovery schedule 4 | 2015-08-09 | 2015-08-23
37 | XtremIO | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
38 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
39 |  | HPNA FID Integration with XtremIO |  |  | Completed
40 |  | connectivity Testing |  |  | failed | need to create FID under XMS OS side as well
41 |  | Discovery schedule 1 (HK) | 2015-07-19 | 2015-08-02
42 |  | Discovery schedule 2 (SG) | 2015-08-09 | 2015-08-23
43 | HDS ( USPV/VSP ) | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
44 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
45 |  | HPNA FID Integration with HDS |  |  | Completed
46 |  | connectivity Testing |  |  | Completed
47 |  | Discovery schedule 1 (HK) | 2015-06-14 | 2015-06-28
48 |  | Discovery schedule 2 (SG) | 2015-07-05 | 2015-07-19
49 |  | Discovery schedule 3 | 2015-07-26 | 2015-08-09
50 |  | Discovery schedule 4 | 2015-08-16 | 2015-08-30
51 | IBM XIV | Gather Pre-requisities | 2015-05-25 | 2015-06-08 | Completed
52 |  | Review and Update in Aperture | 2015-05-27 | 2015-06-30 | Completed
53 |  | HPNA FID Integration with HDS |  |  | Completed
54 |  | connectivity Testing |  |  | failed | Because of 7778 port disabled..firewall request is pending
55 |  | Discovery schedule 1 (HK) | 2015-08-09 | 2015-08-23
56 | Exceptions | EMC VNX file |  | N/A
57 |  | EMC CLARiiON |  | N/A
58 |  | EMC Centera |  | N/A
59 |  | EMC DMX |  | N/A
60 | Project Closer |  |  | 2015-09-15
61
62
63
64