## Current Projects
Team | Global Storage Performance
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | HDS RIAT POC | Al Mahmood | TBD | Design | Planning 390G POC. Currently collecting requirements. HDS want to use new software release on Nov 10th.
NAM | Vitrual Instruments (VI) POC | Al Mahmood | TBD | Design | Planning 390G POC. Currently collecting requirements.
NAM | OCI Perform & Plan POC | Al Mahmood | TBD | Design | Planning 390G POC. Currently collecting requirements.

## Closed Projects
Team | Global Storage Performance
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification

## HDS RIAT
Team | Global Storage Performance
Manager | Al Mahmood
Project: | HDS RIAT
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | Collecting POC requirements 390G | Al Mahmood Kery Hines | TBD | Design | HDS wants to use new software being released on Nov 10th.
NAM | Order new VM in 390G for RIAT probe | Kery Hines | 2014-11-07 | Pending | Trying to combine VM request with VI & OCI projects
NAM | Submit firewall rules (need IP from VM) | Kery Hines | 2014-11-14 | Waiting | Need to validate access/rules/ports
NAM | CATE to test new RIAT software | CATE | 2014-11-14 | Waiting | CATE will test once HDS releases the software on Nov 7th
NAM | Setup any FID's/access (read) needed by RIAT software | Kery Hines | 2014-11-21 | Waiting | Need initial CATE blessing to deploy into Prod
NAM | Deploy new RIAT software on CATE OK's | Kery Hines | 2014-11-21 | Waiting | Need initial CATE blessing to deploy into Prod

## Vitrual Instruments
Team | Global Storage Performance
Manager | Al Mahmood
Project: | Virtual Instruments
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | TBD | Design | Still in planning phase
NAM | Order new VM(s) in 390G for VI Wisdom | Kery Hines | TBD | Pending | Trying to combine VM request with RIAT & OCI projects
NAM | CATE to test VI software in Lab | CATE | TBD | Waiting
NAM | Setup any FID's/access (read) needed by VI software (if any) | Kery Hines | TBD | Waiting
NAM | Deploy VI software with CATE's blessing | Kery Hines | TBD | Waiting
NAM | Collect POC requirements 390G for VI Taps | Al Mahmood Kery Hines | TBD | Waiting | After software portion has been completed. Determine arrays to tap (disruptive).

## OCI Perform & Plan
Team | Global Storage Performance
Manager | Al Mahmood
Project: | NetApp OCI Perform & Plan
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | TBD | Design | Still in planning phase
NAM | Order new VM(s) in 390G for OCI | Kery Hines | TBD | Pending | Trying to combine VM request with RIAT & VI projects
NAM | CATE to test OCI software in Lab | CATE | TBD | Waiting
NAM | Setup any FID's/access (read) needed by OCI software (if any) | Kery Hines | TBD | Waiting
NAM | Deploy OCI software with CATE's blessing | Kery Hines | TBD | Waiting