## Discovery Status
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | Scheduled | Completed | % Work Complete
Manually Scheduled | SRM Discovery Activity Status | 35 days | Sat 4/18/15 | Thu 6/4/15 |  |  | 0 | 0 | 0%
Auto Scheduled | Cisco MDS Discovery Activities - SG/HK | 15 days | Sat 4/18/15 | Sat 5/9/15 |  |  | 90 | 90 | 100%
Manually Scheduled | Discovery - Phase1 | 1 day | Sat 4/18/15 | Sat 4/18/15 |  |  | 13 | 13 | 100%
Manually Scheduled | Discovery - Phase2 | 1 day | Sat 4/25/15 | Sat 4/25/15 |  |  | 29 | 29 | 100%
Manually Scheduled | Discovery - Phase3 | 1 day | Sat 5/9/15 | Sat 5/9/15 |  |  | 48 | 48 | 100%
Auto Scheduled | XtremIO Discovery Activities - SG/HK | 5 days | Sat 5/16/15 | Sat 5/23/15 |  |  | 16 | 16 | 100%
Manually Scheduled | Discovery - Phase1 | 1 day | Sat 5/16/15 | Sat 5/16/15 |  |  | 12 | 12 | 100%
Manually Scheduled | Discovery - Phase2 | 1 day | Sat 5/23/15 | Sat 5/23/15 |  |  | 4 | 4 | 100%
Manually Scheduled | NAS/VNX File - SG/HK | 13 days? | Sat 5/16/15 | Tue 6/2/15 |  |  | 3 | 3 | 0%
Manually Scheduled | Discovery - Phase1 | 1 day | Sat 5/16/15 | Sat 5/16/15 |  |  | 2 | 2 | 10%
Manually Scheduled | Discovery - Phase2 | 1 day | Sat 5/23/15 | Sat 5/23/15 |  |  | 1 | 1 | 5%
Manually Scheduled | Discovery - Phase3 | 1 day | Tue 6/2/15 | Tue 6/2/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase4 | 1 day | Sat 5/16/15 | Sat 5/16/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase5 | 1 day | Sat 5/16/15 | Sat 5/16/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase6 | 1 day | Sat 5/16/15 | Sat 5/16/15 |  |  | 0 | 0 | 0%
Auto Scheduled | Clariion/VNX Block - SG/HK | 7 days? | Sat 5/23/15 | Tue 6/2/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase1 | 1 day | Sat 5/23/15 | Sat 5/23/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase2 | 1 day | Tue 6/2/15 | Tue 6/2/15 |  |  | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase3 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase4 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase5 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | IBM XIV - SG/HK | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase1 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase2 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | HDS VSP - SG/HK | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase1 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase2 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase3 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase4 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | VMAX VSP - SG/HK | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase1 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase2 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase3 | [5 empty] | 0 | 0 | 0%
Manually Scheduled | Discovery - Phase4 | [5 empty] | 0 | 0 | 0%

## Tasks
Task No | Main Task | Sub Task | Status
1 | FID Creation | Create FID "srmadmin" & "spg" | Completed
2 | Cisco MDS Discovery Activities - SG/HK | Cisco MDS Discovery Activities - SG/HK | Completed
3 |  | Inventory Review | Completed
4 |  | Pre-requisites | Completed
5 |  | creating SNMP Community String "srmadmin" to facility role | Completed
6 |  | Adding missing ACLs & review the configuration | Completed
7 |  | Plan for Discovery schedules | Completed
8 |  | Review & Confirm the status | Completed
9 | XtremIO Discovery Activities - SG/HK | XtremIO Discovery Activities - SG/HK | Completed
10 |  | Inventory Review | Completed
11 |  | Pre-requisites | Completed
12 |  | creating local ID "srmadmin" as a RO role | Completed
13 |  | Plan for Discovery schedules | Completed
14 |  | Review & Confirm the status | Completed
15 | NAS/VNX File - SG/HK | NAS/VNX File - SG/HK
16 |  | Inventory Review
17 |  | Pre-requisites | In Progress
18 |  | Adding FID "srmadmin" into LDAP group | In Progress
19 |  | Integrate LDAP Group into domain and assign Operator privileges | In Progress
20 |  | Review ACLs configuration | In Progress
21 |  | Disable SSLV3 in control station | In Progress
22 |  | Plan for Discovery schedules
23 |  | Review & Confirm the status
24 | Clariion/VNX Block - SG/HK | Clariion/VNX Block - SG/HK
25 |  | Inventory Review | Completed
26 |  | Pre-requisites | Completed
27 |  | Adding FID "srmadmin" into LDAP group | Completed
28 |  | Integrate LDAP Group into domain and assign Operator privileges | Completed
29 |  | Review ACLs configuration | Completed
30 |  | Enable performance statistics | Completed
31 |  | Plan for Discovery schedules | in progress
32 |  | Review & Confirm the status
33 | IBM XIV - SG/HK | IBM XIV - SG/HK
34 |  | Inventory Review | in progress
35 |  | Pre-requisites | in progress
36 |  | The XIV CIM Agent must be available (In v10.1.0 and higher, it is preinstalled & enabled on the admin module) User Account (Service Account). | in progress
37 |  | workaround must be implemented | in progress
38 |  | script created on the XCLI management server that will run the xcli command “config_get” every 10 minutes | in progress
39 |  | Plan for Discovery schedules
40 |  | Review & Confirm the status
41 | HDS VSP - SG/HK | HDS VSP - SG/HK
42 |  | Inventory Review
43 |  | Pre-requisites
44 |  | Need to upgrade to HCS 8.0.1
45 |  | Installation Checklist Document
46 |  | Package Details
47 |  | SN Change ( 7th Jan 2015 )
48 |  | Upgrade to
49 |  | HCS GUI
50 |  | HCS Tuning Manager
51 |  | HCS CLI
52 |  | HCS TMEA
53 |  | Confirmation after Upgrade
54 |  | Adding FID "srmadmin" into LDAP group
55 |  | Integrate LDAP Group into domain and assign Read Only privileges
56 |  | Plan for Discovery schedules
57 |  | Review & Confirm the status
58 | VMAX - SG/HK | VMAX - SG/HK
59 |  | Inventory Review
60 |  | Pre-requisites
61 |  | for Solution Enabler - Required 2 new Linux Physical Servers in SG & 2 new Linux Physical servers in HK
62 |  | 2 servers - HK
63 |  | Raise TCRS
64 |  | Purchase the Servers
65 |  | Aperture tickets
66 |  | Servers Power ON
67 |  | Network Cabling Request
68 |  | Fibre cable request
69 |  | OS & Patch implementation
70 |  | PowerBroker setup
71 |  | Solution Enabler installation request
72 |  | Zoning & Gate Keeper device assignments
73 |  | SRM will utilize the existing SYMAPI Server to communicate with the Symmetrix Devices via SYMCLI.
74 |  | In the event that the SYMAPI Server uses a "nethost" file, ensure the collector hostname or IP Address
75 |  | is in it. For example, "vm-2981-564 *"
76 |  | VMAX - SymAuth / Acl configurations
77 |  | For Solutions Enabler 7.6.2.25 and higher, only the Monitor role is required for the “srmadmin” user.
78 |  | The “srmadmin” user requires permission to access the storapid daemon in the “daemon_users” file.
79 |  | For Symmetrix Access Control (symacl, if enabled), the user “srmadmin” must be added to an Access Group which has the Access Type “BASE” and “VLOGIX” for all devices
80
81
82
83
84 |  | 2 servers - SG
85 |  | Raise TCRS
86 |  | Purchase the Servers
87 |  | Aperture tickets
88 |  | Servers Power ON
89 |  | Network Cabling Request
90 |  | Fibre cable request
91 |  | OS & Patch implementation
92 |  | PowerBroker setup
93 |  | Solution Enabler installation request
94 |  | Zoning & Gate Keeper device assignments
95 |  | SRM will utilize the existing SYMAPI Server to communicate with the Symmetrix Devices via SYMCLI.
96 |  | In the event that the SYMAPI Server uses a "nethost" file, ensure the collector hostname or IP Address
97 |  | is in it. For example, "vm-2981-564 *"
98 |  | VMAX - SymAuth / Acl configurations
99 |  | For Solutions Enabler 7.6.2.25 and higher, only the Monitor role is required for the “srmadmin” user.
100 |  | The “srmadmin” user requires permission to access the storapid daemon in the “daemon_users” file.
101 |  | For Symmetrix Access Control (symacl, if enabled), the user “srmadmin” must be added to an Access Group which has the Access Type “BASE” and “VLOGIX” for all devices
102
103
104 |  | For Unisphere for Vmax ( U4V) - Required 2 new windows virtual Servers in SG & 2 new Windows Virtual servers in HK
105 |  | Raise TCRS
106 |  | Purchase the VMs
107 |  | OS & Patch implementation
108 |  | Unisphere for Vmax ( U4V) installation request
109 |  | Pre-requisites
110 |  | Unisphere hostname or IP address
111 |  | Unisphere network port (if not the default 8443)
112 |  | Unisphere credentials (Username/Password)
113 |  | SYMCLI credentials (if using ACLs)
114 |  | Logon to the VMAX collector host as “srmadmin” (or use powerbroker to become “srmadmin”) and issue the following commands to verify SYMAPI connectivity:
115 |  | o /opt/emc/SYMCLI/bin/symcfg list
116 |  | o /opt/emc/SYMCLI/bin/symcfg list –sid <SID> list -v

## Tasks - MPP
Task Mode | Task Name | Duration | Start | Finish | Predecessors | Resource Names | % Work Complete
Manually Scheduled | Create FID " srmadmin " & " spg " |  |  |  |  | Ashok | 0%
Manually Scheduled | Cisco MDS Discovery Activities - SG/HK |  |  |  |  | Sunil | 0%
Manually Scheduled | Inventory Review |  |  |  |  | Sunil | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Sunil | 0%
Manually Scheduled | creating SNMP Community String " srmadmin " to facility role |  |  |  |  | Sunil | 0%
Manually Scheduled | Adding missing ACLs & review the configuration |  |  |  |  | Sunil | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Sunil | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Sunil | 0%
Manually Scheduled | XtremIO Discovery Activities - SG/HK |  |  |  |  | Nisha | 0%
Manually Scheduled | Inventory Review |  |  |  |  | Nisha | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Nisha | 0%
Manually Scheduled | creating local ID " srmadmin " as a RO role |  |  |  |  | Nisha | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Nisha | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Nisha | 0%
Manually Scheduled | NAS/VNX File - SG/HK |  |  |  |  | Mohan | 0%
Manually Scheduled | Inventory Review | 1 day | Thu 6/4/15 | Thu 6/4/15 |  | Mohan | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Mohan | 0%
Manually Scheduled | Adding FID " srmadmin " into LDAP group |  |  |  |  | Mohan | 0%
Manually Scheduled | Integrate LDAP Group into domain and assign Operator privileges |  |  |  |  | Mohan | 0%
Manually Scheduled | Review ACLs configuration |  |  |  |  | Mohan | 0%
Manually Scheduled | Disable SSLV3 in control station |  |  |  |  | Mohan | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Mohan | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Mohan | 0%
Manually Scheduled | Clariion/VNX Block - SG/HK |  |  |  |  | Ganesh | 0%
Manually Scheduled | Inventory Review |  |  |  |  | Ganesh | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Ganesh | 0%
Manually Scheduled | Adding FID " srmadmin " into LDAP group |  |  |  |  | Ganesh | 0%
Manually Scheduled | Integrate LDAP Group into domain and assign Operator privileges |  |  |  |  | Ganesh | 0%
Manually Scheduled | Review ACLs configuration |  |  |  |  | Ganesh | 0%
Manually Scheduled | Enable performance statistics |  |  |  |  | Ganesh | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Ganesh | 0%
Manually Scheduled | Review & Confirm the status | [5 empty] | 0%
Manually Scheduled | IBM XIV - SG/HK |  |  |  |  | Nisha | 0%
Auto Scheduled | Inventory Review | 1 day | Thu 6/4/15 | Thu 6/4/15 |  | Nisha | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Nisha | 0%
Manually Scheduled | The XIV CIM Agent must be available (In v10.1.0 and higher, it is preinstalled & enabled on the admin module) User Account (Service Account). |  |  |  |  | Nisha | 0%
Manually Scheduled | workaround must be implemented |  |  |  |  | Nisha | 0%
Manually Scheduled | script created on the XCLI management server that will run the xcli command “config_get” every 10 minutes |  |  |  |  | Nisha | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Nisha | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Nisha | 0%
Manually Scheduled | HDS VSP - SG/HK | [5 empty] | 0%
Auto Scheduled | Inventory Review | 1 day | Thu 6/4/15 | Thu 6/4/15 |  | Ganesh,Sunil | 0%
Manually Scheduled | Pre-requisites |  |  |  |  | Robin | 0%
Manually Scheduled | Need to upgrade to HCS 8.0.1 |  |  |  |  | Robin | 0%
Manually Scheduled | Installation Checklist Document |  |  |  |  | Robin | 0%
Manually Scheduled | Package Details |  |  |  |  | Robin | 0%
Manually Scheduled | SN Change ( 7th Jan 2015 ) |  |  |  |  | Robin | 0%
Manually Scheduled | Upgrade to |  |  |  |  | Robin | 0%
Manually Scheduled | HCS GUI |  |  |  |  | Robin | 0%
Manually Scheduled | HCS Tuning Manager |  |  |  |  | Robin | 0%
Manually Scheduled | HCS CLI |  |  |  |  | Robin | 0%
Manually Scheduled | HCS TMEA |  |  |  |  | Robin | 0%
Manually Scheduled | Confirmation after Upgrade |  |  |  |  | Robin | 0%
Manually Scheduled | Adding FID " srmadmin " into LDAP group |  |  |  |  | Robin | 0%
Manually Scheduled | Integrate LDAP Group into domain and assign Read Only privileges |  |  |  |  | Robin | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | VMAX - SG/HK | [5 empty] | 0%
Manually Scheduled | Inventory Review |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | Pre-requisites | [5 empty] | 0%
Manually Scheduled | for Solution Enabler - Required 2 new Linux Physical Servers in SG & 2 new Linux Physical servers in HK | [5 empty] | 0%
Manually Scheduled | 2 servers - HK | [5 empty] | 0%
Manually Scheduled | Raise TCRS |  |  |  |  | Ganesh | 0%
Manually Scheduled | Purchase the Servers |  |  |  |  | Ashok,Ganesh | 0%
Manually Scheduled | Aperture tickets |  |  |  |  | Saravanan | 0%
Manually Scheduled | Servers Power ON |  |  |  |  | Saravanan | 0%
Manually Scheduled | Network Cabling Request |  |  |  |  | Saravanan | 0%
Manually Scheduled | Fibre cable request |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | OS & Patch implementation |  |  |  |  | Saravanan | 0%
Manually Scheduled | PowerBroker setup |  |  |  |  | Saravanan | 0%
Manually Scheduled | Solution Enabler installation request |  |  |  |  | Ganesh | 0%
Manually Scheduled | Zoning & Gate Keeper device assignments |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | SRM will utilize the existing SYMAPI Server to communicate with the Symmetrix Devices via SYMCLI. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | In the event that the SYMAPI Server uses a " nethost " file, ensure the collector hostname or IP Address |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | is in it. For example, " vm-2981-564 * " |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | VMAX - SymAuth / Acl configurations |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | For Solutions Enabler 7.6.2.25 and higher, only the Monitor role is required for the “srmadmin” user. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | The “srmadmin” user requires permission to access the storapid daemon in the “daemon_users” file. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | For Symmetrix Access Control (symacl, if enabled), the user “srmadmin” must be added to an Access Group which has the Access Type “BASE” and “VLOGIX” for all devices |  |  |  |  | Ganesh,Vivek | 0%
Auto Scheduled | 2 servers - SG | 1 day | Thu 6/4/15 | Thu 6/4/15 |  |  | 0%
Auto Scheduled | Raise TCRS | 1 day | Thu 6/4/15 | Thu 6/4/15 |  | Ganesh | 0%
Manually Scheduled | Purchase the Servers |  |  |  |  | Ashok,Ganesh | 0%
Manually Scheduled | Aperture tickets |  |  |  |  | Saravanan | 0%
Manually Scheduled | Servers Power ON |  |  |  |  | Saravanan | 0%
Manually Scheduled | Network Cabling Request |  |  |  |  | Saravanan | 0%
Manually Scheduled | Fibre cable request |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | OS & Patch implementation |  |  |  |  | Saravanan | 0%
Manually Scheduled | PowerBroker setup |  |  |  |  | Saravanan | 0%
Manually Scheduled | Solution Enabler installation request |  |  |  |  | Ganesh | 0%
Manually Scheduled | Zoning & Gate Keeper device assignments |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | SRM will utilize the existing SYMAPI Server to communicate with the Symmetrix Devices via SYMCLI. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | In the event that the SYMAPI Server uses a " nethost " file, ensure the collector hostname or IP Address |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | is in it. For example, " vm-2981-564 * " |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | VMAX - SymAuth / Acl configurations |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | For Solutions Enabler 7.6.2.25 and higher, only the Monitor role is required for the “srmadmin” user. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | The “srmadmin” user requires permission to access the storapid daemon in the “daemon_users” file. |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | For Symmetrix Access Control (symacl, if enabled), the user “srmadmin” must be added to an Access Group which has the Access Type “BASE” and “VLOGIX” for all devices |  |  |  |  | Ganesh,Vivek | 0%
Auto Scheduled | For Unisphere for Vmax ( U4V) - Required 2 new windows virtual Servers in SG & 2 new Windows Virtual servers in HK | 1 day | Thu 6/4/15 | Thu 6/4/15 |  |  | 0%
Manually Scheduled | Raise TCRS |  |  |  |  | Ganesh | 0%
Manually Scheduled | Purchase the VMs |  |  |  |  | Ganesh | 0%
Manually Scheduled | OS & Patch implementation |  |  |  |  | Wintel | 0%
Manually Scheduled | Unisphere for Vmax ( U4V) installation request |  |  |  |  | Wintel | 0%
Auto Scheduled | Pre-requisites | 1 day | Thu 6/4/15 | Thu 6/4/15 |  |  | 0%
Manually Scheduled | Unisphere hostname or IP address |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | Unisphere network port (if not the default 8443) |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | Unisphere credentials (Username/Password) |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | SYMCLI credentials (if using ACLs) |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | Logon to the VMAX collector host as “srmadmin” (or use powerbroker to become “srmadmin”) and issue the following commands to verify SYMAPI connectivity: /opt/emc/SYMCLI/bin/symcfg list & /opt/emc/SYMCLI/bin/symcfg list –sid < SID > list -v |  |  |  |  | Ganesh,Vivek | 0%
Manually Scheduled | Plan for Discovery schedules |  |  |  |  | Ganesh,Sunil | 0%
Manually Scheduled | Review & Confirm the status |  |  |  |  | Ganesh,Sunil | 0%