## Current Projects
Team | Global Storage Analytic
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | HDS RIAT POC | Al Mahmood | Q1 2015 | In Progress | VM received pending RIAT install; CATE testing new RIAT release |  |  | N/A
NAM | Virtual Instruments (VI) POC | Al Mahmood | Q1 2015 | In Progress | VI provided appliance install guide. Working with 390G procurement team to get loaner equipment approved. |  |  | N/A
NAM | OCI Perform & Plan POC | Al Mahmood | Q1 2015 | In Progress | TCRS submitted for two OCI servers |  |  | N/A

## Closed Projects
Team | Global Storage Analytic
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build

## HDS RIAT
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | HDS RIAT
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Phase1: Prep 390G Build Out | Team | Q4 2014 | In Progress |  |  |  | N/A
NAM | Order new VM in 390G for RIAT probe | Kery Hines Ashok Kumar Reddy | 2014-11-07 | In Progress | TCRS CAP0039085 completed. Need to have VM team install OVA package. | 2014-11-20 | Pending OVA install | N/A
NAM | Obtain new VM IP for FW rules | Kery Hines | 2014-11-20 | In Progress | TCRS CAP0039085 completed new IP provided |  |  | N/A
NAM | Submit firewall rules | Kery Hines | 2014-12-05 | In Progress | CMP WS27236293 submitted 11/20 |  |  | N/A
NAM | Request FID to be used by RIAT software | Kery Hines | 2014-11-21 | In Progress | CMP WS27269015 submitted in 11/21 for FID RIATadmin |  |  | N/A
NAM | Setup FID access. CMP for AD group SAN_View; add RIATadmin to 390G EMC arrays via symauth (monitor role) | Kery Hines | 2014-12-10 | Pending | Waiting for FID to be created |  |  | N/A
NAM | CATE to test new RIAT software | CATE | 2014-12-12 | In Progress | New RIAT version delivered to CATE on Nov 10th, CATE is currently testing. Pre-CIVA discovered 63 issues. HDS reviewing. |  |  | N/A
NAM | CATE OK's RIAT usage in prod | Kery Hines Ashok Kumar Reddy | 2014-12-19 | Waiting | Need initial CATE blessing to begin config/usage in prod |  |  | N/A
NAM | Phase2: Configuration Verification | Team | Q4 2014 | Waiting | . |  |  | N/A
NAM | Configure RIAT on 390G server NAMERIAT01 | Kery Hines Ashok Kumar Reddy | TBD | Waiting |  |  |  | N/A
NAM | Install/configure supporting software EMC Solutions Enabler and IBM XCLI | Kery Hines Ashok Kumar Reddy | TBD | Waiting |  |  |  | N/A
NAM | Determine initial arrays to discover and schedule/perform discovery | Kery Hines Ashok Kumar Reddy | TBD | Waiting | This will test FW rules and access to EMC, IBM & HDS arrays |  |  | N/A
NAM | Discover all arrays in scope. Validate end-to-end RIAT process | Kery Hines Ashok Kumar Reddy | TBD | Waiting |  |  |  | N/A
NAM | Phase3: Evaluation | Team | Q1 2015 | Waiting |  |  |  | N/A
NAM | RIAT evaluation test plan | Team | Q1 2015 | Waiting |  |  |  | N/A
NAM | RIAT results and recommendations | Team | Q1 2015 | Waiting |  |  |  | N/A

## Vitrual Instruments
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | Virtual Instruments
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | Q4 2014 | In Progress | VI team has supplied the installation planning guide for VI appliance. VI team want to perform a site survey. Tyring to arrange with local site team. |  |  | N/A
NAM | Install VI appliance in 390G | Kery Hines | Q4 2014 | In Progress | Working with Citi procurement team (Rosemary Badilla Rodriguez) to get loaner equipment contracts in place. Working with VI team & local site team to schedule a site survey by VI team. |  |  | N/A
NAM | Setup any FID's/access (read) needed by VI software (if any) | Kery Hines | TBD | Waiting |  |  |  | N/A
NAM | Collect POC requirements 390G for VI Taps | Al Mahmood Kery Hines | TBD | Waiting | After software portion has been completed. Determine arrays to tap (disruptive). |  |  | N/A

## OCI Perform & Plan
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | NetApp OCI Perform & Plan
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | Q4 2014 | In Progress | NetApp has provided the server spec of the 2 VM's they require |  |  | N/A
NAM | Order new VM(s) in 390G for OCI | Kery Hines | Q4 2014 | In Progress | Submitting TCRS this week (by Nov 14th) |  |  | N/A
NAM | CATE to test OCI software in Lab | CATE | TBD | Waiting |  |  |  | N/A
NAM | Setup any FID's/access (read) needed by OCI software (if any) | Kery Hines | TBD | Waiting |  |  |  | N/A
NAM | Deploy OCI software with CATE's blessing | Kery Hines | TBD | Waiting |  |  |  | N/A