## General SAN Work
General SAN Workplan for Saturday - 04-06-2011
Action | RFC | Request Number | Total Space |  | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices (required field) | Contact | Comments
|  |  |  | Tier |  |  | required
Decom | 13982956 | 1105050529221 | 133 | Tier-3 | FDC | fdcgtsiscaa01c | 3544 |  | 7C:0 | 10000000c9759ff2 |  | 10C:1 | 10000000c9725d44 | 291,292,293,294 ' | BARTOSZ JABLONSKI | please remove the zones as well fdcgtsiscaa01c_LPFC1_3544_10C1 vsan 11 & fdcgtsiscaa01c_LPFC0_3544_7C0 vsan 10
Decom | 13982956 | 1105050529221 |  | Tier-3 | FDC | fdcgtsiscaa02c | 3544 |  |  | 10000000c9723d57 |  |  | 10000000c97238fb |  |  | please remove the zones as well fdcgtsiscaa02c_LPFC0_3544_7C0 vsan 10 & fdcgtsiscaa02c_LPFC0_3544_7C0 vsan 10
Decom | 13982956 | 110505054435 |  | Tier-3 | RDC | rdcgtsiscaa01p | 3452 |  |  | 10000000c96b43be |  |  | 10000000c96c61e3
Decom | 13982956 | 110505054435 |  | Tier-3 | RDC | rdcgtsiscaa02p | 3452 |  |  | 10000000c96c6427 |  |  | 10000000c96b3d08
Decom | 13982956 | 1105050529221 | 233 | Tier-4 | FDC | fdcgtsiscaa02u | fdchds03_78398 |  | 3H | 10000000c972039d |  | 4H | 10000000c9723e51 | 3C07,3C08,3C09,83:F3,83:F4,83:F5,83:F6 | BARTOSZ JABLONSKI | please remove the zones as well fdcgtsiscaa02u_LPFC1_3564_13A1 vsan 11 & fdcgtsiscaa02u_LPFC0_3564_4A0 vsan 10 & fdcgtsiscaa02u_LPFC0_fdchds03_1FL_3H vsan 10 & fdcgtsiscaa02u_LPFC0_3564_4A0 vsan 10
Decom | 13982956 | 1105240442411 |  |  |  | GCORADB1EUC | [9 empty] | Thomas is working on ..
Removal | 13982956 | 110522232340 | 100 | Tier-4 | RDC | rdcbackleg5 | symconfigure -sid 678 -cmd unbind tdev 0C4A:0C4C,044C,044D,088F,0890,0891 from pool 0678_450_20 preview
Removal | 13982956 | 110522233237 | 166 | Tier-4 | RDC | rdcbackleg6
Removal | 13982956 | 110520090518 | 200 | Tier-4 | RDC | FIGRIDAP2U | 2819 |  | 4C:0, | 10000000c93af609 |  | 13D:0 | 10000000c94fc6bb | 50b,50c,52c,52d,52e,52f | Mariusz Kasinski
Removal | 13982956 | 110520090208 |  | Tier-4 | RDC | FIGRIDAP1U | 2819 |  | 4C:0, | 10000000c945bbb3 |  | 13D:0 | 10000000c945bbe1
Removal | 13982956 | 110509054117 | 100 | Tier-4 | FDC | fdcgcgad001n01p | fdchds02_18779 |  | 1c | 10000000C973FCA4 |  | 2c | 10000000C977BC93 | 00:3C:07,00:60:04,00:60:05,00:80:69 | Sasikumar Pandurangan | Don’t touch to fdcgcgad001n02p
Removal | 13982956 | 110509053522 | 100 | Tier-4 | RDC | rdcgcgad001n01c | RDCHDS02 |  | 1c | 10000000C97C838A |  | 2c | 10000000C97C8449 | 00:3C:00, 00:60:04,00:60:05 , 00:80:00 | Sasikumar Pandurangan
Removal | 13982956 | 1103280226132 |  | Tier-4 | RDC | rdcgcgad001n02c | RDCHDS02 |  | 1c | 10000000C97C8308 |  | 2c | 10000000C97C87A6 |  | Sasikumar Pandurangan
Decom | 13982956 |  | 135.6 | Tier-4 | RDC | RDCGCGAD001N01U | 3452 |  | 8A:1 | 10000000c9795b22 |  | 9A:0 | 10000000c977495f | 08A8,08A9,08AA,08AB,0C99 | Sasikumar Pandurangan
Decom | 13982956 |  |  | Tier-4 | RDC | RDCGCGAD001N02U | 3452 |  | 8A:1 | 10000000c9791131 |  | 9A:0 | 10000000c97c7523

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester |  | RFC Description | VR | Scheduled Date | Initials | Comments
13879119 | HAYNES/PAUL |  | ADD 4 STORAGE NODES TO DE02 CENTERA |  |  |  | PIT Change
13865225 | MURDOCK/STEPHEN |  | QUARTERLY PURGE TO US PROD DATABASE AMUSP1 | WS4141294/WS4141365 |  |  | Split / Establish required but no VR provided.
13903630 | SHAVEZ/CRAIG |  | SAN STACK UPGRADE OVCM |  |  |  | Upgrade the SAN Stack on eurodldn1uksql1 to version 3, may need SPC2 flag updating
13699300 | BABLADI/SACHIN |  | RBCS CREDIT ENGINE SFTP UPGRADE-10.1.47 | WS4091111 |  |  | split/establish required for regbal_3452_3544_A
13987158 | MCBRIDE/J |  | DCSM SERVER DECOMMISSIONS | NA |  |  | Added the details in below
13587291 | EFUNOGBON/TAIWO |  | MIGRATE VL28/29 FROM SOL2SAC19/20 TO 43/44(2) | NA |  |  | Network team change
13726091 | KIRK/MICHAEL |  | EBASTEP2-MSSQL 2005 SP4 INSTALLATION-COB | VR8061727/VR8061781 |  |  | SAN SPLIT/Establish is required
13914326 | HAYNES/PAUL |  | INSTALL 16 DRIVES INTO RDC4-CX4-0576 | NA |  |  | PIT Change
13937579 | HAYNES/PAUL |  | CONFIGURE THE 16 NEW DRIVES ON RDC4-CX4-0576 | NA |  |  | PIT Change
13941827 | DZIEDZIC/JACEK |  | SC3 FLAG ON SMI-ESES | VR8030998 |  |  | SC3 flag on cluster for rdcgtssmiwd10p & rdcgtssmiwd10p
13960380 | SHINDE/YOGESH |  | EMEA GCOT ETD-CVX WINPROD2 SAN ESTABLISHMENT | VR8084736/VR8084718 |  |  | SRDF/STAR isolate and re-join: GCOT_3471_S6
13978169 | MALINOV/A |  | UPDATE CITIDIRECT SSL CERTIFICATES ON COB | WS4128333 |  |  | split/establish required for rdcgtsnetwd01p_78378_78398_05
13982956 | REDDY/ASHOK |  | UNUSED SAN REMOVALS AND DECOMMISSIONS | NA |  |  | Added the details into General SAN work sheet
13968322 | ASHER/VIPUL |  | ORBIFLOW-SSA-COB SYNCHRONISATION | VR8054238/VR8054255 |  |  | SAN SPLIT/Establish is required for rdcgtsorbwd01p_78378_78398_20
DCSM SERVER DECOMMISSION
UK activity
110524050037 | 66 MOLESWORTH STREET | LDNMDSRDCON002
110524075916 | 66 MOLESWORTH STREET | RDCBACKH1
110524075916 | 66 MOLESWORTH STREET | RDCBACKH2
110524075916 | 66 MOLESWORTH STREET | RDCBACKH2
110526053843 | 66 MOLESWORTH STREET | FIATPAP6C
110526054918 | 66 MOLESWORTH STREET | FIATPAP7C
110526055557 | 66 MOLESWORTH STREET | FIATPAP9C
110526060257 | 66 MOLESWORTH STREET | FIMKTVLAP1C
110527082905 | 66 MOLESWORTH STREET | UKCTIDVSW30
110527112728 | 66 MOLESWORTH STREET | UKSECUASD80
110527113800 | 66 MOLESWORTH STREET | UKSECUASW80
110527115921 | 66 MOLESWORTH STREET | UKSECDRSD80
110527120419 | 66 MOLESWORTH STREET | UKSECDRSA80
110527120755 | 66 MOLESWORTH STREET | UKSECDRSD84
110527121345 | 66 MOLESWORTH STREET | UKSECUASA80
1105271220271 | 66 MOLESWORTH STREET | UKSECUASD84
110523133641 | 33 CANADA SQUARE | THOMSONONE
110524045531 | 33 CANADA SQUARE | LDNMDSCWDART1
110524045752 | 25 CANADA SQUARE | ldnmdscwcon002
110524074203 | 33 CANADA SQUARE | CGCBACKH1
110524074203 | 33 CANADA SQUARE | CGCBACKH1-SUB1
110524074203 | 33 CANADA SQUARE | CGCBACKH2
110524074203 | 33 CANADA SQUARE | CGCBACKH2-SUB1
1105260545011 | 25 CANADA SQUARE | FIATPAP7P
110526055232 | 25 CANADA SQUARE | FIATPAP9P
110526060028 | 25 CANADA SQUARE | FIMKTVLAP1P
110526064647 | 25 CANADA SQUARE | M1GBOL2-CRS01-D2950
110526070602 | 25 CANADA SQUARE | M1GBOL2-CRS02-D1950
110526070853 | 25 CANADA SQUARE | S6200-BRIDGE
110526081909 | 25 CANADA SQUARE | FIATPAP6P
110527084505 | 25 CANADA SQUARE | UKHCB670AS009
110527094434 | 33 CANADA SQUARE | KS4-CISW
110527094730 | 33 CANADA SQUARE | CISC KS 1
110527094853 | 33 CANADA SQUARE | CISC KS 2
110527095028 | 33 CANADA SQUARE | CISC KS 3
1105270951551 | 33 CANADA SQUARE | SBAR KS 2
110527095351 | 33 CANADA SQUARE | SBAR KS 3
110527095536 | 33 CANADA SQUARE | SBAR 1
110527122802 | 33 CANADA SQUARE | KS2-CIYL
110527123212 | 33 CANADA SQUARE | KS3-CIYL
110527123539 | 33 CANADA SQUARE | KS4-CIYL
110527123808 | 33 CANADA SQUARE | KS5-CIYL
110527124009 | 33 CANADA SQUARE | KS6-CIYL
110527124223 | 33 CANADA SQUARE | KS7-CIYL
110527124427 | 33 CANADA SQUARE | KS9-CIYL
110527124723 | 33 CANADA SQUARE | KSC-CIYL
110530074302 | 25 CANADA SQUARE | UKSECPRSA80
110530075443 | 25 CANADA SQUARE | UKSECPRSW80
110530075911 | 25 CANADA SQUARE | UKSECPRSD80
110530080423 | 33 CANADA SQUARE | UKSECPRSD84
German activities
decom | 110318121541 | Heinrich-Lanz-Allee | FDCGTSODSWDPOC1
decom | 110513211240 | Westerbachstr. | FRAWARSA020UA
decom | 110511182624 | Westerbachstr. | FRAEBOSA007DR
decom | 110515024958 | Reuterweg | fdewel-cpx04-m8
decom | 110527025118 | Reuterweg | FRAWARSD014UA
decom | 110525073538 | Reuterweg | FRAGTSSA002DV
decom | 110515025827 | Heinrich-Lanz-Allee | eufwfdcmcast01
decom | 110515025827 | Heinrich-Lanz-Allee | eufwfdcmcast02
decom | VT30884866 | Westerbachstr. | eufwwes01
decom | VT30884866 | Westerbachstr. | eufwwes02
decom | VT30884866 | Westerbachstr. | ffgltapl2euc
decom | VT30884866 | Westerbachstr. | ffgltapl4euc
decom | VT30884866 | Westerbachstr. | ffjsap2euc
decom | VT30884866 | Westerbachstr. | ffmnis02
decom | VT30884866 | Westerbachstr. | ffmsoe02
decom | VT30884866 | Westerbachstr. | ffoctap2euc
decom | VT30884866 | Westerbachstr. | fft-gl3
decom | VT30884866 | Westerbachstr. | fft-gl9
decom | VT30884866 | Westerbachstr. | fftxen02
decom | VT30884866 | Westerbachstr. | frauxiplt01dr
decom | VT30884866 | Westerbachstr. | frauxiplt02dr
decom | VT30884866 | Westerbachstr. | frauxlosrep02
decom | VT30884866 | Westerbachstr. | wbs-csd1-sf
decom | VT30884866 | Westerbachstr. | wbs-csd2-sf

## Sheet1
Decom Servers
old
DEGCBPRSD001 | 110429054215
DEGCBDRSD001 | 110429052429
rdcgcgad001n02c | 1103280226132
gcebsap1bec_old | 110420122456
fdcgtsiscaa01c | 1105050529221
rdcgtsiscaa01p | 110505054435
fdcgtsiscaa01c | 1105050529221
GCORADB1EUC | 1105240442411
RDCGTSFPGAD01P | 1105161140152
rdcbackleg5 | 110522232340
rdcbackleg6 | 110522233237
FIGRIDAP2U | 110520090518
FIGRIDAP1U | 110520090208
fdcgcgad001n01p | 110509054117
rdcgcgad001n01c | 110509053522
fdcgcgad002n02p | 110216025944
RDCGCGAD001N01U
RDCGCGAD001N02U