## Sheet1
General SAN Workplan for Saturday 6th February 2010
[6 empty] | Zones | Added | Removed | Members | Added | Removed
[6 empty] | CGC Red | 0 | 0 | CGC Red | 0 | 0
[6 empty] | CGC Blue | 0 | 0 | CGC Blue | 0 | 0
[6 empty] | RDC Red | 0 | 0 | RDC Red | 0 | 0
[6 empty] | RDC Blue | 0 | 0 | RDC Blue | 0 | 0
[6 empty] | RDC Ruby | 0 | 0 | RDC Ruby | 0 | 0
[6 empty] | RDC Jade | 0 | 0 | RDC Jade | 0 | 0
[6 empty] | FDC Ruby | 0 | 0 | FDC Ruby | 0 | 0
[6 empty] | FDC Jade | 0 | 0 | FDC Jade | 0 | 0
SYMMETRIX
| Hostname / Zone Alias | Site | Red |  | Blue |  | Storage | Symm # | Red | Blue |  | Device #s | Total | Request | NOTES | QA by
|  |  | Sw/Prt | HBA WWN | Sw/Prt | HBA WWN | required | required | FA | FA | sw/pt | required | Space | Number
Server / Zone RENAMES
Zone & Disk ADDS
| p595-5-rdc-vioa | RDC |  | 10000000C97C08B1 |  | 10000000C97C040F |  | 3452 | 3cb | 14ca |  | 0501 | 33Gb | VR5438871 |  | DPC
|  |  |  | 10000000C979FDEB |  | 10000000C979E5B5
| p595-5-rdc-viob | RDC |  | 10000000C97DC106 |  | 10000000C97DBCBF
|  |  |  | 10000000C979E649 |  | 10000000C979E3E9
ZONE REMOVES
FDC RUBY fdcgtsnavad01u_LPFC0_fdchds03_1FL_3H fdcgtsnavad02u_LPFC0_fdchds03_1FL_3H FDC JADE fdcgtsnavad01u_LPFC1_fdchds03_2RL_4H fdcgtsnavad02u_LPFC1_fdchds03_2RL_4H
DISK ADDS
DISK REMOVES
Removal | rdcgtsdela03p | RDC |  | 10000000c97c7721 |  | 10000000c974f3da |  | 3452 | 3bb | 14ba |  | 0442 | 33gb | 100126070048 |  | AR
Removal | rdcgtsdela04p | RDC |  | 10000000c97c7480 |  | 10000000c9762a06 |  | 3452 | 3bb | 14ba |  | 0440, 0441 | 66gb | 100126063944 |  | AR
move | gcopsora1d | RDC |  | 10000000C96C2D2D |  | 10000000C96B432A |  | 3452 | 3cb | 14ca |  | 0501 | 33Gb | VR5438871 |  | DPC
Symm Configure
EXTRA WORK
| RFC 12103515 | EQ DB CLUSTER MOVE / COB TEST | [8 empty] | KR | Start between 12:00 and 14:00, Finish 18:00 (approx)
| RFC 12132114 | UPGRADE OF CONNECTRIX MANAGER SVR/CLIENT | [8 empty] | KR | SAN BAU work; 02/04/10 09:00 02/09/10 17:00
| RFC 11828666 | UPGRADE TR CENTERA ARRAYS TO CENTRA* 4.0.2 | [8 empty] | KR | SAN PIT Work; 02/06/10 00:01 to 02/07/10 18:00
Postponed | RFC 11992013 | EBASTEP2-SECURITY PATCH Q05USP32 FOR SQL 2005 | [8 empty] | KR | RDCGTSEBAWD01P/FDCGTSEBAWD01C replication group name - eba2_3452_3544_A; split 09:00, establish 13:00
Postponed | RFC 11994932 | RAINBOW-SECURITY PATCH Q05USP32 FOR SQL 2005 | [8 empty] | KR | RDCGTSRBWWD01P/FDCGTSRBWWD01C replication group name - rdcgtsrbwwd01p_3720_3810_A13; split 12:00, establish 18:00
| RFC 12135910 | TCMFONDB2U - LOGICAL MOVE - RDC | [8 empty] | KR | zoning,lun masking are required for new HBAs; 09:00 - 18:00
| RFC 12144316 | TO PERFORM MANUAL PURGE ON RCX PROD DATABASE | [8 empty] | AR | SAN split/establish required; 02/05/10 18:00 to 02/08/10 23:59
| RFC 12144470 | DCSM SERVER DECOMMISSION | [8 empty] | AR | 02/05/10 20:00 to 02/08/10 23:00
| RFC 12049023 | LU MULTIFONDS UPGRADE FROM V3.2 TO V3.4 | [8 empty] | AR | Split/Establish required ; 02/06/10 01:00 to 02/07/10 23:55
| RFC 12077443 | PURGE TO US PRODUCTION DATABASE AMUSP1 | [8 empty] | AR | Split/Establish required; 02/06/10 06:00 to 02/07/10 18:00
| RFC 12078179 | CABLING OF NEW CISCO MDS9500 TO SYMMS | [8 empty] | AR | SAN PIT Chage; 02/06/10 14:00 to 02/07/10 18:00
| RFC 12111228 | DCSM WEEKEND CGC2 MOVES 6TH FEB | [8 empty] | AR | Info Only; 02/06/10 07:00 to 02/07/10 23:59
| RFC 12131802 | HDS MICROCODE UPGRADE | [8 empty] | AR | SAN BAU Work; 02/06/10 14:00 to 02/07/10 23:00
| RFC 12132325 | SMI NEXUS AWE SETTINGS - RDCGTSSMIWD25P/26P & FDCGTSSMIWD25C/26C- secmi-am_3452_3544_A | [8 empty] | AR | Split/Establish Required; 02/06/10 09:00 to 02/07/10 19:00
| RFC 12138528 | EMC MICROCODE UPGRADE | [8 empty] | AR | SAN BAU Work; 02/06/10 14:00 to 02/07/10 23:00
| RFC 12138827 | PERFORM DISK REMOVES AS PER VR SYSTEM | [8 empty] | AR | Forsyth Disk reclaims; 02/06/10 14:00 to 02/07/10 13:59
| RFC 12140113 | LINE CARD TRANSFER BETWEEN FDC SWITCHES | [8 empty] | AR | SAN PIT work; 02/06/10 14:00 to 02/07/10 18:00
| RFC 12132325 | COB SPLIT | [8 empty] | JM | Raised issue - no time line and rep grps - check
| RFC 12149703 | COB TEST - GLOBAL PRIME & IPB DATASERVER | [8 empty] | DPC | GP COB test SPLIT 11:00 / ESTABLISH 13:00 - IPB COB test SPLIT 10:00 / ESTABLISH 13:00
| DCSM SERVER DECOMMISSION |  |  |  |  | DCSM WEEKEND CGC2 MOVES 6TH FEB
| UK activity |  |  |  |  | UKGTSPRSD16 *GT IN CITIDOCS
| Tracking # | Building | Device Name |  |  | SUPPORT;citidocs.support@polaris.co.in;showkat.khan@polaris.co.in
| 100113204903 | 66 Molesworth Street | eugendbd |  |  | UKSECPRSD88 *GT EU Recon Technology
| 1001150751471 | 66 Molesworth Street | CAP-13-2501 |  |  | UKEUWUASW01 *GT EMEA eSystems WINTEL
| 100115095027 | 66 Molesworth Street | AMS1B-SALOMONUK |  |  | UKSECPRSD13 *GT UK Wintel Technology Not to be touched till 14:00
| 100115095027 | 66 Molesworth Street | AMS1B-SALOMONUK |  |  | UKWARPRSD06 *GT UK Wintel Technology Not to be touched till 14:00
| 100115103153 | 66 Molesworth Street | AMS1N-SALOMONUK |  |  | UKGTSDRSD33 *GT UK AI Support
| 100118095424 | 66 Molesworth Street | SYMM12R |  |  | UKCTEPRSNT10*GT EMEA Wintel GTS SA
| 100124185020 | 66 Molesworth Street | SOLARPSLN4
| 100124185020 | 66 Molesworth Street | SOLARPSLN4
| 100124185020 | 66 Molesworth Street | SOLARPSLN4
| 100125094425 | 66 Molesworth Street | UKINFDRSD01
| 100126070507 | 66 Molesworth Street | UKFXDVSD14
| 100126080655 | 66 Molesworth Street | WINTELPOOL32
| 100127035936 | 66 MOLESWORTH STREET | tcbamap1d
| 100127035936 | 66 MOLESWORTH STREET | tcbamap1p
| 100127035936 | 66 MOLESWORTH STREET | tcbamap2p
| 100127035936 | 66 MOLESWORTH STREET | tcbamdb1d
| 100127035936 | 66 MOLESWORTH STREET | tcbamdb1p
| 100127035936 | 66 MOLESWORTH STREET | tcbamdb2p
| 100127100845 | 66 Molesworth Street | FICITIVAP1D
| 100127103826 | 66 Molesworth Street | FICITIVAP1U
| 100128095153 | 66 Molesworth Street | UKEAGPRSD03-P
| 1001290518001 | 66 Molesworth Street | UKGTSDRSD24
| 100129052303 | 66 Molesworth Street | UKGTSUASD24
| 100129100413 | 66 Molesworth Street | UKGTSUASD25
| 100129101732 | 66 Molesworth Street | UKEBUDRSD09
| 100129102447 | 66 Molesworth Street | UKEBUDRSD64
| 100129102743 | 66 Molesworth Street | UKEBUUASD64
| 100129103419 | 66 Molesworth Street | UKEBUDRSD02
| 100201054003 | 66 Molesworth Street | RD-DDTIC1-TIB
| 100115115246 | 33 CANADA SQUARE | CAP11-1019
| 100115120225 | 33 CANADA SQUARE | CAP12-1019
| 100115120619 | 33 CANADA SQUARE | CAP13-1019.eur.nsroo
| 100115120927 | 33 CANADA SQUARE | CAP14-1019.eur.nsroo
| 100115121139 | 33 CANADA SQUARE | CAP16-1019
| 100115121357 | 33 CANADA SQUARE | SIA AMSIB
| 100115121357 | 33 CANADA SQUARE | SIA AMSIN
| 100115121357 | 33 CANADA SQUARE | SIA SWITCHIN
| 100125090155 | 33 CANADA SQUARE | UKINFPRSD01
| 1001271025381 | 33 CANADA SQUARE | FICITIVAP2P
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129063814 | 33 CANADA SQUARE | uksecuasd25old
| 100129100926 | 33 CANADA SQUARE | UKEBUPRSD01
| 100201053149 | 33 CANADA SQUARE | CW-DDTIC1-TIB
| 100201055021 | 33 CANADA SQUARE | CW-NFSSERVER1-SF
| 100201055021 | 33 CANADA SQUARE | CW-NFSSERVER1-SF
| 100118100010 | 25 CANADA SQUARE | SYMM06C MODEM
| 100118100130 | 25 CANADA SQUARE | SYMM12C MODEM
| 100122055905 | 25 CANADA SQUARE | FISIMPASW1C
| 100125080351 | 25 CANADA SQUARE | FISIMPDBW1C
| 100125080529 | 25 CANADA SQUARE | FISIMPGNW1C
| 100125105415 | 25 CANADA SQUARE | fisimpcal1c
| 100126063429 | 25 CANADA SQUARE | tcbamap1c
| 100126063429 | 25 CANADA SQUARE | tcbamap1u
| 100126063429 | 25 CANADA SQUARE | tcbamap2u
| 100126063429 | 25 CANADA SQUARE | tcbamdb1c
| 100126063429 | 25 CANADA SQUARE | tcbamdb1u
| 100126063429 | 25 CANADA SQUARE | tcbamdb2u
| 100126063746 | 25 CANADA SQUARE | EQITRS1C
| 100126083256 | 25 CANADA SQUARE | UKCFUASD01
| 100126083256 | 25 CANADA SQUARE | UKCFUASD01
| 100127043952 | 25 CANADA SQUARE | EUTIGRID1P
| 100127044843 | 25 CANADA SQUARE | EUTIGRID2P
| 100127051626 | 25 CANADA SQUARE | gtscbdap01c
| 100127092228 | 25 CANADA SQUARE | TCSFADMIN-CGC4
| 1001270942002 | 25 CANADA SQUARE | UKGCBSD003
| 100127095258 | 25 CANADA SQUARE | UKSECPRSD56
| 100128060912 | 25 CANADA SQUARE | NUKCGC2-QES01
| 100128075238 | 25 CANADA SQUARE | FIGCALIN0070
| 100128094709 | 25 CANADA SQUARE | UKEAGDRSD03-P
| 100129051010 | 25 CANADA SQUARE | LDNCTINAS111
| 100129051010 | 25 CANADA SQUARE | LDNCTINAS111
| 100129051010 | 25 CANADA SQUARE | LDNCTINAS111
| 100129051010 | 25 CANADA SQUARE | LDNCTINAS111
| 100129051010 | 25 CANADA SQUARE | LDNCTINAS111
| 100129051140 | 25 CANADA SQUARE | UKGTSPRSD24
| 100129053220 | 25 CANADA SQUARE | LDNCTINAS112
| 100129053220 | 25 CANADA SQUARE | LDNCTINAS112
| 100129053220 | 25 CANADA SQUARE | LDNCTINAS112
| 100129053220 | 25 CANADA SQUARE | LDNCTINAS112
| 100129053220 | 25 CANADA SQUARE | LDNCTINAS112
| 100129055126 | 25 CANADA SQUARE | LDNCTINAS113
| 100129055126 | 25 CANADA SQUARE | LDNCTINAS113
| 100129055126 | 25 CANADA SQUARE | LDNCTINAS113
| 100129055126 | 25 CANADA SQUARE | LDNCTINAS113
| 100129055126 | 25 CANADA SQUARE | LDNCTINAS113
| 100129061354 | 25 CANADA SQUARE | LDNCTINAS114
| 100129061354 | 25 CANADA SQUARE | LDNCTINAS114
| 100129061354 | 25 CANADA SQUARE | LDNCTINAS114
| 100129061354 | 25 CANADA SQUARE | LDNCTINAS114
| 100129061354 | 25 CANADA SQUARE | LDNCTINAS114
| 100129072615 | 25 CANADA SQUARE | LDNCTINAS115
| 100129072615 | 25 CANADA SQUARE | LDNCTINAS115
| 100129072615 | 25 CANADA SQUARE | LDNCTINAS115
| 100129072615 | 25 CANADA SQUARE | LDNCTINAS115
| 100129072615 | 25 CANADA SQUARE | LDNCTINAS115
| 100129074102 | 25 CANADA SQUARE | LDNCTINAS116
| 100129074102 | 25 CANADA SQUARE | LDNCTINAS116
| 100129074102 | 25 CANADA SQUARE | LDNCTINAS116
| 100129074102 | 25 CANADA SQUARE | LDNCTINAS116
| 100129074102 | 25 CANADA SQUARE | LDNCTINAS116
| 100129102133 | 25 CANADA SQUARE | UKEBUPRSD64
| 100129103116 | 25 CANADA SQUARE | UKEBUPRSD03
Germany activity
| Reuterweg | FRAUXBACK02 | 091006101842