## General SAN Work
General SAN Workplan for Saturday - 05-03-2011
Action | RFC | Request Number | Total Space |  | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices # | Contact | Comments
|  |  |  | Tier |  |  | required | [6 empty] | Required
LUN Migration | RFC#13602708 | 110218084403 | 2000 | Tier-4 | RDC | eqkdb5p | 0678 |  | 08H:0 | 10000000c99f9d68 |  | 08H:1 | 10000000c99fa056 | 1147,114F,1157,115F,1167,116F,1177,117F |  | Moving luns to eqkdb3/4p
LUN Migration | RFC#13602708 | 110218084403 |  | Tier-4 | RDC | eqkdb6p |  |  |  | 10000000c99f9d76 |  |  | 10000000c99fa010
LUN Migration | RFC#13602708 | 110218084542 | 2000 | Tier-4 | CGC | eqkdb7p | 0623 |  | 9F:0 | 10000000c9b0ae5a |  | 8F:1 | 10000000c9b0bf2e | 05F0,05F8,0600,0608,0610,0618,0620,0628 |  | moving luns to eqkdb1/2p
LUN Migration | RFC#13602708 | 110218084730 |  | Tier-4 | CGC | eqkdb8p |  |  |  | 10000000c9b09542 |  |  | 10000000c9b0bcb4
| RFC#13602708 | 1102240107572 |  |  |  | fdcgcgatlad01p
Removal | RFC#13602708 | 110224132151 | 100 | Tier-4 | FDC | FDCGTSINFWC02U | 78398 |  |  | 10000000C999CC94 |  |  | 10000000C999CA4A | 82:C8 TO 82:CA
Removal | RFC#13602708 | 110224132023 |  | Tier-4 | FDC | FDCGTSINFWC01U | 78398 |  |  | 10000000C999D982 |  |  | 10000000C999D2D2
Removal | RFC#13602708 | 110224131839 | 100 | Tier-3 | FDC | FDCGTSINFWC02C | 78398 |  |  | 10000000C999CD0A |  |  | 10000000C999CD0B | 72:0C to 72:0E
Removal | RFC#13602708 | 110224131715 |  | Tier-3 | FDC | FDCGTSINFWC01C | 78398 |  |  | 10000000C999D1D0 |  |  | 10000000C999D1D1
Removal | RFC#13602708 | 110224131556 |  | Tier-3 | RDC | RDCGTSINFWC02P | 78378 |  |  | 10000000C9935397 |  |  | 10000000C98FDA8C
Removal | RFC#13602708 | 110224131051 |  | Tier-3 | RDC | RDCGTSINFWC01P | 78378 |  |  | 10000000C99350EF |  |  | 10000000C99359FA
| RFC#13602708 | 110216025408 |  |  |  | rdcgcgad002n02u | [7 empty] | 81:E9 to
| RFC#13602708 | 110216025800 |  |  |  | rdcgcgad002n02c
| RFC#13602708 | 110216025944 |  |  |  | fdcgcgad002n02p
UNUSED | RFC#13602708 | VT#29520132 | 842.9 | Tier-3 | RDC | ukgtsprsd28 | 2839 |  |  | 10000000c95e506f |  |  | 10000000c95e5ad9 | 0940,0941,0942,0AA1,0ABE,0AC3,0AC4,0AC5,0AC6,0B1B,0B1C,0B1D,0B29,0B2A,0B2B,0B2C,0B2D,0B2E,0B2F,0B30,0B31,0B32,0B35,0B36,0B37 | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 |  | Tier-3 | CGC | ukgtsdrsd28 | 2838 |  |  | 10000000c95e5eb1 |  |  | 10000000c95e5df7 |  | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 269.7 | Tier-3 | CGC | ukgtsprsd06 | 2838 |  |  | 10000000c93e5181 |  |  | 10000000c93b9dd3 | 0B03,0B04,0B05,0B06,0B07,0B08,0B09,0B0A | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 |  | Tier-3 | RDC | ukgtsdrsd06 | 2839 |  |  | 10000000c9422ee0 |  |  | 10000000c94235f8 |  | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 101.2 | Tier-3 | CGC | ukgtsprsd15 | 2838 |  |  | 10000000c93b9cc7 |  |  | 10000000c93bb873 | 08AF,08B0,08B1 | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 |  | Tier-3 | RDC | ukgtsdrsd15 | 2839 |  |  | 10000000c93af546 |  |  | 10000000c93bb940 |  | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 134.9 | Tier-3 | CGC | ukgtsprsd24 | 2838 |  |  | 10000000c952f9de |  |  | 10000000c952f9bb | 08B2,08B3,08B4,08B5 | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 |  | Tier-3 | RDC | ukgtsdrsd24 | 2839 |  |  | 10000000c9516ebc |  |  | 10000000c95180b9 |  | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 101.2 | Tier-3 | CGC | uksecprsa86 | 2838 |  |  | 10000000c9436726 |  |  | 10000000c9473e83 | 08B6,08B7,08B8 | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 |  | Tier-3 | RDC | uksecdrsa86 | 2839 |  |  | 10000000c94368ee |  |  | 10000000c9436736 |  | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | RDC | fiimcap1euu | 2839 |  |  | 10000000c935cdfa |  |  | 10000000c935e7b3 | 03DF,03E0 | Kasinski, Mariusz
UNUSED | RFC#13602708 | VT#29520132 | 4.3 | Tier-4 | RDC | tcswnetqa1 | 2819 |  |  | 10000000c93ed41c |  |  | 10000000c93ed4cb | 0D3F,0D40,0D41,0D42,0D43,0D44 | Dmitruk, Grzegorz
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | RDC | ukemdrsa02 | 2819 |  |  | 10000000c93e5188 |  |  | 10000000c93e514d | 064C,064D | Kochan, Pawel
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | RDC | ukemdrsa03 | 2819 |  |  | 10000000c93b9a55 |  |  | 10000000c93e5157 | 064E,064F | Kochan, Pawel
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | RDC | ukemuasa01 | 2819 |  |  | 10000000c93e5370 |  |  | 10000000c93e54d6 | 0A24,0A25 | Kochan, Pawel
UNUSED | RFC#13602708 | VT#29520132 | 101.2 | Tier-4 | RDC | ukgtsuasd16 | 2819 |  |  | 10000000c9473c4f |  |  | 10000000c9473c50 | 04FC,058C,058D | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 101.2 | Tier-4 | RDC | eqeuro2u | 1065 |  |  | 10000000c96908b7 |  |  | 10000000c9690885 | "0052,0053,0054" | Bazan, Wojciech
UNUSED | RFC#13602708 | VT#29520132 | 337.2 | Tier-4 | RDC | ukgtsuasd28 | 1065 |  |  | 10000000c95e5c92 |  |  | 10000000c95e5e2d | 04B7,04B8,04B9,04BA,04BB,04BC,04BD,04BE,04BF,04C0 | Mcbride, Walter
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | CGC | eqnfsap3p | 1868 |  |  | 10000000c95f9254 |  |  | 10000000c95f98a4 | " 0634,0635" | Bazan, Wojciech
UNUSED | RFC#13602708 | VT#29520132 | 708.1 | Tier-4 | CGC | tcncsuat2 | 1868 |  |  | 10000000c935c5c1 |  |  | 10000000c935a8a1 | 0587,0588,0589,058A,058B,058C,058D,058E,058F,0590,0591,0592,0593,0594,0595,0596,0597,0598,0599,059A,059B | Dmitruk, Grzegorz
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | CGC | ukemprsa01 | 1868 |  |  | 10000000c93b9ba7 |  |  | 10000000c93b9bd1 | 0679,067A | Kochan, Pawel
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | CGC | ukemprsa02 | 1868 |  |  | 10000000c93a796c |  |  | 10000000c93a7977 | 067D,067E | Kochan, Pawel
UNUSED | RFC#13602708 | VT#29520132 | 67.4 | Tier-4 | CGC | ukemprsa03 | 1868 |  |  | 10000000c93e4ede |  |  | 10000000c93b9abd | 063E,063F | Kochan, Pawel
Decomm's and Removals Process
Week 1 - Remove masking (presentation to server, all paths)
Week 2 - Remove zoning

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester |  | RFC Description |  |  |  | VR | Scheduled Date | Initials | Comments
13541996 | LYSZKOWSKI/JAN |  | VTM FOR LONDON 1 CORP_CONS PROD SERVERS | [6 empty] | Check san servers affected are ok.
13541985 | LYSZKOWSKI/JAN |  | VTM FOR LONDON 2 CORP_CONS PROD SERVERS | [6 empty] | Check san servers affected are ok.
13547896 | HAYNES/PAUL |  | UPGRADE FIRMWARE OF 1 SWITCH IN CGC | [6 empty] | PIT Change
13554540 | HAYNES/PAUL |  | CHECK AND MOVE POWER CONS ON CISCO (WELLE) | [6 empty] | PIT Change
13580389 | MARCHONG/F |  | DATA MGRTN FROM 10R/14R->RDCHDS04 PREP TASKS | [6 empty] | PIT
13587449 | DARRAGH/PETER |  | MSSQL SP4 INSTALL ON CHECKS32 SAA |  |  |  | VR7514660 |  |  | Split/Establish
13570311 | AHMED/SAL |  | FIRMWARE UPDATE FOR WRDC XP24K- SENATOSKA | [6 empty] | PIT
13555047 | BARGODE/SWARUP |  | EBASTEP2/BACS COB TEST - MOVE BACK TO PROD |  |  |  | VR7465528 / VR7465540
13592939 | HESLOP/A |  | MANTAS DEV LPAR MOVE | [6 empty] | DPC has raised an issue against this as this an a migration Aperture should be enough for this.
13581010 | KOLVER/KEITH |  | STRATUS DEV/UAT LIVE COB TEST - SWITCH BACK |  |  |  | NA |  |  | PIT
13472389 | KLUTH/MANFRED |  | ECB5 - GOLIVE MIGRATION TO FDC |  |  |  | NA |  |  | PIT
13592533 | DARRAGH/PETER |  | MSSQL SP4 INSTALL ON CHECKS32 MENA | [6 empty] | Sync & Split
13593616 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EGWWINIM |  |  |  | NA |  |  | PIT
13594394 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUEGVMA |  |  |  | NA |  |  | PIT
13593340 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUGMWSM |  |  |  | NA |  |  | PIT
13593303 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUCTIWPA |  |  |  | NA |  |  | PIT
13593278 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUCTFA |  |  |  | NA |  |  | PIT
13593244 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUG3SAA |  |  |  | NA |  |  | PIT
13593198 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUGTSSAA |  |  |  | NA |  |  | PIT
13593153 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION10R/14R-WK2-EUINFRAENG |  |  |  | NA |  |  | PIT
13596865 | HAYNES/PAUL |  | CHECK AND MOVE POWER CON ON CISCO (UK) |  |  |  | NA |  |  | PIT
13591717 | WILLIAMS/CARL |  | INSTALLATION OF EXPANSION TO VMAX ARRAY - FDC |  |  |  | NA |  |  | PIT
13591535 | WILLIAMS/CARL |  | INSTALLATION OF NEW VMAX ARRAY - FDC |  |  |  | NA |  |  | PIT
13495833 | COLES/DAVID |  | EMC DMX4 5772 TO 5773 MICROCODE UPGRADE |  |  |  | NA |  |  | PIT
13591679 | WiLIAMS/CARL |  | FW UPGRADE ON SAN SW TO VERSION 4.2.1A |  |  |  | NA |  |  | PIT
13603036 | SWARUP/GANESH |  | PERSPECTIVE ANNUAL COB TEST |  |  |  | VR#7555168 |  |  | SPLIT/Establish : ldnsissdpp001_78378_78398_24
13609293 | BAZAN/WOJCIECH |  | STORAGE RECLAIM FROM EQKDB5/6/7/8P |  |  |  | NA |  |  | Added the details into Disk Removes
13609498 | MCBRIDE/J |  | DCSM SERVER DECOMMISSIONS |  |  |  | NA |  |  | Added the details in below
13257070 | RUDOLF/M |  | GDOS EMEA-TCFESECPROD82 -EMC STORAGE MIGR |  |  |  | NA |  |  | 19R/20R migration work
13602708 | REDDY/ASHOK |  | UNUSED SAN REMOVALS AND DECOMMISSIONS |  |  |  | NA |  |  | Added the details into Disk Removes
13602914 | THOMPSON/ANDREW |  | TSY: DB CUT BACK TO PRODUCTION |  |  |  | VR 7537285 |  |  | Failback required : ldntsy01sdpr_3720_3810_A17
13603373 | DARRAGH/PETER |  | MSSQL 05 CU7 ON CHECKS-32 SSA |  |  |  | VR#7538345 |  |  | Sync & Split
13603494 | DARRAGH/PETER |  | MSSQL 05 CU7 ON CHECKS-32 MENA |  |  |  | VR#7539783 |  |  | Sync & Split required ; ukebuprsd98_0552_0745 ;
13603566 | DZIEDZIC/ADAM |  | NEW STORAGE FOR FXMM (STAR) |  |  |  | NA
13609286 | DZWIGALA/PAWEL |  | GDOS EMEA- TCTAPAP2P -EMC STORAGE MIGR |  |  |  | NA |  |  | 19R/20R migration work
13405109 | WENNER/MARTIN |  | UAT DECOM OLD ORBIT BROKERAGE DATABASE SERVER |  |  |  | NA |  |  | Info Only
DCSM SERVER DECOMMISSION
UK | activity
101115061112 | 66 | MOLESWORTH | STREET | rdcgtsgtusa01c
1101061129054 | 66 | MOLESWORTH | STREET | R10040-LDN
110107132139 | 66 | MOLESWORTH | STREET | LSE1-CGM5-3825a | / | VZB
wos89245
110107132658 | 66 | MOLESWORTH | STREET | LSE1-CGM5-3825b
110113034248 | 66 | MOLESWORTH | STREET | CISCO2600 | BI35
110119062018 | 66 | MOLESWORTH | STREET | RDC-1-M-FM4000
110119062807 | 66 | MOLESWORTH | STREET | EGBRDC-1-NRZH
110128034355 | 66 | MOLESWORTH | STREET | SW22R_EDGE_BLUE_RDC3
110128045304 | 66 | MOLESWORTH | STREET | RDCGTSSFEWA01P
110209074604 | 66 | MOLESWORTH | STREET | SWIFT | FIN | DUALP-1RDC
110210102514 | 66 | MOLESWORTH | STREET | TCUBXDB1C
110223090729 | 66 | MOLESWORTH | STREET | UKHRGDRSW05
110223090935 | 66 | MOLESWORTH | STREET | UKHRGDRSD05
110223091539 | 66 | MOLESWORTH | STREET | UKCTIDRSD14
110224005214 | 66 | MOLESWORTH | STREET | rdcgcgatlad01c
110224005214 | 66 | MOLESWORTH | STREET | rdcgcgatlad01u
110224094920 | 66 | MOLESWORTH | STREET | FXFOXDEV2
110224095428 | 66 | MOLESWORTH | STREET | FXFOXUAT5
110224121433 | 66 | MOLESWORTH | STREET | EUBMCAP3C
1102251210052 | 66 | MOLESWORTH | STREET | EUBMCAP4C
110228073910 | 66 | MOLESWORTH | STREET | UKSECDRSD57
110228074432 | 66 | MOLESWORTH | STREET | UKSECUASD57
101011022844 | 25 | CANADA | SQUARE | SYMM09C
101011090044 | 25 | CANADA | SQUARE | SYMM19C-STORAGE-A
101011090044 | 25 | CANADA | SQUARE | SYMM19C-STORAGE-B
101011090044 | 25 | CANADA | SQUARE | SYMM19C-SYSTEM
101025042744 | 25 | CANADA | SQUARE | SYMM18C-STORAGE-A
101025042930 | 25 | CANADA | SQUARE | SYMM18C-STORAGE-B
1010250431301 | 25 | CANADA | SQUARE | SYMM18C-SYSTEM
110118093009 | 25 | CANADA | SQUARE | ROL2VGW01
110125073520 | 33 | CANADA | SQUARE | LDNMDSCWDLDTS5
110125075815 | 33 | CANADA | SQUARE | LDNMDSCWDLDTS6
110223053409 | 33 | CANADA | SQUARE | ROL1DIN01
110223053728 | 33 | CANADA | SQUARE | GPRS
1102230902501 | 25 | CANADA | SQUARE | UKHRGPRSW05
110223090517 | 25 | CANADA | SQUARE | UKHRGPRSD05
110223091209 | 25 | CANADA | SQUARE | UKCTIPRSD14
110223091352 | 25 | CANADA | SQUARE | UKCTIPRSD14-SUB
1102241233301 | 25 | CANADA | SQUARE | EUBMCAP3P
110225101928 | 33 | CANADA | SQUARE | FLXCGCP0
110225101928 | 33 | CANADA | SQUARE | FLXCGCP1
110225123711 | 25 | CANADA | SQUARE | EUBMCAP4P
110228072607 | 25 | CANADA | SQUARE | UKSECPRSD57
German | activities
decom | 110209113948 | Reuterweg | EUFWWELL02
decom | 110215195854 | Reuterweg | FRAGOPSA002UA
decom | 110215193918 | Reuterweg | fragopsa002dv

## Sheet1
fdcgcgatlad01p | RFC#13602708 | 1102240107572 | R50049A26095
FDCGTSINFWC02U | RFC#13602708 | 110224132151 | R50049A26096
FDCGTSINFWC01U | RFC#13602708 | 110224132023 | R50049A26097
FDCGTSINFWC02C | RFC#13602708 | 110224131839 | R50049A26098
FDCGTSINFWC01C | RFC#13602708 | 110224131715 | R50049A2609C
RDCGTSINFWC02P | RFC#13602708 | 110224131556 | R50049A2609D
RDCGTSINFWC01P | RFC#13602708 | 110224131051 | R50049A2609E
rdcgcgad002n02u | RFC#13602708 | 110216025408 | R50049A2609F
rdcgcgad002n02c | RFC#13602708 | 110216025800 | R50049A260A0
fdcgcgad002n02p | RFC#13602708 | 110216025944 | R501322A3C0F
eqkdb5p | RFC#13602708 | 110218084120 | R501322A3C10
eqkdb6p | RFC#13602708 | 110218084403 | R501322A81E9
eqkdb7p | RFC#13602708 | 110218084542 | R501322A81EA
eqkdb8p | RFC#13602708 | 110218084730 | R501322A81EB
ukgtsdrsd28 | RFC#13602708 | VT#29520132 | R501322A81EC
ukgtsprsd06 | RFC#13602708 | VT#29520132 | R501322A81ED
ukgtsprsd15 | RFC#13602708 | VT#29520132 | R501322A81F2
ukgtsprsd24 | RFC#13602708 | VT#29520132 | R501322A81F3
uksecprsa86 | RFC#13602708 | VT#29520132 | R501322A81F4
ukgtsdrsd06 | RFC#13602708 | VT#29520132 | R501322A81F5
ukgtsdrsd15 | RFC#13602708 | VT#29520132 | R501322A8241
ukgtsdrsd24 | RFC#13602708 | VT#29520132
ukgtsprsd28 | RFC#13602708 | VT#29520132
uksecdrsa86 | RFC#13602708 | VT#29520132
fiimcap1euu | RFC#13602708 | VT#29520132
tcswnetqa1 | RFC#13602708 | VT#29520132
ukemdrsa02 | RFC#13602708 | VT#29520132
ukemdrsa03 | RFC#13602708 | VT#29520132
ukemuasa01 | RFC#13602708 | VT#29520132
ukgtsuasd16 | RFC#13602708 | VT#29520132
eqeuro2u | RFC#13602708 | VT#29520132
ukgtsuasd28 | RFC#13602708 | VT#29520132
eqnfsap3p | RFC#13602708 | VT#29520132
tcncsuat2 | RFC#13602708 | VT#29520132
ukemprsa01 | RFC#13602708 | VT#29520132
ukemprsa02 | RFC#13602708 | VT#29520132
ukemprsa03 | RFC#13602708 | VT#29520132