## General SAN Work
General SAN Workplan for Saturday - 19-02-2011
Action | RFC | Request Number | Total Space | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices # | Contact | Comments
[6 empty] | required | [6 empty] | Required
removal | 13554452 | 110111065723 | 792 | FDC | p7-780-12-fdc-v-id60 | 879 |  | 8fb | c0507602e03f01d8 / c0507602e03f01dc |  | 9fa | c0507602e03f01da / c0507602e03f01de | 01C9,01CA,01CB,01CC,01CD,01CE,01CF,01D0,01D1,01D2,01D3,01D4,01D5,01D6,01D7,01D8,01D9,01DA,01DB,01DC,01DD,01DE,01DF,01E0 | Kevin Donald | Due to FDC MGTs are not working
removal | 13442599 | 101208045541 | 160 | FDC | gctmtsamlap1ffd | 879 |  | 8ea | 10000000c99c72d5 |  | 9eb | 10000000c99c79e3 | 0445,0437,0438,0439,043A |  | Due to FDC MGTs are not working
| 13442599 | VR6962079 | 166 | FDC | tifarmcd8ffp(tieauditcd1p) | 3943 |  |  | 10000000c9715ef2 |  |  | 10000000c9716530 | 489,48a,48b,490,492 | Jeyaraj, Lenin | Due to FDC MGTs are not working
decom | 13442599 | 1101071206021 | 33 | FDC | FDCGTSCBEWA02DV | 879 |  | 08F:0 | 10000000c93b7df5 |  | 09F:1 | 10000000c93e4e96 | 1380 | Walter McBride | Due to FDC MGTs are not working
decom | 13442599 | 1101071141432 | 33 | FDC | FDCGTSCBEWA01DV | 879 |  | 7H:1 | 10000000c9448cea |  | 10H:0 | 10000000c93b7e41 | 1548 | Walter McBride | Due to FDC MGTs are not working
decom | 13442599 | 1101071135172 | 135 | FDC | FDCGTSCBEWD02DV | 879 |  | 07G:1 | 10000000c935b1ec |  | 10G:0 | 10000000c935b1eb | 0A4A,0A4B,0A4C,0A4D,0B2A | Walter McBride | Due to FDC MGTs are not working
decom | 13442599 | 1101071127072 |  | FDC | FDCGTSCBEWD01DV |  |  |  | 10000000c93382d3 |  |  | 10000000c93e4f2f |  | Walter McBride | Due to FDC MGTs are not working
migration | 13442599 | 110203060223 | 734 | RDC | tcmfondb4u | 13462 |  |  | 10000000C956291A |  |  | 10000000C953F895 | A8:09 - A8:1E | Michal Pytka | Not enough time to complete
Lun Migration | 13473066 | 110125071049 | 33 | RDC | eqecom1p | 0552 |  | 7E:0 | 10000000C975665C |  | 10E:1 | 10000000C9756A9F | 041D | Wojtek Bazan | Postponed
Lun Migration |  | 110125071759 |  | CGC | eqecom1c | 0552 |  | 7E:0 | 10000000C97570FF |  | 10E:1 | 10000000C9756638 |  | Wojtek Bazan | Postponed
Removal | 13442599 | VT29170198 | 101 | FDC | fdcgtsmfaad01u | 879 |  | 7H:1 | 10000000c99c8ec5 / 10000000c99c8ec4 |  | 10H:0 | 10000000c9c0cac8 / 10000000c9c0cac9 | 01EA,01EB,01EC,158A | Paul Holman | Due to FDC MGTs are not working
Removal | 13442599 |  |  | FDC | fdcgtsmfaad02u |  |  |  | 10000000c99c93e8 / 10000000c99c93e9 |  |  | 10000000c99c9274 / 10000000c99c9275 |  |  | Due to FDC MGTs are not working
Removal | 13442599 | VT29040206 | 101 | FDC | fdcgtsmfaad03u |  |  | 7H:1 | 10000000c99c90a2 / 10000000c99c90a3 |  | 10H:0 | 10000000c9c0bb06 / 10000000c9c0bb07 | 01ED,01EE,01EF,158B |  | Due to FDC MGTs are not working
Removal | 13442599 |  |  |  | fdcgtsmfaad04u |  |  |  | 10000000c99c60dc / 10000000c99c60dd |  |  | 10000000c99c92e0 / 10000000c99c92e1 |  |  | Due to FDC MGTs are not working
Removal | 13555350 | 110125071049 / 110125071759 | 34.5GB | RDC / CGC | eqecom1p / eqecom1c | 0552 / 0745 | [6 empty] | 041D | BAZAN/WOJCIECH | This is a removal of 1 disk from these servers to an add on servers below.
Add | 13555350 | 110125074029 / 110125073927 / 110125073625 / 110125072840 / 110125072739 / 110125072516 | 34.5GB | CGC / RDC | EQQFF3C / EQQFF2C / EQQFF1C / EQQFF3P / EQQFF2P / EQQFF1P | 0745 / 0552 | [6 empty] | 041D | BAZAN/WOJCIECH | Add the disk removed above to the servers on this row.
|  | 110126052433 |  |  | fisybdb7p
|  | 1011300837232 |  |  | fiap6d
|  | 1101071206021 |  |  | FDCGTSCBEWA02DV
|  | 1101071141432 |  |  | FDCGTSCBEWA01DV
|  | 1101071135172 |  |  | FDCGTSCBEWD02DV
|  | 1101071127072 |  |  | FDCGTSCBEWD01DV
|  | 110203060223 |  |  | tcmfondb4u
|  | 110125071049 |  |  | eqecom1p
|  | 110125071759 |  |  | eqecom1c
|  | 110204045033 |  |  | TCCCSTDB1D
|  | VT29170198 |  |  | fdcgtsmfaad01u
|  | VT29170198 |  |  | fdcgtsmfaad02u
|  | VT29040206 |  |  | fdcgtsmfaad03u
|  | VT29040206 |  |  | fdcgtsmfaad04u
|  | 110111065723 |  |  | p7-780-12-fdc-v-id60
|  | 101208045541 |  |  | gctmtsamlap1ffd
|  | VR6962079 |  |  | tifarmcd8ffp(tieauditcd1p)
|  | 110211013858 |  |  | rdcgcgatlad01u
|  | 110211013736 |  |  | rdcgcgatlad01c
|  | 110211013430 |  |  | fdcgcgatlad01p
|  | 110210231644 |  |  | tiasysap002lnu
|  | VT#29320708 |  |  | VT#29320708
Decomm's and Removals Process
Week 1 - Remove masking (presentation to server, all paths)
Week 2 - Remove zoning

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR | Scheduled Date | Initials | Comments
13548093 | HAYNES/PAUL | PERFORM DISK REMOVES AS PER VR SYSTEM | N/A |  |  | PIT Change
13536482 | SWARUP/GANESH | PERSPECTIVE/INFOGLIDE APP TEST IN COB ENV | VR7464444 |  |  | SPLIT/Establish required - ldnsissdpp001_78378_78398_24
13536395 | MARCHONG/F | EMEA SAN-HDS MIGRATION19R/20R-WK11-EUGTSSAA | N/A |  |  | HDS Migrations
13536378 | MARCHONG/F | EMEA SAN-HDS MIGRATION19R/20R-WK11-EUGMWSM | N/A |  |  | HDS Migrations
13524365 | EBEL/MICHAEL | MULTIVERSA IBS/IFP COB TEST | VR7465148 /  VR7465164 /  VR7465194 |  |  | Replication operations required
13519407 | HAYNES/PAUL | INSTALL ADDITIONAL DISKS INTO RDCHDS04 | N/A |  |  | PIT Change
13509487 | MURDOCK/STEPHEN | QUARTERLY PURGE TO US PROD DATABASE AMUSP1 | VR7475510 / VR7475542
13473175 | HAYNES/PAUL | UPGRADE OF MCDATA FIRMWARE RED AND GREEN | N/A |  |  | PIT Change
13472389 | KLUTH/MANFRED | ECB5 - GOLIVE MIGRATION TO FDC |  |  |  | PIT Change
12821056 | GIBBS/SIMON | EMC DMX4 5772 TO 5773 MICROCODE UPGRADE | N/A |  |  | PIT Change
13483599 | GAWRYS/ARTUR | UAT: CHANGE BUNDLE Q1 2011: JFP EU |  |  |  | Issue Raised to determine impact and involvement of SAN team.
13548895 | HAYNES/PAUL | CHECK AND MOVE POWER CONNECTIONS ON CISCO | N/A |  |  | PIT Change
13396421 | MURALIDHARAN/D | CAPE MQ 7.0.1.3 UPGRADE | VR7464402 |  |  | Need to approve RFC after issue closed, all looks good.
13554751 | HARRISON/VANUK | TSY: DB CUT BACK TO PRODUCTION | VR7464828 |  |  | Failback - ldntsy01sdpr_3720_3810_A17
13554896 | MCBRIDE/J | DCSM SERVER DECOMMISSIONS | N/A |  |  | Information
13555350 | BAZAN/WOJCIECH | SRDF LUN MOVE FROM ECOM TO QFF | N/A |  |  | This is for a Lun to be removed from some servers and then presented to others. See General SAN Work tab for information on this RFC.
DCSM SERVER DECOMMISSION
UK activity