## General SAN Work
General SAN Workplan for Saturday - 08-12-2012
SAN Removals
Action | RFC | Request Number | Total Space GB | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices (required field) | Contact | Comments | CONFIIRMATION
decommission |  | 121123094038 |  |  | FISTMAP1C | [8 empty] | MAREK BARCZYK | mcdata
decommission |  | 121123093317 |  |  | FISTMAP1P | [8 empty] | MAREK BARCZYK | mcdata
decommission |  | 1211210927002 |  |  | EQSMART2U | [8 empty] | Kamil Seweryn | mcdata
decommission |  | 1211210630501 |  |  | eqperf2u | [8 empty] | Dawid Kosenczuk | mcdata
decommission |  | 1211210628151 |  |  | eqperf1u | [8 empty] | Dawid Kosenczuk | mcdata
decommission |  | 121108100917 |  |  | gcblzap1eup | [8 empty] | DB35844 | Priority - Pending from Last week-mcdata
decommission |  | VT40669014 |  |  | ukebuuasd28 | [8 empty] | DB35844 | Priority - Pending from Last week - Mcdata
decommission |  | 1210231025522 | tape zoning to remove |  | rdcbackn71 |  |  |  | ? |  |  | ? |  | Dominik Mierzejewski | Priority - Pending from Last week - rdcbackh71 to confirm?? | waiting confirmation
decommission |  | 1210231029182 | tape zoning to remove |  | wdcbackn71 |  |  |  | 10:00:00:00:c9:97:bb:93 |  |  | 10:00:00:00:c9:97:c0:09 |  | Dominik Mierzejewski | Priority - Pending from Last week | waiting confirmation
decommission |  | 1211081003271 |  |  | GCEBSAP1BEP | [8 empty] | DB35844
decommission |  | 1211081007281 |  |  | GCEBSAP2BEP | [8 empty] | DB35844
VT40570644
VT40672763
FOR RE-scheduling (Customer request)
decommission |  | 1211301038181 |  |  | rdcgcgipbaa01p | 3720 |  | 7A:0 | 10:00:00:00:c9:6c:2e:c0 10:00:00:00:c9:6b:ff:81 |  | 10A:1 | 10:00:00:00:c9:6c:25:99 10:00:00:00:c9:6c:65:19 | 0525:0527 | DB35844

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR/Aperture | Scheduled Date | Initials | Comments | STATUS
16309313 |  | DS/E/RZ/Y NEW SERVER BUILD