## General SAN Work
General SAN Workplan for Saturday
[6 empty] | Zones | Added | Removed | Members | Added | Removed
[6 empty] | CGC Red | 0 | 0 | CGC Red | 0 | 0
[6 empty] | CGC Blue | 0 | 0 | CGC Blue | 0 | 0
[6 empty] | RDC Red | 0 | 0 | RDC Red | 0 | 0
[6 empty] | RDC Blue | 0 | 0 | RDC Blue | 0 | 0
[6 empty] | RDC Ruby | 0 | 0 | RDC Ruby | 0 | 0
[6 empty] | RDC Jade | 0 | 0 | RDC Jade | 0 | 0
[6 empty] | FDC Ruby | 0 | 0 | FDC Ruby | 0 | 0
[6 empty] | FDC Jade | 0 | 0 | FDC Jade | 0 | 0
SYMMETRIX
| Hostname / Zone Alias | Site | Red |  | Blue |  | Storage | Symm # | Red | Blue |  | Device #s | Total | Request | NOTES | QA by
|  |  | Sw/Prt | HBA WWN | Sw/Prt | HBA WWN | required | required | FA | FA | sw/pt | required | Space | Number
Server / Zone RENAMES
Zone & Disk ADDS
ZONE REMOVES
DISK ADDS
DISK REMOVES
Decom | fiap5d(fitetgzap1p) | RDC | [11 empty] | 101122094302 |  | AR
Decom | fiap6d(fitetgzap1u) | RDC | [11 empty] | 101122073707 |  | AR
Decom | rdcgtsmfaad02p | RDC | [11 empty] | 1011250624131 |  | AR
Removal | LDNFI21SDUAN1 | RDC |  | 10000000c96a7408 |  | 10000000c96a4f27 |  | 2819 | 3A:0 | 14B:0 |  | 102,101,100,0FF,0FE,0FD,0FC,0FB,0FA,0F9,0F8,0F7,0F6,0F5,0F4 | 900gb | 101123092306 |  | AR
[9 empty] | 3D:0 | 14C:0 |  | 2DA
[9 empty] | 4C:0 | 13D:0 |  | 530
[9 empty] | 4B:0 | 13A:0 |  | 4CA,4C9,4C8,488,487,486,485,484,483,482
Removal | LDNFI21SDUAN2 | RDC |  | 10000000c96c1d66 |  | 10000000c96c1c46 |  | 2819 | 3A:0 | 14B:0 |  | 102,101,100,0FF,0FE,0FD,0FC,0FB,0FA,0F9,0F8,0F7,0F6,0F5,0F4 |  | 101123095146 |  | AR
[9 empty] | 3D:0 | 14C:0 |  | 2DA
[9 empty] | 4C:0 | 13D:0 |  | 530
[9 empty] | 4B:0 | 13A:0 |  | 4CA,4C9,4C8,488,487,486,485,484,483,482
Decom | fdcicgcdcwd01u/fdcicgcdcwd01c | FDC |  | fdcicgcdcwd01u |  | fdcicgcdcwd01c |  | 0879 | 7F:0 | 10F:1 |  | 0506,0549,054A,054B,054C,054D,054E,0B28,0B29 | 238GB | VR6741217 | fdcicgcdcwd01c_01u | AR
Decom | lndcmbse00301 | RDC |  | 10000000c9678510 |  | 10000000c9636248 |  | 1065 | 3C:0 | 14D:0 |  | 081A,07F5,0803,082F,0821,0828,080A,06EA,07FC,07E0 | 4512 | RFC 13268789 | VT28390577 | AR
[8 empty] | 2819 | 8D:0 | 9C:0 |  | 0BFD,0C05,0C0D,0C15,0C1D,0C25,0C2D,0C35
Decom | lndcmbse00302 | RDC |  | 10000000c96bb786 |  | 10000000c96bb4a0 |  | 1065 | 3C:0 | 14D:0 |  | 081A,07F5,0803,082F,0821,0828,080A,06EA,07FC,07E0
[8 empty] | 2819 | 8D:0 | 9C:0 |  | 0BFD,0C05,0C0D,0C15,0C1D,0C25,0C2D,0C35
Decom | lndcmbse00303 | RDC |  | 10000000c96bc160 |  | 10000000c96bb2c8 |  | 1065 | 3C:0 | 14D:0 |  | 081A,07F5,0803,082F,0821,0828,080A,06EA,07FC,07E0
[8 empty] | 2819 | 8D:0 | 9C:0 |  | 0BFD,0C05,0C0D,0C15,0C1D,0C25,0C2D,0C35
r

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester |  | RFC Description | VR | Scheduled Date | Initials | Comments
RFC 13206348 | HAYNES/PAUL |  | PERFORM DISK REMOVES AS PER VR SYSTEM |  | 11/12 to 12/12 | KR | PIT Change
13301293 | CZARCZYK/K |  | ALM SERVERS EMC TO HDC STORAGE ARRAY MIGRATIO | N/A | 10/12 to 12/12 | HD | EMC 19R/20R to HDS RDCHDS04 migrations
13224214 | MCCAUGHTRY/J |  | CGC ANNUAL COB - RETEST IMACE FIGARO MTN | VR7109603 / VR7109573 / VR7109540 | 11/12 to 12/12 | HD | VR7109603 - SAN SRDF group ficashdb1p_0745_0552. VR7109573 - SAN SRDF group fiimcap1eup_0745_0552. VR7109540 - SAN SRDF split/establish fiimcdb1eup_0745_0552
13310454 | HANLON/RICHARD |  | MULTIFONDS SG PATCH RELEASE-WO#201010320 (San Split/Establish required) | ??? | 11/12 to 12/12 | HD
13307215 | HANLON/RICHARD |  | MULTIFONDS US PATCH RELEASE-WO#201010319 (San Split/Establish required) | ??? | 11/12 to 12/12 | HD
13295464 | NANCARROW/PAUL |  | DECOMMISION DEV SERVERS FIAP5D/FIAP6D |  | 11/12 to 11/12 | HD | Issue raised as I have requested inq ouput for decomm' servers and details of whther we can reclaim storage.
13269334 | DEPTULA/MACIEJ |  | FI EMEA - PT,CDS,INTELLECT FAILBACK TO PROD | VR7034061 | 11/12 to 12/12 | HD | Personality swaps (fioradb1p_2838_2839, fisybdb1p_0745_0552 & fisybdb4p_0745_0552)
13317484 | KHANNA/VINEET |  | VTM PATCH Q05UCU70 -SMI (Split/Establish secrouter_3452_3544_A) | VR7100898/VR7100908 | 11/12 to 13/12 | HD
13317522 | NAPIERAJ/PATRYK |  | EMEA SAN-HDS MIGRATION - EQSA | N/A | 11/12 to 12/12 | HD
13280408 | SANGHADIA/C |  | FULL DECOMMISION OF UKEBUPRSD99/DRSD99 SERVER | N/A | 12/08/10 to 12/13/10 | AR | Info Only
13294859 | SANGHADIA/C |  | FULL DECOMISSION OF SERVER PRSD39/DRSD39 | N/A | 12/08/10 to 12/14/10 | AR | Info Only
13318359 | LYSZKOWSKI/JAN |  | VTM FOR LONDON 2 CORP_CONS COB SERVERS | N/A | 12/10/10 to 12/12/10 | AR | Info Only
13320231 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5R-DSNACVHM | N/A | 12/10/10 to 12/15/10 | AR | PIT Change
13308883 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5-EUG3LAA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13308869 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5-EUG3SAA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13308856 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5-EUCTFA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13308840 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5-EDUXHPA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13308788 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5-EEEQSAM | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13265380 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5U-EUGTSSA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13265343 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5U-EUG3LAA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13265300 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION 19R/20R-WEEK5U-EUCTFA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13265207 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5U-EUGMWSM | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13253658 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION19R/20R-WEEK5U-EUG3SAA | N/A | 12/08/10 to 12/13/10 | AR | PIT Change
13212631 | HAYNES/PAUL |  | REMOVE 6 ARRAYS FROM CGC AND RDC | N/A | 12/11/10 to 12/16/10 | AR | PIT Change
13317142 | REDDY/ASHOK |  | UNUSED SAN REMOVALS AND DECOMMISSIONS | N/A | 2010-12-11 | AR | Added the detyails into DISK REMOVES
13323297 | MCBRIDE/J |  | DCSM SERVER DECOMMISSION | N/A | 2010-12-10 | AR | added the details in below
13316987 | MARCHONG/F |  | EMEA SAN-HDS MIGRATION 19R/20R-WEEK5-EDUXHPA | N/A | 2010-12-11 | AR | PIT Change
13322841 | ARVETI/MANOHARA |  | SSTLOG COB TESTING |  | 2010-12-08 | AR | Issue raised
13323043 | AHMED/SAL |  | EMEA-HDS USP-V M/CODE 60-07-52 - FDC/RDC | N/A | 2010-12-11 | AR | PIT Change
13323268 | BAZAN/WOJCIECH |  | ZEUS DB - SYB INSTANCES RE-BALANCE |  | 2010-12-11 | AR | eqdb1p_0745_0552_ZLN11 eqdb1p_0745_0552_ZLN12 eqdb1p_0745_0552_ZLN16 eqdb1p_0745_0552_EURO
13323277 | AHMED/SAL |  | EMEA - TRACE/SWAP PORT FOR RDC 25R - PORT 138 | N/A | 2010-12-11 | AR | post and pre checks required
13323359 | BAZAN/WOJCIECH |  | EQSMART5-10P: NEW LUNS
DCSM SERVER DECOMMISSION
UK activity
101029084220 | 66 Molesworth Street | rd-dbu01-sf
101029084427 | 66 Molesworth Street | rd-dbu02-sf
101029084813 | 66 Molesworth Street | rd-dbu03-sf
101029085114 | 66 Molesworth Street | rd-dbu04-sf
101102101551 | 66 Molesworth Street | TCEDLWEB2P
101112084009 | 66 Molesworth Street | LDNCCMWAAMU1
101112084247 | 66 Molesworth Street | LDNCCMWAAMU2
101119100712 | 66 Molesworth Street | UKGTSDRSD07
101119101408 | 66 Molesworth Street | UKGTSUASD07
101119101611 | 66 Molesworth Street | UKGTSPRSD08
101119102335 | 66 Molesworth Street | UKGTSDRSD08
101119102608 | 66 Molesworth Street | UKGTSUASD08
1011191030051 | 66 Molesworth Street | UKGTSDRSD21
1011191031481 | 66 Molesworth Street | UKGTSUASD21
101119105025 | 66 Molesworth Street | UKGTSDRSD22
101119105209 | 66 Molesworth Street | UKGTSUASD22
101122013106 | 66 Molesworth Street | UKCTISD29DV
101129055828 | 66 Molesworth Street | tifarmcd11lnp
101130053654 | 66 Molesworth Street | UKGTSUASD16
101130054332 | 66 Molesworth Street | UKGTSUASA16
101130054607 | 66 Molesworth Street | UKGTSUASA17
101130054843 | 66 Molesworth Street | UKGTSUASD28
101130070726 | 66 Molesworth Street | fitetgzap1p
101130083344 | 66 Molesworth Street | fiap6d
101130092909 | 66 Molesworth Street | UKCIBDRSA01
101202063236 | 66 Molesworth Street | UKCTEDRSD02
101202064904 | 66 Molesworth Street | UKINFDRSD03
101202071631 | 66 Molesworth Street | UKEBUPRSD39
101202072449 | 66 Molesworth Street | UKEBUUASD39
101202072835 | 66 Molesworth Street | UKEBUPRSD99
101202100006 | 66 Molesworth Street | FIBPAGW2P
101203142205 | 66 Molesworth Street | RD-P2PSH01-MDH
101203142439 | 66 Molesworth Street | RD-P2PSH02-MDH
101203142648 | 66 Molesworth Street | RD-IDBFH1-TIB
101204170956 | 66 Molesworth Street | EUWBICWEBS002
101204171714 | 66 Molesworth Street | EUWBICWEBS003
100616091336 | 33 CANADA SQUARE | euwebsenseevalproxy
101029082856 | 33 CANADA SQUARE | cw-dbu01-sf
101029083541 | 33 CANADA SQUARE | CW-DBU02-SF
101029083803 | 33 CANADA SQUARE | cw-dbu03-sf
101029083958 | 33 CANADA SQUARE | cw-dbu04-sf
101102101142 | 25 CANADA SQUARE | TCEDLWEB1P
101119100449 | 25 CANADA SQUARE | UKGTSPRSD07
101119102813 | 25 CANADA SQUARE | UKGTSPRSD21
101119103341 | 25 CANADA SQUARE | UKGTSPRSD22
101120084528 | 25 CANADA SQUARE | LDNCMBSTIF002
101123050308 | 33 CANADA SQUARE | OLIEXWEB2
101202060503 | 25 CANADA SQUARE | LDNTFIST500
101202064700 | 25 CANADA SQUARE | UKCTEPRSD02
101202065208 | 25 CANADA SQUARE | UKINFPRSD03
101202072100 | 25 CANADA SQUARE | UKEBUDRSD39
101202073111 | 25 CANADA SQUARE | UKEBUDRSD99
101203113759 | 25 CANADA SQUARE | CW-P2PSH01-MDH
101203141716 | 25 CANADA SQUARE | CW-P2PSH02-MDH
101204172200 | 25 CANADA SQUARE | EUWPIPWEBS003
101204172200 | 25 CANADA SQUARE | EUWPIPWEBS003
101204172200 | 25 CANADA SQUARE | EUWPIPWEBS003
100913133327 | 66 Molesworth Street | GFIGEXLN0007
100918144201 | 66 Molesworth Street | INFRAORAUA1
101011023511 | 66 Molesworth Street | SYMM15R
101011023732 | 66 Molesworth Street | SYMM13R
101012052554 | 66 Molesworth Street | SYMM13R-MODEM
1011021022411 | 66 Molesworth Street | TCEDLWEB3P
101115061112 | 66 MOLESWORTH STREET | rdcgtsgtusa01c
101117053754 | 66 Molesworth Street | UKCTIDRSA52
101117054915 | 66 Molesworth Street | UKCTIDRSA53
101118102533 | 66 Molesworth Street | EULON708-HX
101122050044 | 66 Molesworth Street | LDNTFISA003
101122094503 | 66 Molesworth Street | LONDBSTE2-GW
101122094808 | 66 Molesworth Street | londbste2-gw2
101124102346 | 66 Molesworth Street | UKTSYDRSD07
1009080611481 | 33 CANADA SQUARE | EUFWCGCP01
101119064951 | 33 CANADA SQUARE | uksecuasd25
101122081409 | 33 CANADA SQUARE | UKEQSW01
101125102253 | 25 CANADA SQUARE | FIBPAGW3P
101129051730 | 33 CANADA SQUARE | UKEQSW01
German activities
101013122644 | decom | Westerbachstr. | FRACTIST003DR
101125112124 | decom | Reuterweg | FFTEBUSA006
101207053640 | decom | Heinrich-Lanz-Allee | FDCCTISPCWA01U
101207050823 | decom | Heinrich-Lanz-Allee | FDCCTIEUCWW01U