## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR | Scheduled Date | Initials | Comments
13234203 | HAYNES/PAUL | UPGRADE OF MCDATA FIRMWARE RED AND GREEN | N/A | 27/11 to 28/11 | TW | TW covers DE
13255630 | LYSZKOWSKI/JAN | VTM FOR LONDON 2 CORP_CONS PROD SERVERS | N/A | 26/11 to 28/11 | HD | Info Only
13255645 | LYSZKOWSKI/JAN | VTM FOR LONDON 1 CORP_CONS PROD SERVERS | N/A | 26/11 to 28/11 | HD | Info Only
13269695 | CZAJKOWSKI/R | SAN SPLIT / ESTABLISH FDCTSY01SDDR LDNTSY01SDPR | VR7034702 | 27/11 to 02/12 | HD | Approved by SAN - split/Establish required | ldntsy01sdpr_3720_3810_A17
13263936 | ADAMS/ANGELA | ISG DATASERVICES 2 x COB TEST (one of them is STAR COB Test) gcot_3471_s5 & gcdsgsyb2p_3720_3810_a33 | VR7049552 / VR7049823 / VR7050689 / VR7050701 | 27/11 to 27/11 | HD | Approved by SAN (failover/failback & switchover/switchback bring back COB data)
13224214 | MCCAUGHTRY/J | CGC ANNUAL COB - RETEST IMACE FIGARO MTN | VR7042761 / VR7042792 / VR7042321 | 27/11 to 28/11 | HD | Approved by SAN - FAILOVER/FAILBACK & split/Establish is required | fiimcdb1eup_0745_0552 ; fiimcap1eup_0745_0552;ficashdb1p_0745_0552
13269789 | MCBRIDE/J | DCSM SERVER DECOMMISSION | N/A | 26/11 to 29/11 | HD | Approved by SAN (Andy Johnstone email approved)
13269534 | SUMMERS/JOHN | IOWA: EXTRA SAN NEEDED FOR IOWA APPLICATION (STAR allocation) | N/A | 26/11 to 28/11 | HD | STAR/SRDF Group GCOT_3471_S1. Approved by SAN;VR6996962
13264548 | POOLE/MARK | HDS FAILBACK TRAMP/COMPASS APPLICATION TO PROD | VR7028380 | 27/11 to 28/11 | HD | Approved by SAN - FAILBACK required | trampcompass_78378_78398_1A

## General SAN Work
General SAN Workplan for Saturday
[6 empty] | Zones | Added | Removed | Members | Added | Removed
[6 empty] | CGC Red | 0 | 0 | CGC Red | 0 | 0
[6 empty] | CGC Blue | 0 | 0 | CGC Blue | 0 | 0
[6 empty] | RDC Red | 0 | 0 | RDC Red | 0 | 0
[6 empty] | RDC Blue | 0 | 0 | RDC Blue | 0 | 0
[6 empty] | RDC Ruby | 0 | 0 | RDC Ruby | 0 | 0
[6 empty] | RDC Jade | 0 | 0 | RDC Jade | 0 | 0
[6 empty] | FDC Ruby | 0 | 0 | FDC Ruby | 0 | 0
[6 empty] | FDC Jade | 0 | 0 | FDC Jade | 0 | 0
SYMMETRIX
| Hostname / Zone Alias | Site | Red |  | Blue |  | Storage | Symm # | Red | Blue |  | Device #s | Total | Request | NOTES | QA by
|  |  | Sw/Prt | HBA WWN | Sw/Prt | HBA WWN | required | required | FA | FA | sw/pt | required | Space | Number
Server / Zone RENAMES
Zone & Disk ADDS
ZONE REMOVES
DISK ADDS
DISK REMOVES
Symm Configure
r

## Extra Work-old
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR | Scheduled Date | Initials | Comments
13206308 | HAYNES/PAUL | PERFORM DISK REMOVES AS PER VR SYSTEM | N/A | 27/11 to 28/11 | KR | PIT (Paul Haynes) - CHNGCONT - Cancelled
13234203 | HAYNES/PAUL | UPGRADE OF MCDATA FIRMWARE RED AND GREEN | N/A | 27/11 to 28/11 | TW | TW covers DE
13227785 | HAYNES/PAUL | SAN CLEANUP - REMOVE OLD NODES IN DE | N/A | 27/11 to 27/11 | HD | PIT (Paul Haynes)
13255630 | LYSZKOWSKI/JAN | VTM FOR LONDON 2 CORP_CONS PROD SERVERS | N/A | 26/11 to 28/11 | HD | Info Only
13255645 | LYSZKOWSKI/JAN | VTM FOR LONDON 1 CORP_CONS PROD SERVERS | N/A | 26/11 to 28/11 | HD | Info Only
13265207 | MARCHONG/F | EMEA SAN-HDS MIGRATION 19R/20R-WEEK3-EUGMWSM | N/A | 26/11/ to 30/11 | HD | PIT (Sal')
13265300 | MARCHONG/F | EMEA SAN-HDS MIGRATION 19R/20R-WEEK3-EUCTFA | N/A | 26/11/ to 30/11 | HD | PIT (Sal')
13265343 | MARCHONG/F | EMEA SAN-HDS MIGRATION 19R/20R-WEEK3-EUG3LAA | N/A | 26/11/ to 30/11 | HD | PIT (Sal')
13265380 | MARCHONG/F | EMEA SAN-HDS MIGRATION 19R/20R-WEEK3-EUGTSSA | N/A | 26/11/ to 30/11 | HD | PIT (Sal')
13268789 | REDDY/ASHOK | UNUSED SAN REMOVALS AND DECOMMISSIONS | N/A | 27/11 to 28/11 | HD | Not Approved by CC
13269527 | AHMED/SAL | EMEA-HDS USP-V M/CODE 60-07-52 UPDATE | N/A | 27/11 to 28/11 | HD | Info Only
13269695 | CZAJKOWSKI/R | SAN SPLIT / ESTABLISH FDCTSY01SDDR LDNTSY01SDPR | VR7034702 | 27/11 to 02/12 | HD | Approved by SAN
13263936 | ADAMS/ANGELA | ISG DATASERVICES 2 x COB TEST (one of them is STAR COB Test) gcot_3471_s5 & gcdsgsyb2p_3720_3810_a33 | VR7049552 / VR7049823 / VR7050689 / VR7050701 | 27/11 to 27/11 | HD | Approved by SAN (failover/failback & switchover/switchback bring back COB data)
13256331 | LUDWICZAK/M | REMOVE DISK FROM DIMENSIONS UAT AND PROD | N/A | 27/11 to 27/11 | HD | Issue, lack of resources to accomodate these remove of disks for all hosts. Change Control Issue
13224214 | MCCAUGHTRY/J | CGC ANNUAL COB - RETEST IMACE FIGARO MTN | VR7042761 / VR7042792 / VR7042321 | 27/11 to 28/11 | HD | Approved by SAN
13224066 | SHAVEZ/CRAIG | SAN STACK UPGRADE ON LDNCTISDESM001 / FFTCTISDESM001 (need to add SPC-2 Flags to HBA's for these two servers ) | N/A | 27/11 to 27/11 | HD | Approved by SAN (LDNCTISDESM001 = HDS / FFTCTISDESM001 = EMC). CHNGCONT Issue
13269789 | MCBRIDE/J | DCSM SERVER DECOMMISSION | N/A | 26/11 to 29/11 | HD | Approved by SAN (Andy Johnstone email approved)
13269534 | SUMMERS/JOHN | IOWA: EXTRA SAN NEEDED FOR IOWA APPLICATION (STAR allocation) | N/A | 26/11 to 28/11 | HD | STAR/SRDF Group GCOT_3471_S1. Approved by SAN
13269334 | DEPTULA/MACIEJ | FI EMEA - PT,CDS,INTELLECT FAILBACK TO PROD | VR7034061 | 27/11 to 27/11 | HD | Approved by SAN. CHANGCONT Issue
13264548 | POOLE/MARK | HDS FAILBACK TRAMP/COMPASS APPLICATION TO PROD | VR7028380 | 27/11 to 28/11 | HD | Approved by SAN - FAILBACK required | trampcompass_78378_78398_1A