## Current Projects
Team | Global Storage Analytic
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | HDS RIAT POC | Al Mahmood | Q2 2015 | In Progress | CIVA issues resolved moving forward with RIAT install. Project "out of scope" review in progress. HDS needs to commit to at least 80% of Citi requirements in RIAT POC otherwise POC will not go forward (HDS initially marked most as "out of scope" in project plan review). |  |  | N/A
NAM | Virtual Instruments (VI) POC | Al Mahmood | Q2 2015 | In Progress | VI, HDS working with procurement and Fincon to get legal paperwork in place for loaner/permanent equipment for POC |  |  | N/A
NAM | OCI Perform & Plan POC | Al Mahmood | N/A | Cancelled | NetApp application cancelled |  |  | N/A
ALL | SRM Discovery | John Bachant | Q3 2015 | In Progress | Assist SRM team with discoveries. See SRM Discovery tab for regional stats from SRM team |  |  | N/A
ALL | Cisco Slow Drain in SRM | CATE | Q3 2015 | In Progress | Working with CATE, Cisco, EMC and SRM team to get Cisco stats into SRM for analysis |  |  | N/A

## Closed Projects
Team | Global Storage Analytic
Manager | Al Mahmood
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | OCI Perform & Plan POC | Al Mahmood | N/A | Cancelled | NetApp application cancelled

## HDS RIAT
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | HDS RIAT
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Phase1: Prep 390G Build Out | Team | Q4 2014 | In Progress |  |  |  | N/A
NAM | Order new VM in 390G for RIAT probe | Kery Hines Ashok Kumar Reddy | 2014-11-07 | Completed | TCRS CAP0039085 completed. Need to have VM team install OVA package. | 2014-11-29 | OVA install completed | N/A
NAM | Obtain new VM IP for FW rules | Kery Hines | 2014-11-20 | Completed | TCRS CAP0039085 completed new IP provided |  |  | N/A
NAM | Submit firewall rules | Kery Hines | 2014-12-05 | Completed | CMP WS27236293 submitted 11/20 | 2015-01-07 |  | N/A
NAM | Request FID to be used by RIAT software | Kery Hines | 2014-11-21 | Completed | CMP WS27269015 submitted in 11/21 for FID RIATadmin | 2014-11-25 |  | N/A
NAM | Setup FID access. CMP for AD group SAN_View; add RIATadmin to 390G EMC arrays via symauth (monitor role) | Kery Hines | 2014-12-10 | Completed | CMP WS27346967 submitted 11/25 | 2014-12-02 |  | N/A
NAM | CATE to test new RIAT software | CATE | 2014-12-12 | Completed | New RIAT version delivered to CATE on Nov 10th, CATE is currently testing. CIVA discovered 1 mediun + 11 informational issues. CATE seeking OK to deploy this version from Security team. | 2015-01-21 |  | N/A
NAM | CATE OK's RIAT usage in prod | Kery Hines Ashok Kumar Reddy | 2014-12-19 | Completed | Need initial CATE blessing to begin config/usage in prod | 2015-01-28 |  | N/A
NAM | Phase2: Configuration Verification | Team | Q1 2015 | Pending |  |  |  | N/A
NAM | Configure RIAT on 390G server NAMERIAT01 | Kery Hines Ashok Kumar Reddy | Q1 2015 | Pending |  |  |  | N/A
NAM | Install/configure supporting software EMC Solutions Enabler and IBM XCLI | Kery Hines Ashok Kumar Reddy | Q1 2015 | Pending |  |  |  | N/A
NAM | Determine initial arrays to discover and schedule/perform discovery | Kery Hines Ashok Kumar Reddy | TBD | Waiting | This will test FW rules and access to EMC, IBM & HDS arrays. |  |  | N/A
NAM | Discover all arrays in scope. Validate end-to-end RIAT process | Kery Hines Ashok Kumar Reddy | TBD | Waiting |  |  |  | N/A
NAM | Phase3: Evaluation | Team | Q1 2015 | Waiting |  |  |  | N/A
NAM | RIAT evaluation test plan | Team | Q1 2015 | Waiting |  |  |  | N/A
NAM | RIAT results and recommendations | Team | Q1 2015 | Waiting |  |  |  | N/A
Issues Log
1)

## Vitrual Instruments
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | Virtual Instruments
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Phase1: Prep 390G Build Out | Team | Q4 2014 | In Progress |  |  |  | N/A
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | Q4 2014 | Completed | VI team has supplied the installation planning guide for VI appliance. VI team completed 390G site survey the week of Dec 1st. |  |  | N/A
NAM | Install/configure VI appliance in 390G | Kery Hines | Q1 2015 | In Progress | Working with Citi procurement team (Rosemary Badilla Rodriguez) and Fincon (Jen White) to get loaner/permanent (taps) equipment contracts in place. |  |  | N/A
NAM | Collect POC requirements 390G for VI Taps | Al Mahmood Kery Hines | Q1 2015 | In Progress | Storage array EMC VMAX 40K 195702096 selected for analysis and install of taps in phase 2 of the project. FA and Cisco switch info provided to VI for planning |  |  | N/A
NAM | Phase2: Install taps | Team | Q1 2015 | Waiting |  |  |  | N/A
NAM | Install taps into San path | Al Mahmood Kery Hines | Q1 2015 | Waiting | Install taps into A-side storage array EMC VMAX 40K 195702096 SAN paths. Wait one week then install taps into B-Side paths. |  |  | N/A
NAM | Phase3: Evaluation | Team | Q2 2015 | TBD |  |  |  | N/A
NAM | VI evaluation test plan | Team | Q2 2015 | TBD |  |  |  | N/A
NAM | VI results and recommendations | Team | Q2 2015 | TBD |  |  |  | N/A
Issues Log
1)

## OCI Perform & Plan
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | NetApp OCI Perform & Plan
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Phase1: Prep 390G Build Out | Team | Q1 2015 | In Progress |  |  |  | N/A
NAM | Collecting POC requirements 390G for Software | Al Mahmood Kery Hines | Q4 2014 | Completed | NetApp has provided the server spec of the 2 VM's they require |  |  | N/A
NAM | Order new VM(s) in 390G for OCI | Kery Hines | Q1 2015 | Completed | TCRS CAP0039085 approved and in progress |  |  | N/A
NAM | CATE to review and (or) test OCI software in the CATE lab | CATE | TBD | Cancelled | CATE evaluated the product in 2011. Not sure if they will re-examine for this POC |  |  | N/A
NAM | Setup any FID's/access (read) needed by OCI software (if any) | Kery Hines | Q1 2015 | Cancelled | Use existing OCI FID's |  |  | N/A
NAM | Phase2: Configuration Verification | Team | Q1 2015 | Cancelled |  |  |  | N/A
NAM | Deploy/configure OCI software | Kery Hines | Q1 2015 | Cancelled | Pending VM build out (in progress) |  |  | N/A
NAM | Phase3: Evaluation | Team | Q2 2015 | Cancelled |  |  |  | N/A
NAM | OCI evaluation test plan | Team | Q2 2015 | Cancelled |  |  |  | N/A
NAM | OCI results and recommendations | Team | Q2 2015 | Cancelled |  |  |  | N/A
NAM | Phase4: Teardown | Team | Q2 2015 | In Progress |  |  |  | N/A
NAM | Reture VM's back to pool | Kery Hines | Q1 2015 | In Progress | Return VM's aquired under TCRS CAP0039085 |  |  | N/A
Issues Log
1)

## SRM Discovery
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | SRM Discovery
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
NAM | Assist SRM team with hardware discovery | Team | Q3 2015 | In Progress | As of Jan 15th 2015 NAS: 660 Total 206 Discovered 31% complete SAN: 275 Total 156 Discovered 56% complete SAN Switches: 182 Total 168 Discovered 92% completed |  |  | N/A
EMEA | Assist SRM team with hardware discovery | Team | Q3 2015 | In Progress | As of Jan 15th 2015 NAS: 134 Total 2 Discovered 1% complete SAN: 58 Total 17 Discovered 29% complete SAN Switches: 108 Total 30 Discovered 27% completed |  |  | N/A
APAC | Assist SRM team with hardware discovery | Team | Q3 2015 | In Progress | As of Jan 15th 2015 NAS: no info yet SAN: no info yet SAN Switches: no info yet |  |  | N/A
LATAM | Assist SRM team with hardware discovery | Team | Q3 2015 | In Progress | As of Jan 15th 2015 NAS: no info yet SAN: no info yet SAN Switches: 16 Total 2 Discovered 12% completed |  |  | N/A
Issues Log
1)

## Cisco Slow Drain
Team | Global Storage Analytic
Manager | Al Mahmood
Project: | Cisco slow drain stats
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Run/Build
All | Working with CATE, Cisco, EMC and SRM team to get Cisco stats into SRM for analysis | Team | Q3 2015 | In Progress | • Interop testing between MDS and SRM slated to begin early March. • Testing to complete early May timeframe, but Cisco is working with eCATS team to vet out the full testing schedule. • Reviewed high level test plan and topology. • Citi would like to review all of the test cases which will be outlined in a JTPOR. • Once the eCATs testing officially kicks off, there will be a meeting to review the JTPOR. • Citi would like to see a project plan outlining timeline and when they will be able to see various elements and output of the testing, along with final tool delivery dates. • Cisco to provide a more detailed timeline for the testing milestones by end of February prior to beginning testing. • EMC can incorporate testing timeline into the overall project plan. • A weekly call will be established to provide updates. |  |  | N/A
Issues Log
1)