## Summary
CATE Items for Run Storage
| Description | Run Contact | CATE Contact | Date | Comments
| 2nd NAS vendor outside of EMC VNX for dual vendor strategy | Shibu Thayil
| No real tools to perform custom alerting. We will need to depend on custom and reactive type of alerting to avoid running into outages especially for environments where we are over-committing heavily and performance oriented workloads. Unfortunately builtin SNMP alerts for storage systems are very limited; extremely limited for especially newer technologies such as XtremIO, etc. This is not in scope for SRM. | Shibu Thayil
| Any effort for another vendor for VDI space outside of EMC XtremIO | Shibu Thayil
| Can we look into a product which can assist us with performing COB/DR tests quicker? Today we rely on in house scripts and manual commands to execute major COB tests which take up many hours and resources. If there is a tool out that that can help us do this task better for all storage products, it will certainly be beneficial. | Shibu Thayil
| NetApp Grid NAS Migration Solution | Syam
| Solution for NAS Migration of NetApp Compliance devices to EMC VNX | Syam
| HPNA Rules for XIO, initial implementation | Bryan DeLuca | Jeff Hernandez
| HPNA Rules for VNX, initial implementation | Bryan DeLuca
| HPNA Rules for NetApp? Initial implementation | Bryan DeLuca
| HPNA Rules update - Cisco Roles in the live environment. Will there be changes to the rule set to match legacy deployments? | Bryan DeLuca | Ludwig Derodel
| G1000 - ISRP Items. CAP#623223 | Shibu Thayil | Gary Johnson |  | Milestone dates have been retargetted.
| VMAX3-ISRP Items. CAP#623225 | Shibu Thayil | Quang Le |  | Milestone dates have been retargetted.
| EMC VNX SEMS Reporting, initial implementation | Bryan DeLuca | Gary Johnson
| NetApp EERS/CISAR feed script, CAP#612773 | Bryan DeLuca | Richard Sopp |  | Milestone dates have been retargetted.
| EMC VNX/NAS EERS/CISAR feed script, CAP#612773 | Bryan DeLuca | Richard Sopp |  | Milestone dates have been retargetted.
| EMC VMAX EERS/CISAR feed script, CAP#612773 | Bryan DeLuca | Ludwig Derodel |  | Milestone dates have been retargetted.
| HDS EERS/CISAR feed script, CAP#612773 | Bryan DeLuca | Ludwig Derodel |  | Milestone dates have been retargetted.
| IBM XIV EERS/CISAR feed script, CAP#612773 | Bryan DeLuca | Ludwig Derodel |  | Milestone dates have been retargetted.
| EMEA NAS Branch locations require a solution for legacy NetApp filer restore post migration to VNX | Scott
| Citrix / CAP NAS bill of matrials | Scott
| SnapLock equivalent for EMC FLR | Scott
| Multi- Protool solution on EMC VNX to support ICG / Ram Raddy. | Scott
| NAS Migration improvements for EMCopy. Removing privlege requirement and EMCopy is not currently a separate product in CTC. | Bryan DeLuca | Ludwig Derodel

## CAP#612773 CISAR
CAP#612773 Storage CISAR Feed
M. ID | Milestone Description | Milestone Owner | Milestone Original Target Date
563619 | CATE begins development of NetApp FID feed tool | Sopp, Richard (RS01146) | 15 Jan, 2015
563620 | CATE releases NetApp FID feed tool | Sopp, Richard (RS01146) | 29 May, 2015
563621 | CATE releases EMC NAS FID feed tool | Sopp, Richard (RS01146) | 29 May, 2015
563622 | CATE releases Cisco MDS FID feed tool | Derodel, Ludwig (LD59486) | 18 May, 2015
563623 | CATE releases VMAX FID feed tool | Derodel, Ludwig (LD59486) | 18 May, 2015
563626 | CATE releases HDS FID feed tool | Derodel, Ludwig (LD59486) | 01 Jun, 2015
563629 | CATE releases XIV FID feed tool | Derodel, Ludwig (LD59486) | 01 Jun, 2015
563632 | Operations completes any implementation required for the SAN tools. | Pereira, Leonid (LP12219) | 13 Jul, 2015
563635 | Operations completes any implementation required for the NAS tools. | Pereira, Leonid (LP12219) | 13 Jul, 2015
563636 | CISAR fields are populated by the L3 Operational team for SAN devices | Pereira, Leonid (LP12219) | 21 Aug, 2015
563637 | CISAR fields are populated by the L3 Operational team for NAS devices | Pereira, Leonid (LP12219) | 28 Aug, 2015
563638 | Turnover evidence to Risk Management | DeLuca, Bryan (BD70270) | 04 Sep, 2015
History of CAP Milestone Changes
Date | Description of change
2015-07-07 | 563621 retarget 08/15/2015

## CAP#623223 G1000
CAP#623223 G1000 Early Deployment
M. ID | Milestone Description | Milestone Owner | Milestone Original Target Date
572254 | Complete the CIVA test SOW #81357 | Johnson, Gary (GJ06529) | 2015-05-29
572255 | Complete and close ISRP Questionnaire | Johnson, Gary (GJ06529) | 2015-05-29
572256 | Obtain Approval for the solution from stake holders: CATE (Global Engineering Lead for the domain) and Operations (Citi Storage) | Johnson, Gary (GJ06529) | 2015-06-19
572257 | Register Non-Compliant Items (NCI's) of the solution according to Issue Lifecycle Management (creating a Risk Exception) | Johnson, Gary (GJ06529) | 2015-06-26
572258 | Complete ISRP process | Johnson, Gary (GJ06529) | 2015-07-15
572259 | Update HDS G1000 configuration standard if needed (RFP announcement) | Johnson, Gary (GJ06529) | 2015-07-20
572260 | Update pilot environment following RFP announcement | Thayil, Shibu (ST60913) | 25 Aug, 2015
572261 | Submit evidence for validation | DeLuca, Bryan (BD70270) | 15 Sep, 2015
History of CAP Milestone Changes
Date | Description of change
2015-05-22 | 572254 & 572255 retarget 06/24/2015 572256 retarget 06/26/2015 Justification: Delays in CIVA testing
2015-07-07 | 572254, 572256, 572257 retarget 07/31/2015 Justification: Delays in CIVA retest. 572255 retarget 07/15/2015 Justification: Pending TISO/GISO approval.

## CAP#623225 VMAX3
CAP#623225 VMAX3 Early Deployment
M. ID | Milestone Description | Milestone Owner | Milestone Original Target Date
572262 | Complete the CIVA test SOW #8174 | Le, Quang (QL68074) | 2015-05-29
572263 | Obtain Approval for the solution from stake holders: CATE (Global Engineering Lead for the domain) and Operations (Citi Storage) | Le, Quang (QL68074) | 2015-06-26
572264 | Complete integration with Citi ePO central console for AntiVirus protection. | Le, Quang (QL68074) | 2015-06-26
572265 | Register Non-Compliant Items (NCI's) within the solution according to Issue Lifecycle Management | Le, Quang (QL68074) | 2015-07-15
572266 | Complete ISRP process | Le, Quang (QL68074) | 2015-07-25
572267 | Release RFP (Release for Production) announcement. | Le, Quang (QL68074) | 15 Aug, 2015
572268 | Update pilot environment following RFP announcement | Thayil, Shibu (ST60913) | 15 Sep, 2015
572269 | Submit Evidence to Risk Management for validation | DeLuca, Bryan (BD70270) | 30 Sep, 2015
History of CAP Milestone Changes