## Current Projects
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | ViPR automated provisioning POC | Shibu Thayil | TBD | In Progress | Performed end to end provisioning using ViPR for a live server 390G. Also provided feedback to EMC to improve the provisioning process to adhere to Citi standards.
NAM | New Hitachi VSP G1000 array installation (BAU) | Shibu Thayil | Q1, 2015 | In Progress | 5 HDS G1000's were purchased and are pending install. 2 - SWDC, 2 - MWDC, 1 - GTDC. CATE needs to certify arrays & HCS 8.0; ETA Q4 2014. Q1 2015 for the deployment of these arrays once certification is completed.
NAM | Hitachi HUS-VM All Flash array POC | Shibu Thayil | TBD | Waiting | Pending CATE certification. Target datacenter is currently MWDC.
NAM | EMC VMAX-3 array installation (Tech Refresh) | Shibu Thayil | Q2, 2015 | Waiting | 8 (?) EMC VMAX3's were purchased and are pending install. CATE needs to certify arrays & Solutions Enabler 8.x; ETA Q1 2015 for Certification. Q2 2015 for rollouts.
NAM | EMC Scale I/O POC | Shibu Thayil | TBD | Waiting | CATE testing in lab at present; ETA Q1 2015 for Certification
NAM | SAN Storage for Actifio production Pilot | Shibu Thayil | TBD | Waiting | Install of Actifio servers in production pilot in SWDC and MWDC; 20-25TB Bronze Tier storge required Actifio controller with 2 servers install planned in each DC
EMEA | XtremIO VDI install | Shibu Thayil | TBD | In Progress | NAM rolled out completely. Currently rollouts are taking place in EMEA & APAC.
EMEA | Switzerland TSM replacement | Shibu Thayil | 2015-03-31 | In Progress | Waiting for Symantect to rack and configure
EMEA | Frankfurt legacy TSM replacement | Shibu Thayil | 2015-03-31 | In Progress | Waiting for hardware build and software delivery
EMEA | SRM Rollout for EMEA (RDC) | Shibu Thayil | 2014-12-15 | In Progress | Need to complete rollout for RDC by mid Dec 2014. Remaining D/C can be completed with a target date of end of March 2015.
LATAM | ESX Ctrix MTY -> QRDC Migration |  |  | In Progress | PO Submitted. Equipment delivery pending. ETA week of 1/12
NAM | VSI General Purpose VSI Phase II | Shibu Thayil | 2015-02-16 | In Progress | Equip delivered 12/19. Storage install pending RUTH
NAM | MSSB ESX Cluster re-purpose to GP VSI | Shibu Thayil | 2015-02-27 | In Progress | Equip delivery (ETA) end of Dec., pending install SWDC
NAM | VSI General Purpose On-Site Net New | Shibu Thayil | 2015-02-27 | In Progress | Equip delivery (ETA) first week of Jan, pending install GTDC and SWDC
NAM | VSI General Purpose VSI Net New | Shibu Thayil | 2015-02-27 | In Progress | Equip delivery (ETA) end of Dec., pending install RUTH/390G/GTDC/SWDC/MWDC
NAM | EMC FLR worm compliance | Shibu Thayil | Q2, 2015 | In Progress | Application UAT is on-going. Stale configuration identified and started decomm activities. Issue--no FLR storage space available currently to allow migration ready in February--ETA Q3 2015 | Q3, 2015 | pending FLR storage allocation
NAM/EMEA | Changing Default Passwords, creating read only user for vendor acesss (NAM) Review NAM and EMEA XtremIO Setup and make changes | Shibu Thayil | Q1, 2015 | In Progress | 1. ETA for changing default password 28-Feb-2015 2. updated email configuration on all NAM XtremIO brick. Receiving email notification 3. install certificates and AD groups from EUR domain for EMEA access

## Closed Projects
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Region | Project | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | 21 XtremIO(VDI 2.0) Storage Rollout | Shibu Thayil | 2015-02-28 | Closed | Worked with CATE, Build team, EMC Resources, Citi Network Team(s), Virtualization Operations team, ESX Build team to complete the project 2.5 months ahead of originally advertised completion dates | 2014-10-31 | Due to Tony Disanto request, we had to pull in the dates to meet the urgent escalations.
NAM | SDDC GTDC Pilot | Shibu Thayil | 2014-10-31 | Closed | Worked with CATE storage, Virtualization Ops team, ESX build team to finalize the requirements for the SDDC GTDC pilot project. Then documented and worked with Storage build team to install, provision, QA and release the storage Virtualization Operations team | 2014-10-03 | Worked aggressively to deliver the storage quicker.

## ViPR POC
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | EMC ViPR POC
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | CATE certification of ViPR | CATE | TBD | In Progress | CATE has been testing in the lab for over a year now
NAM | Order 3 new VM's in 390G for ViPR |  | 2014-08-01 | Completed | Completed
NAM | Install ViPR software | VM Team | 2014-08-01 | Completed | ViPR was delivered as a VM package. VM team installed with VM builds.
NAM | Request "vipradmin" FID needed to access SAN software | Kery Hines | 2014-09-03 | Completed | CMP WS25393977 placed on Sept 3rd. Completed
NAM | Add "vipradmin" to privileged AD SAN group SAN_Support | Kery Hines | 2014-09-04 | Completed | CMP WS25419058 placed on Sept 4th. Completed
NAM | Create VSAN for ViPR POC in 390G SAN11 A & B Fabrics | Raja Balasubramanian | 2014-09-15 | Completed | VSANs created for ViPR POC. CHG0000367572,CHG0000379975
NAM | Review ViPR default configuration | Kery Hines Raja Balasubramanian | 2014-10-01 | Completed | Set all default "scans" to once a day for POC. Asked CATE for enhancement to authentication provider search criteria to support AD lookup using search by “sAMAccountName”
NAM | Review ViPR support and SAN code levels with EMC prior to first discovery | Kery Hines Raja Balasubramanian | 2014-10-06 | Completed | Sanity check with the vendor to insure all SAN hardware to be discovered is supported by current ViPR software REVs
NAM | Discover 390G Hitachi SAN storage arrays (USPV, VSP & HUSVM) | Kery Hines Raja Balasubramanian | 2014-10-10 | Completed | Setup ViPR discovery engine to query 390G Hitachi Command Suite (HCS) database. Completed RFC CHG0000414582
NAM | Discover 390G Cisco SAN 11 fabric | Kery Hines Raja Balasubramanian | 2014-10-11 | Completed | Setup ViPR discovery engine to query 390G Hitachi Command Suite (HCS) database. Completed RFC CHG0000414582
NAM | Review/build ViPR virtual arrays, pools, resources | Kery Hines Raja Balasubramanian | TBD | In Progress | Initial virtual work completed. Ran into several issues regarding port groupings (not supported), multiple users in different tenant groups (not supported)
NAM | Upgrade ViPR to 2.1.x (or 2.2) | Kery Hines Raja Balasubramanian | TBD | To be scheduled | Requested enhancements, bug fixes
NAM | Discover new host and provision HDS storage | Kery Hines Raja Balasubramanian Vivek Jain | 2014-11-07 | Completed | Creating Volumes and Exporting to host (Zoning and masking) completed; CHG0000444242
NAM | Discover EMC Symmetrix Arrays | Kery Hines Raja Balasubramanian | TBD | Pending | TBD
NAM | Discover EMC VNX/Clariion Arrays | Kery Hines Raja Balasubramanian | TBD | Pending | TBD
NAM | Discover EMC Extreme I/O Arrays | Kery Hines Raja Balasubramanian | TBD | Pending | TBD
NAM | Discover IBM XiV arrays | Kery Hines Raja Balasubramanian | TBD | Pending | TBD

## HDS G1000
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | HDS G1000
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | CATE certification | CATE | TBD | In Progress | CATE certifying G1000 and HCS 8.0
NAM | Install G1000's and create install PCM | Kery Hines Raja Balasubramanian | TBD | Waiting | Arrays at datacenters pending install
NAM | Upgrade HCS from 7.4 to 8.0 | Kery Hines Raja Balasubramanian | TBD | Waiting | Pending CATE; determine scope (upgrade all HCS servers or just a few and turnover remainder to SAN teams)
NAM | Turnover arrays and PCM's to various teams | Kery Hines Raja Balasubramanian | TBD | Waiting | TBD

## Flash HUSVM
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | Flash HUSVM
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | CATE certification | CATE |  | Completed | Already certified
NAM | Install Flash HUSVM and create install PCM | Kery Hines Raja Balasubramanian | TBD | Waiting | TBD

## VMAX3
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | EMC VMAX3
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | CATE certification | CATE | TBD | In Progress | CATE certifying VMAX3 and SE 8.x
NAM | Install VMAX3's and create install PCM | Kery Hines Raja Balasubramanian | TBD | Waiting | Arrays at datacenters pending install
NAM | Upgrade SE from 7.6 to 8.x | Kery Hines Raja Balasubramanian | TBD | Waiting | Pending CATE; determine scope (upgrade all SE servers or just a few and turnover remainder to SAN teams)
NAM | Upgrade U4V from 1.6.1 to 1.6.x | Kery Hines Raja Balasubramanian | TBD | Waiting | Pending CATE; determine scope (upgrade all U4V servers or just a few and turnover remainder to SAN teams)

## Scale IO
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | EMC Scale I/O
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | CATE certification | CATE | TBD | In Progress | Testing in the lab at present
NAM | Order physical servers for POC | TBD | TBD | Waiting | TBD
NAM | Install configure Scale I/O software | TBD | TBD | Waiting | TBD

## SRM
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | EMC ViPR - SRM
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
EMEA | Core Infrastructure Servers (Front/Backend) | EMC |  | Completed | SRM Installation about to start.
EMEA | Collector Servers in FDC | EMC | TBD | In Progress | Almost ready - awaiting final SA validation
EMEA | Collector servers in RDC/CGC | EMC | TBD | In Progress | Pending as we are waiting for fixing network issue on RDC LVM cluster
EMEA | Provide updated Inventory | Salauddin Ahmed | 2014-08-01 | In Progress
EMEA | Provide FID’s and access to the SAN products/devices | Salauddin Ahmed | TBD | Waiting | Need to provide access to all those devices that will need to be discovered.
EMEA | Prepare Discovery Schedule | Salauddin Ahmed | TBD | Waiting | Work with SRM team (John, Matt, EMC) to prepare discovery schedule (week days / weekends, which devices first, which at the end, etc.) … with assumption that RDC is the top priority.
EMEA | Review of SRM requirement | Salauddin Ahmed | TBD | Waiting | Review SRM requirement docs available on the SRM SharePoint to ensure all requirements are covered.

## Actifio
Team | Global Storage Emerging Technologies
Manager | Shibu Thayil
Project: | Actifio Product
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | Provide 25TB of SAN storage for Actifio controller/servers in MWDC and SWDC | SAN provisioning Kery Hines Raja Balasubramanian | TBD | Waiting | Waiting for client to enter TCRS