## Current Projects
Team | L3 NA SAN Project Summary
Manager | Scott Taylor
Region | Project | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification
NAM | EMC Symmetrix VMAX 10K/20K/40K running Enginuity version ePAC Upgrade 5876.268.174 | 2015-03-31 | 15 of 120 Arrays completed | Upgrade the existing estate VMAX to the latest CATE certified release.
NAM | Cisco Firmware Upgrade to 5.2.8e | 2015-03-31 | 14 of 200 switches completed. | Upgrade 190 Cisco MDS switches to the latest CATE certified release to enhance the port monitoring in the SAN fabric.
NAM | HDS VSP Microcode upgrade to 70-06-13-00/20 | 2014-12-07 | 80% Completed 21 of 26 VSP HDS arrays have been completed | Micro code update is required to correct defective code delivered by the vendor. Failure to deploy this code can lead to a data unavailable situation.
NAM | SRM Discover SAN devices | 2015-03-31 | Completed Pilot Discovered 100% of SAN arrays in North America | SRM is the strategicsoftware package to provide Performance, Correlation, Fault, Alarming & Capacity Planning in the SAN and NAS environments,
NAM | HPNA | 2014-11-24 | Completed Phase I : Discovered 100% of SAN arrays in North America | HPNA is a Configuration Assurance application run against the Global SAN environment. This tool compares the CATE SBCC to the true configuration on the array/ switch to ensure changes in configuration are identified in the Production SAN environment.
NAM | VMAX3 / ESRS | 2015-03-31 | Project is being scoped for completion in Q1 2015 | Upgrade the ESRS gateways to ensure compatibility with VMAX3
NAM | XtremeIO | 2014-11-01 | Completed the deployment of 21 XtremeIO bricks in North America to support the VDI 2.0 project | XtremeIO is an all flach array used serve VDI desktop images to ESX clusters.
NAM | XIV | 2015-03-31 | IBM XIV Microcode Upgrade to 11.4.2.a 16 of 19 completed
NAM | VNX | 2015-03-31 | VNX Block upgrqade levels in 05.32.000.5.215

## Closed Projects
Team | Global Storage Provisioning and Migrations
Manager | Gary Battersby
Region | Project | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification

## NAS Migrations Q3 2013
Costs Based on Start: |  | 2015-01-01 | Start Date : | 2015-01-17 |  | Copy Rate Estimate: |  | 1 | TB every | 3.2 | Hours |  | Copy Window Max : |  | 12 | Hours |  | Wave Data Per Weekend : |  | 14 | TB
[22 empty] | Schedule | [5 empty] | Cost Estimates
In Scope | VM | Geo | City | Host Name | Serial# | System | Used Capacity | Number of Weekends for Waves | Data Movement | HW Exp | List Price | Months | Extend to Dec 31, 2015 | Country | State | EOL | TR Details | Cluster # | Partner # | Priority | Monthly Maintenance | Project Start Date | Scheduled Week Number | Scheduled Start | Scheduled Finished | Decomm Date | Estimated Months to Cut Over | Estimated Maintenance Costs | Resource Cost | Private Network Costs | Cable Costs | Copy Server Costs | Total Costs
Yes | No | Americas | 390 Greenwich | nasny152dr | 700000039136 | FAS3140 | 30.03 | 3 | 12.5 | 2014-12-31 | 13197.8 | 1 | 126698.88 | United States | NY | 2017-03-31 | TR2013 | 33 | 1 | 6 | 10558.24 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-25 | 2015-05-25 | 5 | 52791.2 | 0 | 0 | 0 | 0 | 52791.2
Yes | No | Americas | 390 Greenwich | nasny153dr | 700000039148 | FAS3140 | 30.75 | 3 | 12.5 | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 33 | 2 | 6 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-25 | 2015-05-25 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD115DR | 700000180313 | FAS3140 | 7.23 | 1 | 3.75 | 2014-12-31 | 11800.78 | 1 | 113287.488 | United States | TX | 2017-03-31 | TR2013 | 34 | 1 | 13 | 9440.624 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 47203.12 | 0 | 0 | 0 | 0 | 47203.12
Yes | No | Americas | Roanoke | NASSWD116DR | 700000180325 | FAS3140 | 8.02 | 1 | 3.75 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 34 | 2 | 13 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD117DR | 700000187581 | FAS3140 | 6.12 | 1 | 2.5 | 2014-12-31 | 9369.96 | 1 | 89951.616 | United States | TX | 2017-03-31 | TR2013 | 35 | 1 | 24 | 7495.968 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 37479.84 | 0 | 0 | 0 | 0 | 37479.84
Yes | No | Americas | Roanoke | NASSWD118DR | 700000187593 | FAS3140 | 17.19 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 35 | 2 | 24 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD009 | 700000180143 | FAS3140 | 7.19 | 1 | 3.75 | 2014-12-31 | 11800.78 | 1 | 113287.488 | United States | OH | 2017-03-31 | TR2013 | 36 | 1 | 13 | 9440.624 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 28321.872 | 0 | 0 | 0 | 0 | 28321.872
Yes | No | Americas | Delaware | NASMWD010 | 700000180131 | FAS3140 | 7.98 | 1 | 3.75 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 36 | 2 | 13 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD011 | 700000180909 | FAS3140 | 26.55 | 2 | 11.25 | 2014-12-31 | 14940.42 | 1 | 143428.032 | United States | OH | 2017-03-31 | TR2013 | 37 | 1 | 2 | 11952.336 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-14 | 2015-03-16 | 3 | 35857.008 | 0 | 0 | 0 | 0 | 35857.008
Yes | No | Americas | Delaware | NASMWD012 | 700000180911 | FAS3140 | 23.51 | 2 | 10 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 37 | 2 | 2 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Tucson | NASTUS103 | 700000174560 | FAS2020 | 0.98 | 1 | 1.25 | 2014-12-31 | 960.54 | 1 | 9221.184 | United States | AZ | 2017-06-17 | TR2014 | 38 | 1 | 91 | 768.432 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1536.864 | 0 | 0 | 0 | 0 | 1536.864
Yes | No | Americas | Tucson | NASTUS104 | 700000174716 | FAS2020 | 0.4 | 1 | 1.25 | 2014-12-31 |  |  |  | United States | AZ | 2017-06-17 | TR2014 | 38 | 2 | 91 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD109DR | 70002136 | FAS3140 | 14.54 | 2 | 6.25 | 2014-12-31 | 10122.32 | 1 | 97174.272 | United States | TX | 2017-03-31 | TR2013 | 39 | 1 | 20 | 8097.856 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 40489.28 | 0 | 0 | 0 | 0 | 40489.28
Yes | No | Americas | Roanoke | NASSWD110DR | 70002137 | FAS3140 | 9.64 | 1 | 5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 39 | 2 | 20 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD031VM | 700000312318 | FAS3170 |  |  |  | 2014-12-31 | 10561.18 | 1 | 101387.328 | United States | OH | 2017-03-31 | TR2013 | 17 | 1 | 17 | 8448.944 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD032VM | 700000312306 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 17 | 2 | 17 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd015vm | 700000124620 | FAS3170 |  |  |  | 2014-12-31 | 9907.16 | 1 | 95108.736 | United States | OH | 2017-03-31 | TR2014 | 5 | 1 | 23 | 7925.728 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd016vm | 700000124618 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 5 | 2 | 23 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd013vm | 700000127775 | FAS3170 |  |  |  | 2014-12-31 | 8953.16 | 1 | 85950.336 | United States | OH | 2017-03-31 | TR2014 | 32 | 1 | 25 | 7162.528 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd014vm | 700000127787 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 32 | 2 | 25 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD033VM | 700000450172 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | OH | 2017-03-31 | TR2013 | 24 | 1 | 38 | 5832.912 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD034VM | 700000450160 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 24 | 2 | 38 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd009vm | 700000066983 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | OH | 2017-03-31 | TR2013 | 30 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd010vm | 700000161628 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 30 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY013VM | 700000378362 | FAS3170 |  |  |  | 2014-12-31 | 6961.16 | 1 | 66827.136 | United States | NY | 2017-03-31 | TR2013 | 19 | 1 | 43 | 5568.928 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY014VM | 700000378374 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 19 | 2 | 43 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY015VM | 700000184199 | FAS3170 |  |  |  | 2014-12-31 | 6961.16 | 1 | 66827.136 | United States | NY | 2017-03-31 | TR2013 | 20 | 1 | 43 | 5568.928 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY016VM | 700000184204 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 20 | 2 | 43 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD021VM | 30028280 | FAS3170 |  |  |  | 2014-12-31 | 6937.16 | 1 | 66596.736 | United States | OH | 2017-03-31 | TR2013 | 8 | 1 | 44 | 5549.728 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD022VM | 700000270625 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 8 | 2 | 44 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD023VM | 700000177237 | FAS3170 |  |  |  | 2014-12-31 | 6937.16 | 1 | 66596.736 | United States | OH | 2017-03-31 | TR2013 | 9 | 1 | 44 | 5549.728 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD024VM | 700000177249 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 9 | 2 | 44 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD025VM | 700000175461 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2013 | 10 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD026VM | 700000175459 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 10 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD027VM | 700000175447 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2013 | 11 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD028VM | 700000175423 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 11 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD017VM | 700000177251 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2014 | 6 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD018VM | 700000184345 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 6 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD019VM | 700000177299 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2014 | 7 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD020VM | 700000177304 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 7 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | nasny009vm | 700000048979 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | NY | 2017-03-31 | TR2013 | 27 | 1 | 53 | 4834.496 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | nasny010vm | 700000048981 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 27 | 2 | 53 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD029VM | 700000329000 | FAS3170 |  |  |  | 2014-12-31 | 5653.14 | 1 | 54270.144 | United States | OH | 2017-03-31 | TR2013 | 18 | 1 | 57 | 4522.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD030VM | 700000328991 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 18 | 2 | 57 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | 390 Greenwich | NY4-3270-2 | 700000729004 | FAS3270 |  |  |  | 2015-07-31 | 13446.76 | 1 | 53787.04 | United States | NY | 2018-12-31 |  |  |  |  | 4482.2533 |  |  | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | 390 Greenwich | NY4-3270-1 | 700000729016 | FAS3270 |  |  |  | 2015-07-31 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 |  |  | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | ALCOBENDAS | MADCTINAS201A | 200000187294 | FAS3140 |  |  |  | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 |  |  |  |  | 4392.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | ALCOBENDAS | MADCTINAS201B | 200000187309 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Ann Arbor | nasaam100 | 3086762 | FAS3020 |  |  |  | 2014-10-31 | 1347 | 1 |  | United States | MI | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Ann Arbor | nasaam101 | 3086763 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | MI | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas201a | 20007947 | FAS3040 |  |  |  | 2014-04-30 | 3973.12 | 1 |  | Spain |  | 2014-04-11 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas201b | 20005889 | FAS3040 |  |  |  | 2014-04-30 |  |  |  | Spain |  | 2014-04-12 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas202a | 20008796 | FAS3040 |  |  |  | 2014-04-30 | 3973.12 | 1 |  | Spain |  | 2014-04-13 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas202b | 20008793 | FAS3040 |  |  |  | 2014-04-30 |  |  |  | Spain |  | 2014-04-14 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNASDR001 | 700000713598 | FAS2040 |  |  |  | 2015-09-30 | 2383.44 | 1 | 3813.504 | Columbia |  | 2015-12-10 |  |  |  |  | 317.792 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNAS002 | 700000714528 | FAS2040 |  |  |  | 2015-09-30 |  |  |  | Columbia |  | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNAS001 | 700000713603 | FAS2040 |  |  |  | 2015-09-30 | 1903.66 | 1 | 3045.856 | Columbia |  | 2015-12-10 |  |  |  |  | 253.8213 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLBOGDR031 | 700000714516 | FAS2040 |  |  |  | 2015-09-30 |  |  |  | Columbia |  | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas201a | 200000002054 | FAS3140 |  |  |  | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 |  |  |  |  | 3298.016 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas201b | 200000002028 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas202a | 200000001995 | FAS3140 |  |  |  | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 |  |  |  |  | 3298.016 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas202b | 200000002016 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | nasmwd011vm | 700000044959 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | OH | 2017-03-31 |  |  |  |  | 4834.496 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | nasmwd012vm | 700000044961 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | NASMWD037VM | 700000596914 | FAS3170 |  |  |  | 2015-04-30 | 9541.94 | 1 | 61068.416 | United States | OH | 2017-03-31 |  |  |  |  | 5089.0347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | NASMWD038VM | 700000596926 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd001 | 3091333 | FAS3050 |  |  |  | 2014-10-31 | 4122.52 | 1 |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd002 | 3091332 | FAS3050 |  |  |  | 2014-10-31 |  |  |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd007 | 3089909 | FAS3020 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd008 | 3089910 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD013 | 700000334794 | FAS3140 |  |  |  | 2014-12-31 | 5889.9 | 1 | 56543.04 | United States | OH | 2017-03-31 |  |  |  |  | 4711.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD014 | 700000334782 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD005DR | 700000382387 | FAS3140 |  |  |  | 2014-12-31 | 10111.96 | 1 | 97074.816 | United States | OH | 2017-03-31 |  |  |  |  | 8089.568 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD006DR | 700000382399 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD007DR | 700000380133 | FAS3140 |  |  |  | 2014-12-31 | 2928.28 | 1 | 28111.488 | United States | OH | 2017-03-31 |  |  |  |  | 2342.624 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD008DR | 700000380121 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD001S | 700000515350 | FAS3140 |  |  |  | 2015-01-30 | 3132.06 | 1 | 27562.128 | United States | OH | 2017-03-31 |  |  |  |  | 2296.844 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD002S | 700000515348 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD003S | 700000517009 | FAS3140 |  |  |  | 2015-01-30 | 7634.16 | 1 | 67180.608 | United States | OH | 2017-03-31 |  |  |  |  | 5598.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD004S | 700000517011 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD009DR | 700000567004 | FAS3140 |  |  |  | 2015-03-31 | 4468.54 | 1 | 32173.488 | United States | OH | 2017-03-31 |  |  |  |  | 2681.124 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD010DR | 700000566995 | FAS3140 |  |  |  | 2015-03-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF7001A | 700000655057 | FAS3210 |  |  |  | 2015-04-30 | 3518.5 | 1 | 22518.4 | United States | OH | 2018-12-31 |  |  |  |  | 1876.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF7001B | 700000655069 | FAS3210 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | GTDCTINASF8002A | 700000634821 | FAS3240 |  |  |  | 2015-04-30 | 2592.02 | 1 | 16588.928 | United States | OH | 2018-12-31 |  |  |  |  | 1382.4107 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1001A | 700000638451 | FAS3240 |  |  |  | 2015-04-30 | 11485.64 | 1 | 73508.096 | United States | OH | 2018-12-31 |  |  |  |  | 6125.6747 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1001B | 700000638449 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1005A | 700000638487 | FAS3240 |  |  |  | 2015-04-30 | 12242.6 | 1 | 78352.64 | United States | OH | 2018-12-31 |  |  |  |  | 6529.3867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1005B | 700000638499 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1006A | 940000062595 | FAS3240 |  |  |  | 2015-04-30 | 10287.6 | 1 | 65840.64 | United States | OH | 2018-12-31 |  |  |  |  | 5486.72 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1006B | 700000647220 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1007A | 940001048778 | FAS3240 |  |  |  | 2015-04-30 | 10728.68 | 1 | 68663.552 | United States | OH | 2018-12-31 |  |  |  |  | 5721.9627 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1007B | 700000635344 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8001A | 700000934453 | FAS3240 |  |  |  | 2015-04-30 | 2097.04 | 1 | 13421.056 | United States | OH | 2018-12-31 |  |  |  |  | 1118.4213 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8001B | 500000245690 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8002A | 850000089803 | FAS3240 |  |  |  | 2015-04-30 | 5138.98 | 1 | 32889.472 | United States | OH | 2018-12-31 |  |  |  |  | 2740.7893 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8002B | 940000041242 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD011DR | 700000668925 | FAS3240 |  |  |  | 2015-05-31 | 10728.68 | 1 | 60080.608 | United States | OH | 2018-12-31 |  |  |  |  | 5006.7173 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD012DR | 700000668913 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF4001A | 700000689761 | FAS2040 |  |  |  | 2015-06-30 | 1949.94 | 1 | 9359.712 | United States | OH | 2015-12-10 |  |  |  |  | 779.976 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF4001B | 700000689759 | FAS2040 |  |  |  | 2015-06-30 |  |  |  | United States | OH | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS401A | 20025965 | FAS3070 |  |  |  | 2014-03-31 | 6766.18 | 1 |  | Germany |  | 2014-04-01 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS401B | 20025966 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-02 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS501A | 20016003 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-03 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS501B | 20016351 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-04 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas503s | 200000007365 | FAS3140 |  |  |  | 2014-06-30 | 3084.24 | 1 | 29608.704 | Germany |  | 2017-03-31 |  |  |  |  | 2467.392 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS405A | 200000181276 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | Germany |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS405B | 200000179728 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas402a | 200000034942 | FAS3170 |  |  |  | 2014-12-31 | 8587.56 | 1 | 82440.576 | Germany |  | 2017-03-31 |  |  |  |  | 6870.048 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas402b | 200000088278 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas505a | 200000135837 | FAS3170 |  |  |  | 2014-12-31 | 11028.42 | 1 | 105872.832 | Germany |  | 2017-03-31 |  |  |  |  | 8822.736 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas505b | 200000136013 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS504A | 200000035063 | FAS3170 |  |  |  | 2014-12-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2017-03-31 |  |  |  |  | 10151.312 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS504B | 200000035099 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut152 | 70000916 | FAS3170 | 15.23 | 2 | 6.25 | 2014-12-31 | 12385.78 | 1 | 118903.488 | United States | NJ | 2017-03-31 | TR2013 | 40 | 1 | 11 | 9908.624 | 2015-01-17 | 10 | 2015-03-21 | 2015-03-28 | 2015-04-27 | 4 | 39634.496 | 0 | 0 | 0 | 0 | 39634.496
Yes | No | Americas | Rutherford | nasrut153 | 70000917 | FAS3170 | 9.38 | 2 | 3.75 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 40 | 2 | 11 | 0 | 2015-01-17 | 10 | 2015-03-21 | 2015-03-28 | 2015-04-27 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut154 | 70000914 | FAS3170 | 8.79 | 2 | 3.75 | 2014-12-31 | 13706.22 | 1 | 131579.712 | United States | NJ | 2017-03-31 | TR2013 | 41 | 1 | 5 | 10964.976 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-14 | 2015-04-13 | 4 | 43859.904 | 0 | 0 | 0 | 0 | 43859.904
Yes | No | Americas | Rutherford | nasrut155 | 70000915 | FAS3170 | 16.39 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 41 | 2 | 5 | 0 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-14 | 2015-04-13 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Georgetown | nasgtd005vm | 700000024387 | FAS3170 |  |  |  | 2014-12-31 | 5458.12 | 1 | 52397.952 | United States | TX | 2017-03-31 | TR2014 | 4 | 1 | 61 | 4366.496 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Georgetown | nasgtd006vm | 700000024399 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 4 | 2 | 61 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | nasgtd001 | 30019701 | FAS3040 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | nasgtd002 | 30019702 | FAS3040 |  |  |  | 2014-10-31 |  |  |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | NASGTD001S | 800000006387 | FAS3140 |  |  |  | 2014-12-31 | 7095.42 | 1 | 68116.032 | United States | TX | 2017-03-31 |  |  |  |  | 5676.336 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8001A | 700000398269 | FAS3170 |  |  |  | 2015-04-30 | 8262.25 | 1 | 52878.4 | United States | TX | 2017-03-31 |  |  |  |  | 4406.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8001B | 700000591263 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8002B | 700000488492 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Jardines | MEXCTINASF8001B | 940001037365 | FAS3240 |  |  |  | 2015-05-31 | 5123.94 | 1 | 28694.064 | Mexico |  | 2018-12-31 |  |  |  |  | 2391.172 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Jardines | MEXCTINASF8001A | 940001037078 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | Mexico |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS201A | 30003866 | FAS3040 |  |  |  | 2014-03-31 | 2342.52 | 1 |  | Pakistan |  | 2014-04-05 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS201B | 30003867 | FAS3040 |  |  |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-06 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS202A | 30001777 | FAS3040 |  |  |  | 2014-03-31 | 2015.82 | 1 |  | Pakistan |  | 2014-04-07 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS202B | 1088268 | FAS3040 |  |  |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-08 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS501A | 20016347 | FAS3070 |  |  |  | 2014-04-30 | 10846.61 | 1 |  | United Kingdom |  | 2014-04-09 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS501B | 20016346 | FAS3070 |  |  |  | 2014-04-30 |  |  |  | United Kingdom |  | 2014-04-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS503S | 200000009052 | FAS3140 |  |  |  | 2014-06-30 | 3084.24 | 1 | 29608.704 | United Kingdom |  | 2017-03-31 |  |  |  |  | 2467.392 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS402A | 200000203907 | FAS3170 |  |  |  | 2014-09-30 | 6812.54 | 1 | 65400.384 | United Kingdom |  | 2017-03-31 |  |  |  |  | 5450.032 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS402B | 200000203919 | FAS3170 |  |  |  | 2014-09-30 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS209A | 200000069117 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS209B | 200000068993 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS210A | 200000069105 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS210B | 200000062004 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS505A | 200000152031 | FAS3170 |  |  |  | 2014-12-31 | 11028.42 | 1 | 105872.832 | United Kingdom |  | 2017-03-31 |  |  |  |  | 8822.736 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS505B | 200000151049 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas504a | 200000043917 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas504b | 200000043905 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS401A | 200000153724 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | United Kingdom |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS401B | 200000155356 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS403A | 200000154376 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | United Kingdom |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS403B | 200000154388 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS302A | 200000007420 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS302B | 200000007547 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS301A | 200000005197 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS301B | 200000002638 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS304A | 200000005056 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS304B | 200000005185 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS303A | 200000005020 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS303B | 200000004997 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS207A | 200000002975 | FAS3170 |  |  |  | 2015-01-31 | 13764.32 | 1 | 121126.016 | United Kingdom |  | 2017-03-31 |  |  |  |  | 10093.8347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS207B | 200000002963 | FAS3170 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas208a | 200000002913 | FAS3170 |  |  |  | 2015-01-31 | 13764.32 | 1 | 121126.016 | United Kingdom |  | 2017-03-31 |  |  |  |  | 10093.8347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas208b | 200000001543 | FAS3170 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4006a | 850000065742 | FAS3240 |  |  |  | 2015-07-31 | 4720.66 | 1 | 18882.64 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1573.5533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4006b | 700001088706 | FAS3240 |  |  |  | 2015-07-31 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4007a | 940000068484 | FAS3240 |  |  |  | 2015-07-31 | 4720.66 | 1 | 18882.64 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1573.5533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4007b | 200000567107 | FAS3240 |  |  |  | 2015-07-31 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6003A | 200000377916 | FAS3240 |  |  |  | 2015-11-30 | 5398.78 | 1 | 4319.024 | United Kingdom |  | 2018-12-31 |  |  |  |  | 359.9187 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6003B | 200000431736 | FAS3240 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6004A | 200000435471 | FAS3240 |  |  |  | 2015-11-30 | 5876.54 | 1 | 4701.232 | United Kingdom |  | 2018-12-31 |  |  |  |  | 391.7693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6004B | 200000435483 | FAS3240 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2011A | 200000436736 | FAS3270 |  |  |  | 2015-11-30 | 15488.02 | 1 | 12390.416 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1032.5347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2011B | 200000439544 | FAS3270 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2012A | 200000430976 | FAS3270 |  |  |  | 2015-11-30 | 15488.02 | 1 | 12390.416 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1032.5347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2012B | 200000430964 | FAS3270 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | MADRID | MADCTINAS202A | 200000187323 | FAS3140 |  |  |  | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 |  |  |  |  | 4392.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | MADRID | MADCTINAS202B | 200000187311 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Mexico City | UNKNOWN | 700000173152 | FAS3140 |  |  |  | 2014-03-31 | 1179.14 | 1 | 11319.744 | Mexico |  | 2017-03-31 |  |  |  |  | 943.312 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Mexico City | UNKNOWN | 700000173164 | FAS3140 |  |  |  | 2014-03-31 |  |  |  | Mexico |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS401A | 200000250508 | FAS3140 |  |  |  | 2015-01-30 | 3221.26 | 1 | 28347.088 | Italy |  | 2017-03-31 |  |  |  |  | 2362.2573 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS401B | 200000250493 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS402A | 200000245395 | FAS3140 |  |  |  | 2015-01-30 | 3221.26 | 1 | 28347.088 | Italy |  | 2017-03-31 |  |  |  |  | 2362.2573 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS402B | 200000245266 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Monterrey | mtyctinasf8001b | 940001036579 | FAS3240 |  |  |  | 2015-05-31 | 5123.94 | 1 | 28694.064 | Mexico |  | 2018-12-31 |  |  |  |  | 2391.172 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Monterrey | mtyctinasf8001a | 940001038010 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | Mexico |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS201A | 200000068448 | FAS3160 |  |  |  | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 |  |  |  |  | 9329.52 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS201B | 200000067183 | FAS3160 |  |  |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS202A | 200000066622 | FAS3160 |  |  |  | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 |  |  |  |  | 9329.52 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS202B | 200000066646 | FAS3160 |  |  |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD111DR | 70002138 | FAS3170 | 123.74 | 9 | 48.75 | 2014-12-31 | 18584.64 | 1 | 178412.544 | United States | TX | 2017-03-31 | TR2013 | 42 | 1 | 1 | 14867.712 | 2015-01-17 | 0 | 2015-04-11 | 2015-06-06 | 2015-07-06 | 7 | 104073.984 | 0 | 0 | 0 | 0 | 104073.984
Yes | No | Americas | Roanoke | NASSWD112DR | 70002139 | FAS3170 | 101.32 | 9 | 40 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 42 | 2 | 1 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-06-06 | 2015-07-06 | 7 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | NEW YORK | NASNY011VM | 700000304995 | FAS3170 |  |  |  | 2014-12-31 | 7969.16 | 1 | 76503.936 | United States | NY | 2017-03-31 | TR2013 | 14 | 1 | 31 | 6375.328 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | NEW YORK | NASNY012VM | 700000305004 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 14 | 2 | 31 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | NASNY001 | 700000516940 | FAS3140 |  |  |  | 2015-01-30 | 4431.42 | 1 | 38996.496 | United States | NY | 2017-03-31 |  |  |  |  | 3249.708 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | NASNY002 | 700000516952 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | NY | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1003a | 940001037092 | FAS3240 |  |  |  | 2015-04-30 | 9883.96 | 1 | 63257.344 | United States | NY | 2018-12-31 |  |  |  |  | 5271.4453 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1003b | 700000633736 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1004a | 700000639364 | FAS3240 |  |  |  | 2015-04-30 | 11397.88 | 1 | 72946.432 | United States | NY | 2018-12-31 |  |  |  |  | 6078.8693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1004b | 700000639376 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Georgetown | GTDCTINASF1008A | 700000270560 | FAS3140 | 0.87296 | 1 |  | 2014-12-31 | 3476.88 | 1 | 33378.048 | United States | TX | 2017-03-31 | TR2014 | 43 | 1 | 70 | 2781.504 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 5563.008 | 0 | 0 | 0 | 0 | 5563.008
Yes | No | Americas | Georgetown | GTDCTINASF1008B | 700000270572 | FAS3140 | 3.0086 | 1 |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 43 | 2 | 70 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | O'Fallon | NASSTL003VM | 700000278809 | FAS3170 |  |  |  | 2014-12-31 | 9931.18 | 1 | 95339.328 | United States | MO | 2017-03-31 | TR2013 | 15 | 1 | 22 | 7944.944 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | O'Fallon | NASSTL004VM | 700000278811 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | MO | 2017-03-31 | TR2013 | 15 | 2 | 22 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | nasstl16 | 3087450 | FAS3050 |  |  |  | 2014-10-31 | 4122.52 | 1 | 39576.192 | United States | MO | [5 empty] | 3298.016 |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | nasstl17 | 3087451 | FAS3050 |  |  |  | 2014-10-31 |  |  |  | United States | MO | [5 empty] | 0 |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | NASSTL003 | 700000592035 | FAS3170 |  |  |  | 2015-04-30 | 18353.42 | 1 | 117461.888 | United States | MO | 2017-03-31 |  |  |  |  | 9788.4907 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | NASSTL004 | 700000592047 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | MO | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Georgetown | NASGTD007 | 700000262915 | FAS3140 | 3.6997 | 1 |  | 2014-12-31 | 4222.4 | 1 | 40535.04 | United States | TX | 2017-03-31 | TR2014 | 44 | 1 | 66 | 3377.92 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6755.84 | 0 | 0 | 0 | 0 | 6755.84
Yes | No | Americas | Georgetown | NASGTD008 | 700000262927 | FAS3140 | 3.8509 | 1 |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 44 | 2 | 66 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS202A | 200000067808 | FAS3140 |  |  |  | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 |  |  |  |  | 3662.8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS202B | 200000067810 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS201A | 200000067145 | FAS3140 |  |  |  | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 |  |  |  |  | 3662.8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS201B | 200000066880 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | CHICAGO | NASCHI06 | 600000015114 | FAS2020 | 2.2301 | 1 |  | 2014-12-31 | 1210.4 | 1 | 11619.84 | United States | IL | 2017-06-17 | TR2014 | 45 | 1 | 88 | 968.32 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1936.64 | 0 | 0 | 0 | 0 | 1936.64
Yes | No | Americas | CHICAGO | NASCHI05 | 700000302959 | FAS2020 | 3.95 | 1 |  | 2014-12-31 |  |  |  | United States | IL | 2017-06-17 | TR2014 | 45 | 2 | 88 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | CHICAGO | NASCHI08 | 600000014744 | FAS2020 | 0.88 | 1 | 1.25 | 2014-12-31 | 788.2 | 1 | 7566.72 | United States | IL | 2017-06-17 | TR2013 | 46 | 1 | 92 | 630.56 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1261.12 | 0 | 0 | 0 | 0 | 1261.12
Yes | No | Americas | CHICAGO | NASCHI07 | 700000295429 | FAS2020 | 0.88 | 1 | 1.25 | 2014-12-31 |  |  |  | United States | IL | 2017-06-17 | TR2013 | 46 | 2 | 92 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | SAN FRANCISCO | NASSFR04 | 600000007856 | FAS2020 | 2.3278 | 1 |  | 2014-12-31 | 1347 | 1 | 12931.2 | United States | CA | 2017-06-17 | TR2014 | 47 | 1 | 86 | 1077.6 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 2155.2 | 0 | 0 | 0 | 0 | 2155.2
Yes | No | Americas | SAN FRANCISCO | NASSFR03 | 700000293213 | FAS2020 | 2.1042 | 1 |  | 2014-12-31 |  |  |  | United States | CA | 2017-06-17 | TR2014 | 47 | 2 | 86 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | nasswd113dr | 700000109826 | FAS3140 | 13.36 | 1 | 6.25 | 2014-12-31 | 12407.18 | 1 | 119108.928 | United States | TX | 2017-03-31 | TR2013 | 48 | 1 | 10 | 9925.744 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 49628.72 | 0 | 0 | 0 | 0 | 49628.72
Yes | No | Americas | Roanoke | nasswd114dr | 70004739 | FAS3140 | 19.2 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 48 | 2 | 10 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD003DR | 700000017827 | FAS3140 | 24.08 | 2 | 10 | 2014-12-31 | 12829.4 | 1 | 123162.24 | United States | OH | 2017-03-31 | TR2013 | 49 | 1 | 7 | 10263.52 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 51317.6 | 0 | 0 | 0 | 0 | 51317.6
Yes | No | Americas | Delaware | NASMWD004DR | 80002155 | FAS3140 | 23.23 | 2 | 10 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 49 | 2 | 7 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut156 | 700000038754 | FAS3140 | 39.3 | 3 | 16.25 | 2014-12-31 | 14940.42 | 1 | 143428.032 | United States | NJ | 2017-03-31 | TR2013 | 50 | 1 | 2 | 11952.336 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-21 | 2015-03-23 | 3 | 35857.008 | 0 | 0 | 0 | 0 | 35857.008
Yes | No | Americas | Rutherford | nasrut157 | 700000038766 | FAS3140 | 35.13 | 3 | 13.75 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 50 | 2 | 2 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd017vm | 700000128884 | FAS3170 |  |  |  | 2014-12-31 | 10261.16 | 1 | 98507.136 | United States | TX | 2017-03-31 | TR2014 | 31 | 1 | 19 | 8208.928 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd018vm | 700000128896 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 31 | 2 | 19 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD027VM | 700000313790 | FAS3170 |  |  |  | 2014-12-31 | 9931.18 | 1 | 95339.328 | United States | TX | 2017-03-31 | TR2013 | 13 | 1 | 22 | 7944.944 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD028VM | 700000313805 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 13 | 2 | 22 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd015vm | 700000047274 | FAS3170 |  |  |  | 2014-12-31 | 8659.14 | 1 | 83127.744 | United States | TX | 2017-03-31 | TR2013 | 29 | 1 | 26 | 6927.312 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd016vm | 700000066969 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 29 | 2 | 26 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD019VM | 700000124656 | FAS3170 |  |  |  | 2014-12-31 | 7945.16 | 1 | 76273.536 | United States | TX | 2017-03-31 | TR2014 | 1 | 1 | 32 | 6356.128 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD020VM | 700000124668 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 1 | 2 | 32 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD025VM | 700000313855 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 12 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD026VM | 700000313867 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 12 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD029VM | 700000180105 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 21 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD030VM | 700000450158 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 21 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD031VM | 700000446341 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 22 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD032VM | 700000446353 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 22 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD021VM | 700000142701 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | TX | 2017-03-31 | TR2013 | 2 | 1 | 50 | 5026.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD022VM | 700000172794 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 2 | 2 | 50 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD023VM | 700000155942 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | TX | 2017-03-31 | TR2013 | 3 | 1 | 50 | 5026.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD024VM | 700000172548 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 3 | 2 | 50 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd011vm | 30020787 | FAS3170 |  |  |  | 2014-12-31 | 4675.12 | 1 | 44881.152 | United States | TX | 2017-03-31 | TR2013 | 26 | 1 | 64 | 3740.096 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd012vm | 700000047286 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 26 | 2 | 64 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD033VM | 700000571249 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | TX | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD034VM | 700000571251 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD037VM | 700000571627 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | TX | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD038VM | 700000571639 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD039VM | 700000593089 | FAS3170 |  |  |  | 2015-04-30 | 9541.94 | 1 | 61068.416 | United States | TX | 2017-03-31 |  |  |  |  | 5089.0347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD040VM | 700000593077 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | nasswd105dr | 3082623 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD119DR | 700000267886 | FAS3140 |  |  |  | 2014-12-31 | 4222.4 | 1 | 40535.04 | United States | TX | 2017-03-31 |  |  |  |  | 3377.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD120DR | 700000267898 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD121DR | 700000282642 | FAS3140 |  |  |  | 2014-12-31 | 13715.2 | 1 | 131665.92 | United States | TX | 2017-03-31 |  |  |  |  | 10972.16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD122DR | 700000282654 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1008A | 700000271679 | FAS3140 |  |  |  | 2014-12-31 | 3476.88 | 1 | 33378.048 | United States | TX | 2017-03-31 |  |  |  |  | 2781.504 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1008B | 700000271681 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD123DR | 700000334744 | FAS3140 |  |  |  | 2014-12-31 | 5889.9 | 1 | 56543.04 | United States | TX | 2017-03-31 |  |  |  |  | 4711.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD124DR | 700000334756 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD004S | 700000515427 | FAS3140 |  |  |  | 2015-01-30 | 3456.06 | 1 | 30413.328 | United States | TX | 2017-03-31 |  |  |  |  | 2534.444 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD005S | 700000515439 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD006S | 700000516988 | FAS3140 |  |  |  | 2015-01-30 | 6194.8 | 1 | 54514.24 | United States | TX | 2017-03-31 |  |  |  |  | 4542.8533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD007S | 700000516990 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD27 | 700000566933 | FAS3140 |  |  |  | 2015-03-31 | 4468.54 | 1 | 32173.488 | United States | TX | 2017-03-31 |  |  |  |  | 2681.124 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD28 | 700000566945 | FAS3140 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF7001A | 700000654900 | FAS3210 |  |  |  | 2015-04-30 | 3518.5 | 1 | 22518.4 | United States | TX | 2018-12-31 |  |  |  |  | 1876.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF7001B | 700000654895 | FAS3210 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1001A | 700000639261 | FAS3240 |  |  |  | 2015-04-30 | 11485.64 | 1 | 73508.096 | United States | TX | 2018-12-31 |  |  |  |  | 6125.6747 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1001B | 700000639273 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1002A | 700000634493 | FAS3240 |  |  |  | 2015-04-30 | 12242.6 | 1 | 78352.64 | United States | TX | 2018-12-31 |  |  |  |  | 6529.3867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1002B | 700000634481 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD29 | 700000668937 | FAS3240 |  |  |  | 2015-05-31 | 13756.54 | 1 | 77036.624 | United States | TX | 2018-12-31 |  |  |  |  | 6419.7187 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD30 | 700000668949 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF8001A | 200000299750 | FAS3270 |  |  |  | 2015-10-31 | 9949.92 | 1 | 15919.872 | United States | TX | 2018-12-31 |  |  |  |  | 1326.656 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF8001B | 700001112791 | FAS3270 |  |  |  | 2015-10-31 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | O'Fallon | nasstl001 | 700000044234 | FAS3140 | 10.59 | 1 | 5 | 2014-12-31 | 7762.94 | 1 | 74524.224 | United States | MO | 2017-03-31 | TR2013 | 51 | 1 | 33 | 6210.352 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 12420.704 | 0 | 0 | 0 | 0 | 12420.704
Yes | No | Americas | O'Fallon | nasstl002 | 700000044246 | FAS3140 | 12.28 | 1 | 5 | 2014-12-31 |  |  |  | United States | MO | 2017-03-31 | TR2013 | 51 | 2 | 33 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | nasswd17 | 700000067690 | FAS3140 | 16.11 | 2 | 7.5 | 2014-12-31 | 11045.36 | 1 | 106035.456 | United States | TX | 2017-03-31 | TR2013 | 52 | 1 | 15 | 8836.288 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 44181.44 | 0 | 0 | 0 | 0 | 44181.44
Yes | No | Americas | Roanoke | nasswd18 | 700000067705 | FAS3140 | 20.54 | 2 | 8.75 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 52 | 2 | 15 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | NEW YORK | NASNY34 | 700000446523 | FAS3140 | 8.029 | 1 |  | 2014-12-31 | 6360.52 | 1 | 61060.992 | United States | NY | 2017-03-31 | TR2014 | 53 | 1 | 49 | 5088.416 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 10176.832 | 0 | 0 | 0 | 0 | 10176.832
Yes | No | Americas | NEW YORK | NASNY35 | 700000446535 | FAS3140 | 12.8194 | 1 |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2014 | 53 | 2 | 49 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | NASRUT007VM | 700000312069 | FAS3170 |  |  |  | 2014-12-31 | 7969.16 | 1 | 76503.936 | United States | NJ | 2017-03-31 | TR2013 | 16 | 1 | 31 | 6375.328 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | NASRUT008VM | 700000312071 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 16 | 2 | 31 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut009vm | 700000446169 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | NJ | 2017-03-31 | TR2013 | 23 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut010vm | 700000558778 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 23 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut003vm | 700000044325 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | NJ | 2017-03-31 | TR2014 | 25 | 1 | 53 | 4834.496 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut004vm | 700000044337 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2014 | 25 | 2 | 53 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut005vm | 700000055594 | FAS3170 |  |  |  | 2014-12-31 | 4675.12 | 1 | 44881.152 | United States | NJ | 2017-03-31 | TR2013 | 28 | 1 | 64 | 3740.096 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut006vm | 700000055609 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 28 | 2 | 64 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | nasrut150 | 30007433 | FAS3040 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | nasrut151 | 30007434 | FAS3040 |  |  |  | 2014-10-31 |  |  |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT140 | 30011070 | FAS3070 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT149 | 30011093 | FAS3070 |  |  |  | 2014-10-31 |  |  |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT19DR | 700000281088 | FAS3140 |  |  |  | 2014-12-31 | 7340.72 | 1 | 70470.912 | United States | NJ | 2017-03-31 |  |  |  |  | 5872.576 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT20DR | 700000281090 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT002S | 700000430756 | FAS3160 |  |  |  | 2014-12-31 | 10487.84 | 1 | 100683.264 | United States | NJ | 2017-03-31 |  |  |  |  | 8390.272 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT003S | 700000516976 | FAS3140 |  |  |  | 2015-01-30 | 3175.76 | 1 | 27946.688 | United States | NJ | 2017-03-31 |  |  |  |  | 2328.8907 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | rutctinasf8001b | 700000571316 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | NJ | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | rutctinasf8001a | 700000571304 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT001DR | 700000603145 | FAS3140 |  |  |  | 2015-04-30 | 4755.42 | 1 | 30434.688 | United States | NJ | 2017-03-31 |  |  |  |  | 2536.224 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT002DR | 700001119115 | FAS3140 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | UNKNOWN | 700000244743 | FAS6080 |  |  |  | 2015-04-30 | 801.5 | 1 | 5129.6 | United States | NJ | 2015-09-15 |  |  |  |  | 427.4667 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1003A | 700000635265 | FAS3240 |  |  |  | 2015-04-30 | 9883.96 | 1 | 63257.344 | United States | NJ | 2018-12-31 |  |  |  |  | 5271.4453 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1003B | 700000635277 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1004A | 700000638384 | FAS3240 |  |  |  | 2015-04-30 | 11397.88 | 1 | 72946.432 | United States | NJ | 2018-12-31 |  |  |  |  | 6078.8693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1004B | 940001061160 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1002A | 700000639144 | FAS3240 |  |  |  | 2015-04-30 | 10728.68 | 1 | 68663.552 | United States | NJ | 2018-12-31 |  |  |  |  | 5721.9627 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1002B | 700000639156 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1007A | 700000639326 | FAS3240 |  |  |  | 2015-04-30 | 9061.68 | 1 | 57994.752 | United States | NJ | 2018-12-31 |  |  |  |  | 4832.896 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1007B | 700000639338 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1006A | 700000639340 | FAS3240 |  |  |  | 2015-04-30 | 10575.6 | 1 | 67683.84 | United States | NJ | 2018-12-31 |  |  |  |  | 5640.32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1006B | 500000218219 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1005A | 700000639522 | FAS3240 |  |  |  | 2015-04-30 | 10575.6 | 1 | 67683.84 | United States | NJ | 2018-12-31 |  |  |  |  | 5640.32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1005B | 700000639534 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | PALO ALTO | SFOCTINASF1001B | 600000014732 | FAS2020 | 0.45587 | 1 |  | 2014-12-31 | 692.98 | 1 | 6652.608 | United States | CA | 2017-06-17 | TR2014 | 54 | 1 | 93 | 554.384 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1108.768 | 0 | 0 | 0 | 0 | 1108.768
Yes | No | Americas | PALO ALTO | SFOCTINASF1001A | 700000293201 | FAS2020 | 0.61427 | 1 |  | 2014-12-31 |  |  |  | United States | CA | 2017-06-17 | TR2014 | 54 | 2 | 93 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr01 | 700000177483 | FAS3140 |  |  |  | 2014-02-28 | 6281.18 | 1 | 60299.328 | Brazil |  | 2017-03-31 |  |  |  |  | 5024.944 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr02 | 700000177495 | FAS3140 |  |  |  | 2014-02-28 |  |  |  | Brazil |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr03 | 700000248218 | FAS3140 |  |  |  | 2014-02-28 | 7970 | 1 | 76512 | Brazil |  | 2017-03-31 |  |  |  |  | 6376 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr04 | 700000175069 | FAS3140 |  |  |  | 2014-02-28 |  |  |  | Brazil |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | BLUE ASH | NASBLU02 | 700000518584 | FAS2040 | 0 | 1 | 0 | 2015-01-30 | 3912.56 | 1 | 34430.528 | United States | MO | 2015-12-10 | TR2013 | 55 | 1 | 70 | 2869.2107 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 5738.4213 | 0 | 0 | 0 | 0 | 5738.4213
Yes | No | Americas | BLUE ASH | NASBLU01 | 700000518596 | FAS2040 | 7.73 | 1 | 3.75 | 2015-01-30 |  |  |  | United States | MO | 2015-12-10 | TR2013 | 55 | 2 | 70 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Budapest | budctinas201a | 200000002054 | FAS3140 | 8.7761 | 1 | 3.75 | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 | TR2014 | 101 | 1 | 8 | 3298.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6596.032 | 0 | 0 | 0 | 0 | 6596.032
Yes | No | EMEA | Budapest | budctinas201b | 200000002028 | FAS3140 | 10.0193 | 1 |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 | TR2014 | 101 | 2 | 8 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Budapest | budctinas202a | 200000001995 | FAS3140 | 8.7547 | 1 | 3.75 | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 | TR2014 | 102 | 1 | 8 | 3298.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6596.032 | 0 | 0 | 0 | 0 | 6596.032
Yes | No | EMEA | Budapest | budctinas202b | 200000002016 | FAS3140 | 9.978 | 1 |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 | TR2014 | 102 | 2 | 8 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | FRACTINAS501A | 20016003 | FAS3070 | 21.2105 | 2 | 8.75 | 2014-03-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2014-04-03 | TR2014 | 103 | 1 | 2 | 10151.312 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 50756.56 | 0 | 0 | 0 | 0 | 50756.56
Yes | No | EMEA | Frankfurt | FRACTINAS501B | 20016351 | FAS3070 | 12.8387 | 1 |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-04 | TR2014 | 103 | 2 | 2 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | FRACTINAS504A | 200000035063 | FAS3170 | 29.7545 | 3 | 12.5 | 2014-12-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2017-03-31 | TR2014 | 104 | 1 | 2 | 10151.312 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 50756.56 | 0 | 0 | 0 | 0 | 50756.56
Yes | No | EMEA | Frankfurt | FRACTINAS504B | 200000035099 | FAS3170 | 29.9273 | 3 |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 | TR2014 | 104 | 2 | 2 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | fractinas505a | 200000135837 | FAS3170 | 30.3591 | 3 | 12.5 | 2014-12-31 | 11028.42 | 1 | 105872.832 | Germany |  | 2017-03-31 | TR2014 | 105 | 1 | 4 | 8822.736 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 44113.68 | 0 | 0 | 0 | 0 | 44113.68
Yes | No | EMEA | Frankfurt | fractinas505b | 200000136013 | FAS3170 | 6.4089 | 1 |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 | TR2014 | 105 | 2 | 4 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Karachi | KHICTINAS201A | 30003866 | FAS3040 | 13.2258 | 1 | 6.25 | 2014-03-31 | 2342.52 | 1 | 22488.192 | Pakistan |  | 2014-04-05 | TR2014 | 106 | 1 | 10 | 1874.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 3748.032 | 0 | 0 | 0 | 0 | 3748.032
Yes | No | EMEA | Karachi | KHICTINAS201B | 30003867 | FAS3040 | 13.2253 | 1 |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-06 | TR2014 | 106 | 2 | 10 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Karachi | KHICTINAS202A | 30001777 | FAS3040 | 13.2314 | 1 | 6.25 | 2014-03-31 | 2015.82 | 1 | 19351.872 | Pakistan |  | 2014-04-07 | TR2014 | 107 | 1 | 11 | 1612.656 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 3225.312 | 0 | 0 | 0 | 0 | 3225.312
Yes | No | EMEA | Karachi | KHICTINAS202B | 1088268 | FAS3040 | 13.229 | 1 |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-08 | TR2014 | 107 | 2 | 11 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS207A | 200000002975 | FAS3170 | 25.5421 | 2 | 10 | 2015-01-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 108 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS207B | 200000002963 | FAS3170 | 29.7505 | 3 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 108 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | ldnctinas208a | 200000002913 | FAS3170 | 24.9845 | 2 | 10 | 2015-01-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 109 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | ldnctinas208b | 200000001543 | FAS3170 | 29.6564 | 3 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 109 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS209A | 200000069117 | FAS3170 | 30.3588 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 110 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS209B | 200000068993 | FAS3170 | 30.319 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 110 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS210A | 200000069105 | FAS3170 | 30.0138 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 111 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS210B | 200000062004 | FAS3170 | 30.3053 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 111 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS301A | 200000005197 | FAS3140 | 9.38 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 112 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS301B | 200000002638 | FAS3140 | 4.8062 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 112 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS302A | 200000007420 | FAS3140 | 9.3824 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 113 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS302B | 200000007547 | FAS3140 | 4.8132 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 113 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS303A | 200000005020 | FAS3140 | 8.8364 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 114 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS303B | 200000004997 | FAS3140 | 10.2541 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 114 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS304A | 200000005056 | FAS3140 | 8.8521 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 115 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS304B | 200000005185 | FAS3140 | 10.261 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 115 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS501A | 20016347 | FAS3070 | 24.5514 | 2 | 10 | 2014-04-30 | 10846.61 | 1 | 104127.456 | United Kingdon |  | 2014-04-09 | TR2014 | 116 | 1 | 5 | 8677.288 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 43386.44 | 0 | 0 | 0 | 0 | 43386.44
Yes | No | EMEA | London | LDNCTINAS501B | 20016346 | FAS3070 | 15.5945 | 2 |  | 2014-04-30 |  |  |  | United Kingdon |  | 2014-04-10 | TR2014 | 116 | 2 | 5 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | ldnctinas504a | 200000043917 | FAS3170 | 29.9002 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 117 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | ldnctinas504b | 200000043905 | FAS3170 | 29.7545 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 117 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS505A | 200000152031 | FAS3170 | 30.0557 | 3 | 12.5 | 2014-12-31 | 11028.42 | 1 | 105872.832 | United Kingdom |  | 2017-03-31 | TR2014 | 118 | 1 | 4 | 8822.736 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 44113.68 | 0 | 0 | 0 | 0 | 44113.68
Yes | No | EMEA | London | LDNCTINAS505B | 200000151049 | FAS3170 | 6.587 | 1 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 118 | 2 | 4 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | ALCOBENDAS | MADCTINAS201A | 200000187294 | FAS3140 | 9.9462 | 1 | 5 | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 | TR2014 | 119 | 1 | 6 | 4392.384 | 2015-01-17 | 3 | 2015-01-31 | 2015-01-31 | 2015-03-02 | 2 | 8784.768 | 0 | 0 | 0 | 0 | 8784.768
Yes | No | EMEA | ALCOBENDAS | MADCTINAS201B | 200000187309 | FAS3140 | 9.9874 | 1 |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 | TR2014 | 119 | 2 | 6 | 0 | 2015-01-17 | 3 | 2015-01-31 | 2015-01-31 | 2015-03-02 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | MADRID | MADCTINAS202A | 200000187323 | FAS3140 | 9.8963 | 1 | 5 | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 | TR2014 | 120 | 1 | 6 | 4392.384 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-07 | 2015-03-09 | 3 | 13177.152 | 0 | 0 | 0 | 0 | 13177.152
Yes | No | EMEA | MADRID | MADCTINAS202B | 200000187311 | FAS3140 | 9.9009 | 1 |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 | TR2014 | 120 | 2 | 6 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-07 | 2015-03-09 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Prague | PRGCTINAS201A | 200000067145 | FAS3140 | 5.3491 | 1 | 2.5 | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 | TR2014 | 121 | 1 | 7 | 3662.8 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 10988.4 | 0 | 0 | 0 | 0 | 10988.4
Yes | No | EMEA | Prague | PRGCTINAS201B | 200000066880 | FAS3140 | 5.3491 | 1 |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 | TR2014 | 121 | 2 | 7 | 0 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Prague | PRGCTINAS202A | 200000067808 | FAS3140 | 5.3491 | 1 | 2.5 | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 | TR2014 | 122 | 1 | 7 | 3662.8 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 10988.4 | 0 | 0 | 0 | 0 | 10988.4
Yes | No | EMEA | Prague | PRGCTINAS202B | 200000067810 | FAS3140 | 5.3491 | 1 |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 | TR2014 | 122 | 2 | 7 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Moscow | VKOCTINAS201A | 200000068448 | FAS3160 | 29.731 | 3 | 12.5 | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 | TR2014 | 123 | 1 | 3 | 9329.52 | 2015-01-17 | 7 | 2015-02-28 | 2015-03-14 | 2015-04-13 | 4 | 37318.08 | 0 | 0 | 0 | 0 | 37318.08
Yes | No | EMEA | Moscow | VKOCTINAS201B | 200000067183 | FAS3160 | 29.694 | 3 |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 | TR2014 | 123 | 2 | 3 | 0 | 2015-01-17 | 7 | 2015-02-28 | 2015-03-14 | 2015-04-13 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Moscow | VKOCTINAS202A | 200000066622 | FAS3160 | 29.6031 | 3 | 12.5 | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 | TR2014 | 124 | 1 | 3 | 9329.52 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-21 | 2015-04-20 | 4 | 37318.08 | 0 | 0 | 0 | 0 | 37318.08
Yes | No | EMEA | Moscow | VKOCTINAS202B | 200000066646 | FAS3160 | 29.7168 | 3 |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 | TR2014 | 124 | 2 | 3 | 0 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-21 | 2015-04-20 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Warsaw | wswctinas201a | 20004838 | FAS3040 | 3.3405 | 1 | 2.5 | 2014-04-06 | 2532.05 | 1 | 24307.68 | Poland |  | na | TR2014 | 125 | 1 | 9 | 2025.64 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 6076.92 | 0 | 0 | 0 | 0 | 6076.92
Yes | No | EMEA | Warsaw | wswctinas201b | 20004839 | FAS3040 | 3.3396 | 1 |  | 2014-04-06 |  |  |  | Poland |  | na | TR2014 | 125 | 2 | 9 | 0 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Warsaw | wswctinas202a | 20004840 | FAS3040 | 3.3325 | 1 | 2.5 | 2014-04-06 | 2532.05 | 1 | 24307.68 | Poland |  | na | TR2014 | 126 | 1 | 9 | 2025.64 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 6076.92 | 0 | 0 | 0 | 0 | 6076.92
Yes | No | EMEA | Warsaw | wswctinas202b | 20004841 | FAS3040 | 3.3326 | 1 |  | 2014-04-06 |  |  |  | Poland |  | na | TR2014 | 126 | 2 | 9 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | EMEA | Milano | MILCTINAS401A | 200000250508 | FAS3140 | 3.4019 |  |  | 2015-01-30 | 3221.26 | 1 | 30924.096 | Italy |  | 2017-03-31 | TR2014 |  |  |  | 2577.008
No | Yes | EMEA | Milano | MILCTINAS401B | 200000250493 | FAS3140 | 1.6682 |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 | TR2014 |  |  |  | 0
No | Yes | EMEA | Milano | MILCTINAS402A | 200000245395 | FAS3140 | 2.6424 |  |  | 2015-01-30 | 3221.26 | 1 | 30924.096 | Italy |  | 2017-03-31 | TR2014 |  |  |  | 2577.008
No | Yes | EMEA | Milano | MILCTINAS402B | 200000245266 | FAS3140 | 1.7417 |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 | TR2014 |  |  |  | 0
Formulas:
Scheduled Start = (MAX(X4:X324)*7)+[Project Start Date]
Scheduled Start = (([Scheduled Week Number]*7)-7)+[Project Start Date]
Scheduled Finished = ((([Number of Weekends for Waves]*7))-7)+[Scheduled Start]
Decomm Date = [Scheduled Finished]+30
Decomm Date = (([Scheduled Week Number]*7)-7)+[Project Start Date]

## NAS Migrations Q4 2013
Costs Based on Start: |  | 2015-01-01 | Start Date : | 2015-01-17 |  | Copy Rate Estimate: |  | 1 | TB every | 3.2 | Hours |  | Copy Window Max : |  | 12 | Hours |  | Wave Data Per Weekend : |  | 14 | TB
[22 empty] | Schedule | [5 empty] | Cost Estimates
In Scope | VM | Geo | City | Host Name | Serial# | System | Used Capacity | Number of Weekends for Waves | Data Movement | HW Exp | List Price | Months | Extend to Dec 31, 2015 | Country | State | EOL | TR Details | Cluster # | Partner # | Priority | Monthly Maintenance | Project Start Date | Scheduled Week Number | Scheduled Start | Scheduled Finished | Decomm Date | Estimated Months to Cut Over | Estimated Maintenance Costs | Resource Cost | Private Network Costs | Cable Costs | Copy Server Costs | Total Costs
Yes | No | Americas | 390 Greenwich | nasny152dr | 700000039136 | FAS3140 | 30.03 | 3 | 12.5 | 2014-12-31 | 13197.8 | 1 | 126698.88 | United States | NY | 2017-03-31 | TR2013 | 33 | 1 | 6 | 10558.24 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-25 | 2015-05-25 | 5 | 52791.2 | 0 | 0 | 0 | 0 | 52791.2
Yes | No | Americas | 390 Greenwich | nasny153dr | 700000039148 | FAS3140 | 30.75 | 3 | 12.5 | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 33 | 2 | 6 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-25 | 2015-05-25 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD115DR | 700000180313 | FAS3140 | 7.23 | 1 | 3.75 | 2014-12-31 | 11800.78 | 1 | 113287.488 | United States | TX | 2017-03-31 | TR2013 | 34 | 1 | 13 | 9440.624 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 47203.12 | 0 | 0 | 0 | 0 | 47203.12
Yes | No | Americas | Roanoke | NASSWD116DR | 700000180325 | FAS3140 | 8.02 | 1 | 3.75 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 34 | 2 | 13 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD117DR | 700000187581 | FAS3140 | 6.12 | 1 | 2.5 | 2014-12-31 | 9369.96 | 1 | 89951.616 | United States | TX | 2017-03-31 | TR2013 | 35 | 1 | 24 | 7495.968 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 37479.84 | 0 | 0 | 0 | 0 | 37479.84
Yes | No | Americas | Roanoke | NASSWD118DR | 700000187593 | FAS3140 | 17.19 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 35 | 2 | 24 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD009 | 700000180143 | FAS3140 | 7.19 | 1 | 3.75 | 2014-12-31 | 11800.78 | 1 | 113287.488 | United States | OH | 2017-03-31 | TR2013 | 36 | 1 | 13 | 9440.624 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 28321.872 | 0 | 0 | 0 | 0 | 28321.872
Yes | No | Americas | Delaware | NASMWD010 | 700000180131 | FAS3140 | 7.98 | 1 | 3.75 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 36 | 2 | 13 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD011 | 700000180909 | FAS3140 | 26.55 | 2 | 11.25 | 2014-12-31 | 14940.42 | 1 | 143428.032 | United States | OH | 2017-03-31 | TR2013 | 37 | 1 | 2 | 11952.336 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-14 | 2015-03-16 | 3 | 35857.008 | 0 | 0 | 0 | 0 | 35857.008
Yes | No | Americas | Delaware | NASMWD012 | 700000180911 | FAS3140 | 23.51 | 2 | 10 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 37 | 2 | 2 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Tucson | NASTUS103 | 700000174560 | FAS2020 | 0.98 | 1 | 1.25 | 2014-12-31 | 960.54 | 1 | 9221.184 | United States | AZ | 2017-06-17 | TR2014 | 38 | 1 | 91 | 768.432 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1536.864 | 0 | 0 | 0 | 0 | 1536.864
Yes | No | Americas | Tucson | NASTUS104 | 700000174716 | FAS2020 | 0.4 | 1 | 1.25 | 2014-12-31 |  |  |  | United States | AZ | 2017-06-17 | TR2014 | 38 | 2 | 91 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD109DR | 70002136 | FAS3140 | 14.54 | 2 | 6.25 | 2014-12-31 | 10122.32 | 1 | 97174.272 | United States | TX | 2017-03-31 | TR2013 | 39 | 1 | 20 | 8097.856 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 40489.28 | 0 | 0 | 0 | 0 | 40489.28
Yes | No | Americas | Roanoke | NASSWD110DR | 70002137 | FAS3140 | 9.64 | 1 | 5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 39 | 2 | 20 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD031VM | 700000312318 | FAS3170 |  |  |  | 2014-12-31 | 10561.18 | 1 | 101387.328 | United States | OH | 2017-03-31 | TR2013 | 17 | 1 | 17 | 8448.944 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD032VM | 700000312306 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 17 | 2 | 17 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd015vm | 700000124620 | FAS3170 |  |  |  | 2014-12-31 | 9907.16 | 1 | 95108.736 | United States | OH | 2017-03-31 | TR2014 | 5 | 1 | 23 | 7925.728 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd016vm | 700000124618 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 5 | 2 | 23 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd013vm | 700000127775 | FAS3170 |  |  |  | 2014-12-31 | 8953.16 | 1 | 85950.336 | United States | OH | 2017-03-31 | TR2014 | 32 | 1 | 25 | 7162.528 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd014vm | 700000127787 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 32 | 2 | 25 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD033VM | 700000450172 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | OH | 2017-03-31 | TR2013 | 24 | 1 | 38 | 5832.912 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD034VM | 700000450160 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 24 | 2 | 38 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd009vm | 700000066983 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | OH | 2017-03-31 | TR2013 | 30 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | nasmwd010vm | 700000161628 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 30 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY013VM | 700000378362 | FAS3170 |  |  |  | 2014-12-31 | 6961.16 | 1 | 66827.136 | United States | NY | 2017-03-31 | TR2013 | 19 | 1 | 43 | 5568.928 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY014VM | 700000378374 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 19 | 2 | 43 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY015VM | 700000184199 | FAS3170 |  |  |  | 2014-12-31 | 6961.16 | 1 | 66827.136 | United States | NY | 2017-03-31 | TR2013 | 20 | 1 | 43 | 5568.928 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | NASNY016VM | 700000184204 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 20 | 2 | 43 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD021VM | 30028280 | FAS3170 |  |  |  | 2014-12-31 | 6937.16 | 1 | 66596.736 | United States | OH | 2017-03-31 | TR2013 | 8 | 1 | 44 | 5549.728 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD022VM | 700000270625 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 8 | 2 | 44 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD023VM | 700000177237 | FAS3170 |  |  |  | 2014-12-31 | 6937.16 | 1 | 66596.736 | United States | OH | 2017-03-31 | TR2013 | 9 | 1 | 44 | 5549.728 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD024VM | 700000177249 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 9 | 2 | 44 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD025VM | 700000175461 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2013 | 10 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD026VM | 700000175459 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 10 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD027VM | 700000175447 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2013 | 11 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD028VM | 700000175423 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 11 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD017VM | 700000177251 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2014 | 6 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD018VM | 700000184345 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 6 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD019VM | 700000177299 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | OH | 2017-03-31 | TR2014 | 7 | 1 | 50 | 5026.512 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD020VM | 700000177304 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2014 | 7 | 2 | 50 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | nasny009vm | 700000048979 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | NY | 2017-03-31 | TR2013 | 27 | 1 | 53 | 4834.496 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | 390 Greenwich | nasny010vm | 700000048981 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 27 | 2 | 53 | 0 | 2015-01-17 |  | 2014-09-27 |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD029VM | 700000329000 | FAS3170 |  |  |  | 2014-12-31 | 5653.14 | 1 | 54270.144 | United States | OH | 2017-03-31 | TR2013 | 18 | 1 | 57 | 4522.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Delaware | NASMWD030VM | 700000328991 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 18 | 2 | 57 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | 390 Greenwich | NY4-3270-2 | 700000729004 | FAS3270 |  |  |  | 2015-07-31 | 13446.76 | 1 | 53787.04 | United States | NY | 2018-12-31 |  |  |  |  | 4482.2533 |  |  | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | 390 Greenwich | NY4-3270-1 | 700000729016 | FAS3270 |  |  |  | 2015-07-31 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 |  |  | 2014-09-27 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | ALCOBENDAS | MADCTINAS201A | 200000187294 | FAS3140 |  |  |  | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 |  |  |  |  | 4392.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | ALCOBENDAS | MADCTINAS201B | 200000187309 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Ann Arbor | nasaam100 | 3086762 | FAS3020 |  |  |  | 2014-10-31 | 1347 | 1 |  | United States | MI | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Ann Arbor | nasaam101 | 3086763 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | MI | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas201a | 20007947 | FAS3040 |  |  |  | 2014-04-30 | 3973.12 | 1 |  | Spain |  | 2014-04-11 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas201b | 20005889 | FAS3040 |  |  |  | 2014-04-30 |  |  |  | Spain |  | 2014-04-12 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas202a | 20008796 | FAS3040 |  |  |  | 2014-04-30 | 3973.12 | 1 |  | Spain |  | 2014-04-13 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Barcelona | bcnctinas202b | 20008793 | FAS3040 |  |  |  | 2014-04-30 |  |  |  | Spain |  | 2014-04-14 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNASDR001 | 700000713598 | FAS2040 |  |  |  | 2015-09-30 | 2383.44 | 1 | 3813.504 | Columbia |  | 2015-12-10 |  |  |  |  | 317.792 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNAS002 | 700000714528 | FAS2040 |  |  |  | 2015-09-30 |  |  |  | Columbia |  | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLNAS001 | 700000713603 | FAS2040 |  |  |  | 2015-09-30 | 1903.66 | 1 | 3045.856 | Columbia |  | 2015-12-10 |  |  |  |  | 253.8213 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Bogota | LACCOLBOGDR031 | 700000714516 | FAS2040 |  |  |  | 2015-09-30 |  |  |  | Columbia |  | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas201a | 200000002054 | FAS3140 |  |  |  | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 |  |  |  |  | 3298.016 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas201b | 200000002028 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas202a | 200000001995 | FAS3140 |  |  |  | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 |  |  |  |  | 3298.016 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Budapest | budctinas202b | 200000002016 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | nasmwd011vm | 700000044959 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | OH | 2017-03-31 |  |  |  |  | 4834.496 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | nasmwd012vm | 700000044961 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | NASMWD037VM | 700000596914 | FAS3170 |  |  |  | 2015-04-30 | 9541.94 | 1 | 61068.416 | United States | OH | 2017-03-31 |  |  |  |  | 5089.0347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Delaware | NASMWD038VM | 700000596926 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd001 | 3091333 | FAS3050 |  |  |  | 2014-10-31 | 4122.52 | 1 |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd002 | 3091332 | FAS3050 |  |  |  | 2014-10-31 |  |  |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd007 | 3089909 | FAS3020 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | nasmwd008 | 3089910 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | OH | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD013 | 700000334794 | FAS3140 |  |  |  | 2014-12-31 | 5889.9 | 1 | 56543.04 | United States | OH | 2017-03-31 |  |  |  |  | 4711.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD014 | 700000334782 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD005DR | 700000382387 | FAS3140 |  |  |  | 2014-12-31 | 10111.96 | 1 | 97074.816 | United States | OH | 2017-03-31 |  |  |  |  | 8089.568 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD006DR | 700000382399 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD007DR | 700000380133 | FAS3140 |  |  |  | 2014-12-31 | 2928.28 | 1 | 28111.488 | United States | OH | 2017-03-31 |  |  |  |  | 2342.624 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD008DR | 700000380121 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD001S | 700000515350 | FAS3140 |  |  |  | 2015-01-30 | 3132.06 | 1 | 27562.128 | United States | OH | 2017-03-31 |  |  |  |  | 2296.844 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD002S | 700000515348 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD003S | 700000517009 | FAS3140 |  |  |  | 2015-01-30 | 7634.16 | 1 | 67180.608 | United States | OH | 2017-03-31 |  |  |  |  | 5598.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD004S | 700000517011 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD009DR | 700000567004 | FAS3140 |  |  |  | 2015-03-31 | 4468.54 | 1 | 32173.488 | United States | OH | 2017-03-31 |  |  |  |  | 2681.124 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD010DR | 700000566995 | FAS3140 |  |  |  | 2015-03-31 |  |  |  | United States | OH | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF7001A | 700000655057 | FAS3210 |  |  |  | 2015-04-30 | 3518.5 | 1 | 22518.4 | United States | OH | 2018-12-31 |  |  |  |  | 1876.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF7001B | 700000655069 | FAS3210 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | GTDCTINASF8002A | 700000634821 | FAS3240 |  |  |  | 2015-04-30 | 2592.02 | 1 | 16588.928 | United States | OH | 2018-12-31 |  |  |  |  | 1382.4107 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1001A | 700000638451 | FAS3240 |  |  |  | 2015-04-30 | 11485.64 | 1 | 73508.096 | United States | OH | 2018-12-31 |  |  |  |  | 6125.6747 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1001B | 700000638449 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1005A | 700000638487 | FAS3240 |  |  |  | 2015-04-30 | 12242.6 | 1 | 78352.64 | United States | OH | 2018-12-31 |  |  |  |  | 6529.3867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1005B | 700000638499 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1006A | 940000062595 | FAS3240 |  |  |  | 2015-04-30 | 10287.6 | 1 | 65840.64 | United States | OH | 2018-12-31 |  |  |  |  | 5486.72 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1006B | 700000647220 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1007A | 940001048778 | FAS3240 |  |  |  | 2015-04-30 | 10728.68 | 1 | 68663.552 | United States | OH | 2018-12-31 |  |  |  |  | 5721.9627 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF1007B | 700000635344 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8001A | 700000934453 | FAS3240 |  |  |  | 2015-04-30 | 2097.04 | 1 | 13421.056 | United States | OH | 2018-12-31 |  |  |  |  | 1118.4213 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8001B | 500000245690 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8002A | 850000089803 | FAS3240 |  |  |  | 2015-04-30 | 5138.98 | 1 | 32889.472 | United States | OH | 2018-12-31 |  |  |  |  | 2740.7893 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF8002B | 940000041242 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD011DR | 700000668925 | FAS3240 |  |  |  | 2015-05-31 | 10728.68 | 1 | 60080.608 | United States | OH | 2018-12-31 |  |  |  |  | 5006.7173 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | NASMWD012DR | 700000668913 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | United States | OH | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF4001A | 700000689761 | FAS2040 |  |  |  | 2015-06-30 | 1949.94 | 1 | 9359.712 | United States | OH | 2015-12-10 |  |  |  |  | 779.976 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Delaware | MWDCTINASF4001B | 700000689759 | FAS2040 |  |  |  | 2015-06-30 |  |  |  | United States | OH | 2015-12-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS401A | 20025965 | FAS3070 |  |  |  | 2014-03-31 | 6766.18 | 1 |  | Germany |  | 2014-04-01 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS401B | 20025966 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-02 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS501A | 20016003 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-03 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS501B | 20016351 | FAS3070 |  |  |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-04 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas503s | 200000007365 | FAS3140 |  |  |  | 2014-06-30 | 3084.24 | 1 | 29608.704 | Germany |  | 2017-03-31 |  |  |  |  | 2467.392 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS405A | 200000181276 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | Germany |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS405B | 200000179728 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas402a | 200000034942 | FAS3170 |  |  |  | 2014-12-31 | 8587.56 | 1 | 82440.576 | Germany |  | 2017-03-31 |  |  |  |  | 6870.048 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas402b | 200000088278 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas505a | 200000135837 | FAS3170 |  |  |  | 2014-12-31 | 11028.42 | 1 | 105872.832 | Germany |  | 2017-03-31 |  |  |  |  | 8822.736 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | fractinas505b | 200000136013 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS504A | 200000035063 | FAS3170 |  |  |  | 2014-12-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2017-03-31 |  |  |  |  | 10151.312 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Frankfurt | FRACTINAS504B | 200000035099 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut152 | 70000916 | FAS3170 | 15.23 | 2 | 6.25 | 2014-12-31 | 12385.78 | 1 | 118903.488 | United States | NJ | 2017-03-31 | TR2013 | 40 | 1 | 11 | 9908.624 | 2015-01-17 | 10 | 2015-03-21 | 2015-03-28 | 2015-04-27 | 4 | 39634.496 | 0 | 0 | 0 | 0 | 39634.496
Yes | No | Americas | Rutherford | nasrut153 | 70000917 | FAS3170 | 9.38 | 2 | 3.75 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 40 | 2 | 11 | 0 | 2015-01-17 | 10 | 2015-03-21 | 2015-03-28 | 2015-04-27 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut154 | 70000914 | FAS3170 | 8.79 | 2 | 3.75 | 2014-12-31 | 13706.22 | 1 | 131579.712 | United States | NJ | 2017-03-31 | TR2013 | 41 | 1 | 5 | 10964.976 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-14 | 2015-04-13 | 4 | 43859.904 | 0 | 0 | 0 | 0 | 43859.904
Yes | No | Americas | Rutherford | nasrut155 | 70000915 | FAS3170 | 16.39 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 41 | 2 | 5 | 0 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-14 | 2015-04-13 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Georgetown | nasgtd005vm | 700000024387 | FAS3170 |  |  |  | 2014-12-31 | 5458.12 | 1 | 52397.952 | United States | TX | 2017-03-31 | TR2014 | 4 | 1 | 61 | 4366.496 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Georgetown | nasgtd006vm | 700000024399 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 4 | 2 | 61 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | nasgtd001 | 30019701 | FAS3040 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | nasgtd002 | 30019702 | FAS3040 |  |  |  | 2014-10-31 |  |  |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | NASGTD001S | 800000006387 | FAS3140 |  |  |  | 2014-12-31 | 7095.42 | 1 | 68116.032 | United States | TX | 2017-03-31 |  |  |  |  | 5676.336 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8001A | 700000398269 | FAS3170 |  |  |  | 2015-04-30 | 8262.25 | 1 | 52878.4 | United States | TX | 2017-03-31 |  |  |  |  | 4406.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8001B | 700000591263 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Georgetown | GTDCTINASF8002B | 700000488492 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Jardines | MEXCTINASF8001B | 940001037365 | FAS3240 |  |  |  | 2015-05-31 | 5123.94 | 1 | 28694.064 | Mexico |  | 2018-12-31 |  |  |  |  | 2391.172 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Jardines | MEXCTINASF8001A | 940001037078 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | Mexico |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS201A | 30003866 | FAS3040 |  |  |  | 2014-03-31 | 2342.52 | 1 |  | Pakistan |  | 2014-04-05 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS201B | 30003867 | FAS3040 |  |  |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-06 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS202A | 30001777 | FAS3040 |  |  |  | 2014-03-31 | 2015.82 | 1 |  | Pakistan |  | 2014-04-07 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Karachi | KHICTINAS202B | 1088268 | FAS3040 |  |  |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-08 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS501A | 20016347 | FAS3070 |  |  |  | 2014-04-30 | 10846.61 | 1 |  | United Kingdom |  | 2014-04-09 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS501B | 20016346 | FAS3070 |  |  |  | 2014-04-30 |  |  |  | United Kingdom |  | 2014-04-10 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS503S | 200000009052 | FAS3140 |  |  |  | 2014-06-30 | 3084.24 | 1 | 29608.704 | United Kingdom |  | 2017-03-31 |  |  |  |  | 2467.392 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS402A | 200000203907 | FAS3170 |  |  |  | 2014-09-30 | 6812.54 | 1 | 65400.384 | United Kingdom |  | 2017-03-31 |  |  |  |  | 5450.032 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS402B | 200000203919 | FAS3170 |  |  |  | 2014-09-30 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS209A | 200000069117 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS209B | 200000068993 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS210A | 200000069105 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS210B | 200000062004 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS505A | 200000152031 | FAS3170 |  |  |  | 2014-12-31 | 11028.42 | 1 | 105872.832 | United Kingdom |  | 2017-03-31 |  |  |  |  | 8822.736 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS505B | 200000151049 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas504a | 200000043917 | FAS3170 |  |  |  | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 |  |  |  |  | 11011.456 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas504b | 200000043905 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS401A | 200000153724 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | United Kingdom |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS401B | 200000155356 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS403A | 200000154376 | FAS3170 |  |  |  | 2014-12-31 | 7518.88 | 1 | 72181.248 | United Kingdom |  | 2017-03-31 |  |  |  |  | 6015.104 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS403B | 200000154388 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS302A | 200000007420 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS302B | 200000007547 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS301A | 200000005197 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS301B | 200000002638 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS304A | 200000005056 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS304B | 200000005185 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS303A | 200000005020 | FAS3140 |  |  |  | 2015-01-31 | 5490.48 | 1 | 48316.224 | United Kingdom |  | 2017-03-31 |  |  |  |  | 4026.352 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS303B | 200000004997 | FAS3140 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS207A | 200000002975 | FAS3170 |  |  |  | 2015-01-31 | 13764.32 | 1 | 121126.016 | United Kingdom |  | 2017-03-31 |  |  |  |  | 10093.8347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINAS207B | 200000002963 | FAS3170 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas208a | 200000002913 | FAS3170 |  |  |  | 2015-01-31 | 13764.32 | 1 | 121126.016 | United Kingdom |  | 2017-03-31 |  |  |  |  | 10093.8347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinas208b | 200000001543 | FAS3170 |  |  |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4006a | 850000065742 | FAS3240 |  |  |  | 2015-07-31 | 4720.66 | 1 | 18882.64 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1573.5533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4006b | 700001088706 | FAS3240 |  |  |  | 2015-07-31 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4007a | 940000068484 | FAS3240 |  |  |  | 2015-07-31 | 4720.66 | 1 | 18882.64 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1573.5533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | ldnctinasf4007b | 200000567107 | FAS3240 |  |  |  | 2015-07-31 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6003A | 200000377916 | FAS3240 |  |  |  | 2015-11-30 | 5398.78 | 1 | 4319.024 | United Kingdom |  | 2018-12-31 |  |  |  |  | 359.9187 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6003B | 200000431736 | FAS3240 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6004A | 200000435471 | FAS3240 |  |  |  | 2015-11-30 | 5876.54 | 1 | 4701.232 | United Kingdom |  | 2018-12-31 |  |  |  |  | 391.7693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF6004B | 200000435483 | FAS3240 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2011A | 200000436736 | FAS3270 |  |  |  | 2015-11-30 | 15488.02 | 1 | 12390.416 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1032.5347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2011B | 200000439544 | FAS3270 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2012A | 200000430976 | FAS3270 |  |  |  | 2015-11-30 | 15488.02 | 1 | 12390.416 | United Kingdom |  | 2018-12-31 |  |  |  |  | 1032.5347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | London | LDNCTINASF2012B | 200000430964 | FAS3270 |  |  |  | 2015-11-30 |  |  |  | United Kingdom |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | MADRID | MADCTINAS202A | 200000187323 | FAS3140 |  |  |  | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 |  |  |  |  | 4392.384 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | MADRID | MADCTINAS202B | 200000187311 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Mexico City | UNKNOWN | 700000173152 | FAS3140 |  |  |  | 2014-03-31 | 1179.14 | 1 | 11319.744 | Mexico |  | 2017-03-31 |  |  |  |  | 943.312 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Mexico City | UNKNOWN | 700000173164 | FAS3140 |  |  |  | 2014-03-31 |  |  |  | Mexico |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS401A | 200000250508 | FAS3140 |  |  |  | 2015-01-30 | 3221.26 | 1 | 28347.088 | Italy |  | 2017-03-31 |  |  |  |  | 2362.2573 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS401B | 200000250493 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS402A | 200000245395 | FAS3140 |  |  |  | 2015-01-30 | 3221.26 | 1 | 28347.088 | Italy |  | 2017-03-31 |  |  |  |  | 2362.2573 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Milano | MILCTINAS402B | 200000245266 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Monterrey | mtyctinasf8001b | 940001036579 | FAS3240 |  |  |  | 2015-05-31 | 5123.94 | 1 | 28694.064 | Mexico |  | 2018-12-31 |  |  |  |  | 2391.172 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Monterrey | mtyctinasf8001a | 940001038010 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | Mexico |  | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS201A | 200000068448 | FAS3160 |  |  |  | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 |  |  |  |  | 9329.52 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS201B | 200000067183 | FAS3160 |  |  |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS202A | 200000066622 | FAS3160 |  |  |  | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 |  |  |  |  | 9329.52 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Moscow | VKOCTINAS202B | 200000066646 | FAS3160 |  |  |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | NASSWD111DR | 70002138 | FAS3170 | 123.74 | 9 | 48.75 | 2014-12-31 | 18584.64 | 1 | 178412.544 | United States | TX | 2017-03-31 | TR2013 | 42 | 1 | 1 | 14867.712 | 2015-01-17 | 0 | 2015-04-11 | 2015-06-06 | 2015-07-06 | 7 | 104073.984 | 0 | 0 | 0 | 0 | 104073.984
Yes | No | Americas | Roanoke | NASSWD112DR | 70002139 | FAS3170 | 101.32 | 9 | 40 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 42 | 2 | 1 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-06-06 | 2015-07-06 | 7 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | NEW YORK | NASNY011VM | 700000304995 | FAS3170 |  |  |  | 2014-12-31 | 7969.16 | 1 | 76503.936 | United States | NY | 2017-03-31 | TR2013 | 14 | 1 | 31 | 6375.328 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | NEW YORK | NASNY012VM | 700000305004 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2013 | 14 | 2 | 31 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | NASNY001 | 700000516940 | FAS3140 |  |  |  | 2015-01-30 | 4431.42 | 1 | 38996.496 | United States | NY | 2017-03-31 |  |  |  |  | 3249.708 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | NASNY002 | 700000516952 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | NY | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1003a | 940001037092 | FAS3240 |  |  |  | 2015-04-30 | 9883.96 | 1 | 63257.344 | United States | NY | 2018-12-31 |  |  |  |  | 5271.4453 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1003b | 700000633736 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1004a | 700000639364 | FAS3240 |  |  |  | 2015-04-30 | 11397.88 | 1 | 72946.432 | United States | NY | 2018-12-31 |  |  |  |  | 6078.8693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | NEW YORK | nycctinasf1004b | 700000639376 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NY | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Georgetown | GTDCTINASF1008A | 700000270560 | FAS3140 | 0.87296 | 1 |  | 2014-12-31 | 3476.88 | 1 | 33378.048 | United States | TX | 2017-03-31 | TR2014 | 43 | 1 | 70 | 2781.504 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 5563.008 | 0 | 0 | 0 | 0 | 5563.008
Yes | No | Americas | Georgetown | GTDCTINASF1008B | 700000270572 | FAS3140 | 3.0086 | 1 |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 43 | 2 | 70 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | O'Fallon | NASSTL003VM | 700000278809 | FAS3170 |  |  |  | 2014-12-31 | 9931.18 | 1 | 95339.328 | United States | MO | 2017-03-31 | TR2013 | 15 | 1 | 22 | 7944.944 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | O'Fallon | NASSTL004VM | 700000278811 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | MO | 2017-03-31 | TR2013 | 15 | 2 | 22 | 0 | 2015-01-17 | 1 |  |  | 2015-01-17 | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | nasstl16 | 3087450 | FAS3050 |  |  |  | 2014-10-31 | 4122.52 | 1 | 39576.192 | United States | MO | [5 empty] | 3298.016 |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | nasstl17 | 3087451 | FAS3050 |  |  |  | 2014-10-31 |  |  |  | United States | MO | [5 empty] | 0 |  | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | NASSTL003 | 700000592035 | FAS3170 |  |  |  | 2015-04-30 | 18353.42 | 1 | 117461.888 | United States | MO | 2017-03-31 |  |  |  |  | 9788.4907 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | O'Fallon | NASSTL004 | 700000592047 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | MO | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Georgetown | NASGTD007 | 700000262915 | FAS3140 | 3.6997 | 1 |  | 2014-12-31 | 4222.4 | 1 | 40535.04 | United States | TX | 2017-03-31 | TR2014 | 44 | 1 | 66 | 3377.92 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6755.84 | 0 | 0 | 0 | 0 | 6755.84
Yes | No | Americas | Georgetown | NASGTD008 | 700000262927 | FAS3140 | 3.8509 | 1 |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 44 | 2 | 66 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS202A | 200000067808 | FAS3140 |  |  |  | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 |  |  |  |  | 3662.8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS202B | 200000067810 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS201A | 200000067145 | FAS3140 |  |  |  | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 |  |  |  |  | 3662.8 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | EMEA | Prague | PRGCTINAS201B | 200000066880 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | CHICAGO | NASCHI06 | 600000015114 | FAS2020 | 2.2301 | 1 |  | 2014-12-31 | 1210.4 | 1 | 11619.84 | United States | IL | 2017-06-17 | TR2014 | 45 | 1 | 88 | 968.32 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1936.64 | 0 | 0 | 0 | 0 | 1936.64
Yes | No | Americas | CHICAGO | NASCHI05 | 700000302959 | FAS2020 | 3.95 | 1 |  | 2014-12-31 |  |  |  | United States | IL | 2017-06-17 | TR2014 | 45 | 2 | 88 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | CHICAGO | NASCHI08 | 600000014744 | FAS2020 | 0.88 | 1 | 1.25 | 2014-12-31 | 788.2 | 1 | 7566.72 | United States | IL | 2017-06-17 | TR2013 | 46 | 1 | 92 | 630.56 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1261.12 | 0 | 0 | 0 | 0 | 1261.12
Yes | No | Americas | CHICAGO | NASCHI07 | 700000295429 | FAS2020 | 0.88 | 1 | 1.25 | 2014-12-31 |  |  |  | United States | IL | 2017-06-17 | TR2013 | 46 | 2 | 92 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | SAN FRANCISCO | NASSFR04 | 600000007856 | FAS2020 | 2.3278 | 1 |  | 2014-12-31 | 1347 | 1 | 12931.2 | United States | CA | 2017-06-17 | TR2014 | 47 | 1 | 86 | 1077.6 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 2155.2 | 0 | 0 | 0 | 0 | 2155.2
Yes | No | Americas | SAN FRANCISCO | NASSFR03 | 700000293213 | FAS2020 | 2.1042 | 1 |  | 2014-12-31 |  |  |  | United States | CA | 2017-06-17 | TR2014 | 47 | 2 | 86 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | nasswd113dr | 700000109826 | FAS3140 | 13.36 | 1 | 6.25 | 2014-12-31 | 12407.18 | 1 | 119108.928 | United States | TX | 2017-03-31 | TR2013 | 48 | 1 | 10 | 9925.744 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-11 | 2015-05-11 | 5 | 49628.72 | 0 | 0 | 0 | 0 | 49628.72
Yes | No | Americas | Roanoke | nasswd114dr | 70004739 | FAS3140 | 19.2 | 2 | 7.5 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 48 | 2 | 10 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Delaware | NASMWD003DR | 700000017827 | FAS3140 | 24.08 | 2 | 10 | 2014-12-31 | 12829.4 | 1 | 123162.24 | United States | OH | 2017-03-31 | TR2013 | 49 | 1 | 7 | 10263.52 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 51317.6 | 0 | 0 | 0 | 0 | 51317.6
Yes | No | Americas | Delaware | NASMWD004DR | 80002155 | FAS3140 | 23.23 | 2 | 10 | 2014-12-31 |  |  |  | United States | OH | 2017-03-31 | TR2013 | 49 | 2 | 7 | 0 | 2015-01-17 | 0 | 2015-04-11 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Rutherford | nasrut156 | 700000038754 | FAS3140 | 39.3 | 3 | 16.25 | 2014-12-31 | 14940.42 | 1 | 143428.032 | United States | NJ | 2017-03-31 | TR2013 | 50 | 1 | 2 | 11952.336 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-21 | 2015-03-23 | 3 | 35857.008 | 0 | 0 | 0 | 0 | 35857.008
Yes | No | Americas | Rutherford | nasrut157 | 700000038766 | FAS3140 | 35.13 | 3 | 13.75 | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 50 | 2 | 2 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd017vm | 700000128884 | FAS3170 |  |  |  | 2014-12-31 | 10261.16 | 1 | 98507.136 | United States | TX | 2017-03-31 | TR2014 | 31 | 1 | 19 | 8208.928 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd018vm | 700000128896 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 31 | 2 | 19 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD027VM | 700000313790 | FAS3170 |  |  |  | 2014-12-31 | 9931.18 | 1 | 95339.328 | United States | TX | 2017-03-31 | TR2013 | 13 | 1 | 22 | 7944.944 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD028VM | 700000313805 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 13 | 2 | 22 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd015vm | 700000047274 | FAS3170 |  |  |  | 2014-12-31 | 8659.14 | 1 | 83127.744 | United States | TX | 2017-03-31 | TR2013 | 29 | 1 | 26 | 6927.312 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd016vm | 700000066969 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 29 | 2 | 26 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD019VM | 700000124656 | FAS3170 |  |  |  | 2014-12-31 | 7945.16 | 1 | 76273.536 | United States | TX | 2017-03-31 | TR2014 | 1 | 1 | 32 | 6356.128 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD020VM | 700000124668 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2014 | 1 | 2 | 32 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD025VM | 700000313855 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 12 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD026VM | 700000313867 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 12 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD029VM | 700000180105 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 21 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD030VM | 700000450158 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 21 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD031VM | 700000446341 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | TX | 2017-03-31 | TR2013 | 22 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD032VM | 700000446353 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 22 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD021VM | 700000142701 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | TX | 2017-03-31 | TR2013 | 2 | 1 | 50 | 5026.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD022VM | 700000172794 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 2 | 2 | 50 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD023VM | 700000155942 | FAS3170 |  |  |  | 2014-12-31 | 6283.14 | 1 | 60318.144 | United States | TX | 2017-03-31 | TR2013 | 3 | 1 | 50 | 5026.512 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | NASSWD024VM | 700000172548 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 3 | 2 | 50 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd011vm | 30020787 | FAS3170 |  |  |  | 2014-12-31 | 4675.12 | 1 | 44881.152 | United States | TX | 2017-03-31 | TR2013 | 26 | 1 | 64 | 3740.096 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Roanoke | nasswd012vm | 700000047286 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 26 | 2 | 64 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD033VM | 700000571249 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | TX | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD034VM | 700000571251 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD037VM | 700000571627 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | TX | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD038VM | 700000571639 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD039VM | 700000593089 | FAS3170 |  |  |  | 2015-04-30 | 9541.94 | 1 | 61068.416 | United States | TX | 2017-03-31 |  |  |  |  | 5089.0347 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | Americas | Roanoke | NASSWD040VM | 700000593077 | FAS3170 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | nasswd105dr | 3082623 | FAS3020 |  |  |  | 2014-10-31 |  |  |  | United States | TX | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD119DR | 700000267886 | FAS3140 |  |  |  | 2014-12-31 | 4222.4 | 1 | 40535.04 | United States | TX | 2017-03-31 |  |  |  |  | 3377.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD120DR | 700000267898 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD121DR | 700000282642 | FAS3140 |  |  |  | 2014-12-31 | 13715.2 | 1 | 131665.92 | United States | TX | 2017-03-31 |  |  |  |  | 10972.16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD122DR | 700000282654 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1008A | 700000271679 | FAS3140 |  |  |  | 2014-12-31 | 3476.88 | 1 | 33378.048 | United States | TX | 2017-03-31 |  |  |  |  | 2781.504 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1008B | 700000271681 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD123DR | 700000334744 | FAS3140 |  |  |  | 2014-12-31 | 5889.9 | 1 | 56543.04 | United States | TX | 2017-03-31 |  |  |  |  | 4711.92 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD124DR | 700000334756 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD004S | 700000515427 | FAS3140 |  |  |  | 2015-01-30 | 3456.06 | 1 | 30413.328 | United States | TX | 2017-03-31 |  |  |  |  | 2534.444 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD005S | 700000515439 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD006S | 700000516988 | FAS3140 |  |  |  | 2015-01-30 | 6194.8 | 1 | 54514.24 | United States | TX | 2017-03-31 |  |  |  |  | 4542.8533 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD007S | 700000516990 | FAS3140 |  |  |  | 2015-01-30 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD27 | 700000566933 | FAS3140 |  |  |  | 2015-03-31 | 4468.54 | 1 | 32173.488 | United States | TX | 2017-03-31 |  |  |  |  | 2681.124 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD28 | 700000566945 | FAS3140 |  |  |  | 2015-03-31 |  |  |  | United States | TX | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF7001A | 700000654900 | FAS3210 |  |  |  | 2015-04-30 | 3518.5 | 1 | 22518.4 | United States | TX | 2018-12-31 |  |  |  |  | 1876.5333 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF7001B | 700000654895 | FAS3210 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1001A | 700000639261 | FAS3240 |  |  |  | 2015-04-30 | 11485.64 | 1 | 73508.096 | United States | TX | 2018-12-31 |  |  |  |  | 6125.6747 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1001B | 700000639273 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1002A | 700000634493 | FAS3240 |  |  |  | 2015-04-30 | 12242.6 | 1 | 78352.64 | United States | TX | 2018-12-31 |  |  |  |  | 6529.3867 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF1002B | 700000634481 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD29 | 700000668937 | FAS3240 |  |  |  | 2015-05-31 | 13756.54 | 1 | 77036.624 | United States | TX | 2018-12-31 |  |  |  |  | 6419.7187 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | NASSWD30 | 700000668949 | FAS3240 |  |  |  | 2015-05-31 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF8001A | 200000299750 | FAS3270 |  |  |  | 2015-10-31 | 9949.92 | 1 | 15919.872 | United States | TX | 2018-12-31 |  |  |  |  | 1326.656 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Roanoke | SWDCTINASF8001B | 700001112791 | FAS3270 |  |  |  | 2015-10-31 |  |  |  | United States | TX | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | O'Fallon | nasstl001 | 700000044234 | FAS3140 | 10.59 | 1 | 5 | 2014-12-31 | 7762.94 | 1 | 74524.224 | United States | MO | 2017-03-31 | TR2013 | 51 | 1 | 33 | 6210.352 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 12420.704 | 0 | 0 | 0 | 0 | 12420.704
Yes | No | Americas | O'Fallon | nasstl002 | 700000044246 | FAS3140 | 12.28 | 1 | 5 | 2014-12-31 |  |  |  | United States | MO | 2017-03-31 | TR2013 | 51 | 2 | 33 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | Roanoke | nasswd17 | 700000067690 | FAS3140 | 16.11 | 2 | 7.5 | 2014-12-31 | 11045.36 | 1 | 106035.456 | United States | TX | 2017-03-31 | TR2013 | 52 | 1 | 15 | 8836.288 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 44181.44 | 0 | 0 | 0 | 0 | 44181.44
Yes | No | Americas | Roanoke | nasswd18 | 700000067705 | FAS3140 | 20.54 | 2 | 8.75 | 2014-12-31 |  |  |  | United States | TX | 2017-03-31 | TR2013 | 52 | 2 | 15 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | NEW YORK | NASNY34 | 700000446523 | FAS3140 | 8.029 | 1 |  | 2014-12-31 | 6360.52 | 1 | 61060.992 | United States | NY | 2017-03-31 | TR2014 | 53 | 1 | 49 | 5088.416 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 10176.832 | 0 | 0 | 0 | 0 | 10176.832
Yes | No | Americas | NEW YORK | NASNY35 | 700000446535 | FAS3140 | 12.8194 | 1 |  | 2014-12-31 |  |  |  | United States | NY | 2017-03-31 | TR2014 | 53 | 2 | 49 | 0 | 2015-01-17 | 2 | 2015-01-24 | 2015-01-24 | 2015-02-23 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | NASRUT007VM | 700000312069 | FAS3170 |  |  |  | 2014-12-31 | 7969.16 | 1 | 76503.936 | United States | NJ | 2017-03-31 | TR2013 | 16 | 1 | 31 | 6375.328 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | NASRUT008VM | 700000312071 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 16 | 2 | 31 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut009vm | 700000446169 | FAS3170 |  |  |  | 2014-12-31 | 7291.14 | 1 | 69994.944 | United States | NJ | 2017-03-31 | TR2013 | 23 | 1 | 38 | 5832.912 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut010vm | 700000558778 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 23 | 2 | 38 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut003vm | 700000044325 | FAS3170 |  |  |  | 2014-12-31 | 6043.12 | 1 | 58013.952 | United States | NJ | 2017-03-31 | TR2014 | 25 | 1 | 53 | 4834.496 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut004vm | 700000044337 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2014 | 25 | 2 | 53 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut005vm | 700000055594 | FAS3170 |  |  |  | 2014-12-31 | 4675.12 | 1 | 44881.152 | United States | NJ | 2017-03-31 | TR2013 | 28 | 1 | 64 | 3740.096 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
Yes | Yes | Americas | Rutherford | nasrut006vm | 700000055609 | FAS3170 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 | TR2013 | 28 | 2 | 64 | 0 | 2015-01-17 |  |  |  |  | #REF! | #REF! | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | nasrut150 | 30007433 | FAS3040 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | nasrut151 | 30007434 | FAS3040 |  |  |  | 2014-10-31 |  |  |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT140 | 30011070 | FAS3070 |  |  |  | 2014-10-31 | 7518.88 | 1 |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT149 | 30011093 | FAS3070 |  |  |  | 2014-10-31 |  |  |  | United States | NJ | [5 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT19DR | 700000281088 | FAS3140 |  |  |  | 2014-12-31 | 7340.72 | 1 | 70470.912 | United States | NJ | 2017-03-31 |  |  |  |  | 5872.576 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT20DR | 700000281090 | FAS3140 |  |  |  | 2014-12-31 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT002S | 700000430756 | FAS3160 |  |  |  | 2014-12-31 | 10487.84 | 1 | 100683.264 | United States | NJ | 2017-03-31 |  |  |  |  | 8390.272 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT003S | 700000516976 | FAS3140 |  |  |  | 2015-01-30 | 3175.76 | 1 | 27946.688 | United States | NJ | 2017-03-31 |  |  |  |  | 2328.8907 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | rutctinasf8001b | 700000571316 | FAS3170 |  |  |  | 2015-03-31 | 6496.9 | 1 | 46777.68 | United States | NJ | 2017-03-31 |  |  |  |  | 3898.14 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | rutctinasf8001a | 700000571304 | FAS3170 |  |  |  | 2015-03-31 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT001DR | 700000603145 | FAS3140 |  |  |  | 2015-04-30 | 4755.42 | 1 | 30434.688 | United States | NJ | 2017-03-31 |  |  |  |  | 2536.224 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | NASRUT002DR | 700001119115 | FAS3140 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | UNKNOWN | 700000244743 | FAS6080 |  |  |  | 2015-04-30 | 801.5 | 1 | 5129.6 | United States | NJ | 2015-09-15 |  |  |  |  | 427.4667 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1003A | 700000635265 | FAS3240 |  |  |  | 2015-04-30 | 9883.96 | 1 | 63257.344 | United States | NJ | 2018-12-31 |  |  |  |  | 5271.4453 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1003B | 700000635277 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1004A | 700000638384 | FAS3240 |  |  |  | 2015-04-30 | 11397.88 | 1 | 72946.432 | United States | NJ | 2018-12-31 |  |  |  |  | 6078.8693 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1004B | 940001061160 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1002A | 700000639144 | FAS3240 |  |  |  | 2015-04-30 | 10728.68 | 1 | 68663.552 | United States | NJ | 2018-12-31 |  |  |  |  | 5721.9627 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1002B | 700000639156 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1007A | 700000639326 | FAS3240 |  |  |  | 2015-04-30 | 9061.68 | 1 | 57994.752 | United States | NJ | 2018-12-31 |  |  |  |  | 4832.896 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1007B | 700000639338 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1006A | 700000639340 | FAS3240 |  |  |  | 2015-04-30 | 10575.6 | 1 | 67683.84 | United States | NJ | 2018-12-31 |  |  |  |  | 5640.32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1006B | 500000218219 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1005A | 700000639522 | FAS3240 |  |  |  | 2015-04-30 | 10575.6 | 1 | 67683.84 | United States | NJ | 2018-12-31 |  |  |  |  | 5640.32 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | Americas | Rutherford | RUTCTINASF1005B | 700000639534 | FAS3240 |  |  |  | 2015-04-30 |  |  |  | United States | NJ | 2018-12-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | PALO ALTO | SFOCTINASF1001B | 600000014732 | FAS2020 | 0.45587 | 1 |  | 2014-12-31 | 692.98 | 1 | 6652.608 | United States | CA | 2017-06-17 | TR2014 | 54 | 1 | 93 | 554.384 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 1108.768 | 0 | 0 | 0 | 0 | 1108.768
Yes | No | Americas | PALO ALTO | SFOCTINASF1001A | 700000293201 | FAS2020 | 0.61427 | 1 |  | 2014-12-31 |  |  |  | United States | CA | 2017-06-17 | TR2014 | 54 | 2 | 93 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr01 | 700000177483 | FAS3140 |  |  |  | 2014-02-28 | 6281.18 | 1 | 60299.328 | Brazil |  | 2017-03-31 |  |  |  |  | 5024.944 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr02 | 700000177495 | FAS3140 |  |  |  | 2014-02-28 |  |  |  | Brazil |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr03 | 700000248218 | FAS3140 |  |  |  | 2014-02-28 | 7970 | 1 | 76512 | Brazil |  | 2017-03-31 |  |  |  |  | 6376 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
No | No | LATAM | Sao Paulo | nasbr04 | 700000175069 | FAS3140 |  |  |  | 2014-02-28 |  |  |  | Brazil |  | 2017-03-31 |  |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | Americas | BLUE ASH | NASBLU02 | 700000518584 | FAS2040 | 0 | 1 | 0 | 2015-01-30 | 3912.56 | 1 | 34430.528 | United States | MO | 2015-12-10 | TR2013 | 55 | 1 | 70 | 2869.2107 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 5738.4213 | 0 | 0 | 0 | 0 | 5738.4213
Yes | No | Americas | BLUE ASH | NASBLU01 | 700000518596 | FAS2040 | 7.73 | 1 | 3.75 | 2015-01-30 |  |  |  | United States | MO | 2015-12-10 | TR2013 | 55 | 2 | 70 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Budapest | budctinas201a | 200000002054 | FAS3140 | 8.7761 | 1 | 3.75 | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 | TR2014 | 101 | 1 | 8 | 3298.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6596.032 | 0 | 0 | 0 | 0 | 6596.032
Yes | No | EMEA | Budapest | budctinas201b | 200000002028 | FAS3140 | 10.0193 | 1 |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 | TR2014 | 101 | 2 | 8 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Budapest | budctinas202a | 200000001995 | FAS3140 | 8.7547 | 1 | 3.75 | 2014-12-31 | 4122.52 | 1 | 39576.192 | Hungary |  | 2017-03-31 | TR2014 | 102 | 1 | 8 | 3298.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 6596.032 | 0 | 0 | 0 | 0 | 6596.032
Yes | No | EMEA | Budapest | budctinas202b | 200000002016 | FAS3140 | 9.978 | 1 |  | 2014-12-31 |  |  |  | Hungary |  | 2017-03-31 | TR2014 | 102 | 2 | 8 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | FRACTINAS501A | 20016003 | FAS3070 | 21.2105 | 2 | 8.75 | 2014-03-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2014-04-03 | TR2014 | 103 | 1 | 2 | 10151.312 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 50756.56 | 0 | 0 | 0 | 0 | 50756.56
Yes | No | EMEA | Frankfurt | FRACTINAS501B | 20016351 | FAS3070 | 12.8387 | 1 |  | 2014-03-31 |  |  |  | Germany |  | 2014-04-04 | TR2014 | 103 | 2 | 2 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | FRACTINAS504A | 200000035063 | FAS3170 | 29.7545 | 3 | 12.5 | 2014-12-31 | 12689.14 | 1 | 121815.744 | Germany |  | 2017-03-31 | TR2014 | 104 | 1 | 2 | 10151.312 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 50756.56 | 0 | 0 | 0 | 0 | 50756.56
Yes | No | EMEA | Frankfurt | FRACTINAS504B | 200000035099 | FAS3170 | 29.9273 | 3 |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 | TR2014 | 104 | 2 | 2 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Frankfurt | fractinas505a | 200000135837 | FAS3170 | 30.3591 | 3 | 12.5 | 2014-12-31 | 11028.42 | 1 | 105872.832 | Germany |  | 2017-03-31 | TR2014 | 105 | 1 | 4 | 8822.736 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 44113.68 | 0 | 0 | 0 | 0 | 44113.68
Yes | No | EMEA | Frankfurt | fractinas505b | 200000136013 | FAS3170 | 6.4089 | 1 |  | 2014-12-31 |  |  |  | Germany |  | 2017-03-31 | TR2014 | 105 | 2 | 4 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Karachi | KHICTINAS201A | 30003866 | FAS3040 | 13.2258 | 1 | 6.25 | 2014-03-31 | 2342.52 | 1 | 22488.192 | Pakistan |  | 2014-04-05 | TR2014 | 106 | 1 | 10 | 1874.016 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 3748.032 | 0 | 0 | 0 | 0 | 3748.032
Yes | No | EMEA | Karachi | KHICTINAS201B | 30003867 | FAS3040 | 13.2253 | 1 |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-06 | TR2014 | 106 | 2 | 10 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Karachi | KHICTINAS202A | 30001777 | FAS3040 | 13.2314 | 1 | 6.25 | 2014-03-31 | 2015.82 | 1 | 19351.872 | Pakistan |  | 2014-04-07 | TR2014 | 107 | 1 | 11 | 1612.656 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 3225.312 | 0 | 0 | 0 | 0 | 3225.312
Yes | No | EMEA | Karachi | KHICTINAS202B | 1088268 | FAS3040 | 13.229 | 1 |  | 2014-03-31 |  |  |  | Pakistan |  | 2014-04-08 | TR2014 | 107 | 2 | 11 | 0 | 2015-01-17 | 1 | 2015-01-17 | 2015-01-17 | 2015-02-16 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS207A | 200000002975 | FAS3170 | 25.5421 | 2 | 10 | 2015-01-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 108 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS207B | 200000002963 | FAS3170 | 29.7505 | 3 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 108 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | ldnctinas208a | 200000002913 | FAS3170 | 24.9845 | 2 | 10 | 2015-01-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 109 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | ldnctinas208b | 200000001543 | FAS3170 | 29.6564 | 3 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 109 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS209A | 200000069117 | FAS3170 | 30.3588 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 110 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS209B | 200000068993 | FAS3170 | 30.319 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 110 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS210A | 200000069105 | FAS3170 | 30.0138 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 111 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | LDNCTINAS210B | 200000062004 | FAS3170 | 30.3053 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 111 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS301A | 200000005197 | FAS3140 | 9.38 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 112 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS301B | 200000002638 | FAS3140 | 4.8062 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 112 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS302A | 200000007420 | FAS3140 | 9.3824 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 113 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS302B | 200000007547 | FAS3140 | 4.8132 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 113 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS303A | 200000005020 | FAS3140 | 8.8364 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 114 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS303B | 200000004997 | FAS3140 | 10.2541 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 114 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS304A | 200000005056 | FAS3140 | 8.8521 | 1 | 3.75 | 2015-01-31 | 5490.48 | 1 | 52708.608 | United Kingdom |  | 2017-03-31 | TR2014 | 115 | 1 | 6 | 4392.384 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 21961.92 | 0 | 0 | 0 | 0 | 21961.92
Yes | No | EMEA | London | LDNCTINAS304B | 200000005185 | FAS3140 | 10.261 | 1 |  | 2015-01-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 115 | 2 | 6 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS501A | 20016347 | FAS3070 | 24.5514 | 2 | 10 | 2014-04-30 | 10846.61 | 1 | 104127.456 | United Kingdon |  | 2014-04-09 | TR2014 | 116 | 1 | 5 | 8677.288 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 43386.44 | 0 | 0 | 0 | 0 | 43386.44
Yes | No | EMEA | London | LDNCTINAS501B | 20016346 | FAS3070 | 15.5945 | 2 |  | 2014-04-30 |  |  |  | United Kingdon |  | 2014-04-10 | TR2014 | 116 | 2 | 5 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-11 | 2015-05-11 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | ldnctinas504a | 200000043917 | FAS3170 | 29.9002 | 3 | 12.5 | 2014-12-31 | 13764.32 | 1 | 132137.472 | United Kingdom |  | 2017-03-31 | TR2014 | 117 | 1 | 1 | 11011.456 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 55057.28 | 0 | 0 | 0 | 0 | 55057.28
Yes | No | EMEA | London | ldnctinas504b | 200000043905 | FAS3170 | 29.7545 | 3 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 117 | 2 | 1 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | London | LDNCTINAS505A | 200000152031 | FAS3170 | 30.0557 | 3 | 12.5 | 2014-12-31 | 11028.42 | 1 | 105872.832 | United Kingdom |  | 2017-03-31 | TR2014 | 118 | 1 | 4 | 8822.736 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-18 | 2015-05-18 | 5 | 44113.68 | 0 | 0 | 0 | 0 | 44113.68
Yes | No | EMEA | London | LDNCTINAS505B | 200000151049 | FAS3170 | 6.587 | 1 |  | 2014-12-31 |  |  |  | United Kingdom |  | 2017-03-31 | TR2014 | 118 | 2 | 4 | 0 | 2015-01-17 | 12 | 2015-04-04 | 2015-04-04 | 2015-05-04 | 5 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | ALCOBENDAS | MADCTINAS201A | 200000187294 | FAS3140 | 9.9462 | 1 | 5 | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 | TR2014 | 119 | 1 | 6 | 4392.384 | 2015-01-17 | 3 | 2015-01-31 | 2015-01-31 | 2015-03-02 | 2 | 8784.768 | 0 | 0 | 0 | 0 | 8784.768
Yes | No | EMEA | ALCOBENDAS | MADCTINAS201B | 200000187309 | FAS3140 | 9.9874 | 1 |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 | TR2014 | 119 | 2 | 6 | 0 | 2015-01-17 | 3 | 2015-01-31 | 2015-01-31 | 2015-03-02 | 2 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | MADRID | MADCTINAS202A | 200000187323 | FAS3140 | 9.8963 | 1 | 5 | 2014-12-31 | 5490.48 | 1 | 52708.608 | Spain |  | 2017-03-31 | TR2014 | 120 | 1 | 6 | 4392.384 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-07 | 2015-03-09 | 3 | 13177.152 | 0 | 0 | 0 | 0 | 13177.152
Yes | No | EMEA | MADRID | MADCTINAS202B | 200000187311 | FAS3140 | 9.9009 | 1 |  | 2014-12-31 |  |  |  | Spain |  | 2017-03-31 | TR2014 | 120 | 2 | 6 | 0 | 2015-01-17 | 4 | 2015-02-07 | 2015-02-07 | 2015-03-09 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Prague | PRGCTINAS201A | 200000067145 | FAS3140 | 5.3491 | 1 | 2.5 | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 | TR2014 | 121 | 1 | 7 | 3662.8 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 10988.4 | 0 | 0 | 0 | 0 | 10988.4
Yes | No | EMEA | Prague | PRGCTINAS201B | 200000066880 | FAS3140 | 5.3491 | 1 |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 | TR2014 | 121 | 2 | 7 | 0 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Prague | PRGCTINAS202A | 200000067808 | FAS3140 | 5.3491 | 1 | 2.5 | 2014-12-31 | 4578.5 | 1 | 43953.6 | Czech Republic |  | 2017-03-31 | TR2014 | 122 | 1 | 7 | 3662.8 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 10988.4 | 0 | 0 | 0 | 0 | 10988.4
Yes | No | EMEA | Prague | PRGCTINAS202B | 200000067810 | FAS3140 | 5.3491 | 1 |  | 2014-12-31 |  |  |  | Czech Republic |  | 2017-03-31 | TR2014 | 122 | 2 | 7 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Moscow | VKOCTINAS201A | 200000068448 | FAS3160 | 29.731 | 3 | 12.5 | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 | TR2014 | 123 | 1 | 3 | 9329.52 | 2015-01-17 | 7 | 2015-02-28 | 2015-03-14 | 2015-04-13 | 4 | 37318.08 | 0 | 0 | 0 | 0 | 37318.08
Yes | No | EMEA | Moscow | VKOCTINAS201B | 200000067183 | FAS3160 | 29.694 | 3 |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 | TR2014 | 123 | 2 | 3 | 0 | 2015-01-17 | 7 | 2015-02-28 | 2015-03-14 | 2015-04-13 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Moscow | VKOCTINAS202A | 200000066622 | FAS3160 | 29.6031 | 3 | 12.5 | 2014-12-31 | 11661.9 | 1 | 111954.24 | Russia |  | 2017-03-31 | TR2014 | 124 | 1 | 3 | 9329.52 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-21 | 2015-04-20 | 4 | 37318.08 | 0 | 0 | 0 | 0 | 37318.08
Yes | No | EMEA | Moscow | VKOCTINAS202B | 200000066646 | FAS3160 | 29.7168 | 3 |  | 2014-12-31 |  |  |  | Russia |  | 2017-03-31 | TR2014 | 124 | 2 | 3 | 0 | 2015-01-17 | 8 | 2015-03-07 | 2015-03-21 | 2015-04-20 | 4 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Warsaw | wswctinas201a | 20004838 | FAS3040 | 3.3405 | 1 | 2.5 | 2014-04-06 | 2532.05 | 1 | 24307.68 | Poland |  | na | TR2014 | 125 | 1 | 9 | 2025.64 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 6076.92 | 0 | 0 | 0 | 0 | 6076.92
Yes | No | EMEA | Warsaw | wswctinas201b | 20004839 | FAS3040 | 3.3396 | 1 |  | 2014-04-06 |  |  |  | Poland |  | na | TR2014 | 125 | 2 | 9 | 0 | 2015-01-17 | 5 | 2015-02-14 | 2015-02-14 | 2015-03-16 | 3 | 0 | 0 | 0 | 0 | 0 | 0
Yes | No | EMEA | Warsaw | wswctinas202a | 20004840 | FAS3040 | 3.3325 | 1 | 2.5 | 2014-04-06 | 2532.05 | 1 | 24307.68 | Poland |  | na | TR2014 | 126 | 1 | 9 | 2025.64 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 6076.92 | 0 | 0 | 0 | 0 | 6076.92
Yes | No | EMEA | Warsaw | wswctinas202b | 20004841 | FAS3040 | 3.3326 | 1 |  | 2014-04-06 |  |  |  | Poland |  | na | TR2014 | 126 | 2 | 9 | 0 | 2015-01-17 | 6 | 2015-02-21 | 2015-02-21 | 2015-03-23 | 3 | 0 | 0 | 0 | 0 | 0 | 0
No | Yes | EMEA | Milano | MILCTINAS401A | 200000250508 | FAS3140 | 3.4019 |  |  | 2015-01-30 | 3221.26 | 1 | 30924.096 | Italy |  | 2017-03-31 | TR2014 |  |  |  | 2577.008
No | Yes | EMEA | Milano | MILCTINAS401B | 200000250493 | FAS3140 | 1.6682 |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 | TR2014 |  |  |  | 0
No | Yes | EMEA | Milano | MILCTINAS402A | 200000245395 | FAS3140 | 2.6424 |  |  | 2015-01-30 | 3221.26 | 1 | 30924.096 | Italy |  | 2017-03-31 | TR2014 |  |  |  | 2577.008
No | Yes | EMEA | Milano | MILCTINAS402B | 200000245266 | FAS3140 | 1.7417 |  |  | 2015-01-30 |  |  |  | Italy |  | 2017-03-31 | TR2014 |  |  |  | 0
Formulas:
Scheduled Start = (MAX(X4:X324)*7)+[Project Start Date]
Scheduled Start = (([Scheduled Week Number]*7)-7)+[Project Start Date]
Scheduled Finished = ((([Number of Weekends for Waves]*7))-7)+[Scheduled Start]
Decomm Date = [Scheduled Finished]+30
Decomm Date = (([Scheduled Week Number]*7)-7)+[Project Start Date]

## Replicated Hosts on Multiple Ar
Team: | Global Storage Provisioning and Migrations
Manager: | Gary Battersby
Project: | NAS Migrations Q3 TR2013
Region | Task | Owner | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification