## Project Summary
Region | Project | Estimated Completion Date | Current Status | Comments | Amended Completion Date | New Date Justification | Reasons for Delay | Risks/ Mitigations
ASPAC | APPC Storage RFP 2013 Tech refresh Migration Project ( SG/HK ) | 2015-06-01 | amber | This is to migrate almost 4 PB of storage as part of this refresh. ~40% migration completed against 57% estimated. UAT migration stalled due to capacity constraint Working closely with the sector aligned team to catch up. |  |  | Initial delays in data center space Downtimes constraints UAT space constraint - being worked on | * HDS VSP warranty expires in March 2015 * Working closely with the platform teams and apps team to catch up
ASPAC | NAS Technology Refresh ( SG/HK ) - Phase1 | 2014-12-01 | amber | 70% completion - expected to complete in next few weeks while focussing on NetApp to avoid the maintenance cost. |  |  | Initial delays in network infra Downtimes constraints | Netapp MA expire on Dec 2014 - focussing to complete it by DEC 2014 Migration scheduled for next 3 more weeks and expecting completion by DEC 2014
ASPAC | China Storage Technology Refresh | 2015-06-01 | green | in progress |  |  | Downtimes constraints | MR to complete as expected - DD to be completed by June 2015
ASPAC | MDS switch technology refresh 2014 (SG/HK) | 2015-12-01 | amber | Pending space allocation in DC and Strcutured cabling. Detailed expedited plan need to be worked on. |  |  | Pending space allocation in DC and Strcutured cabling.
ASPAC | NAS Technology Refresh ( regional in country) - Phase2 | 2015-07-01 | green | in progress
ASPAC | India SAN technology refresh | 2014-09-01 | amber | Only Delhi CX migration 2 servers, completed. There was capacity issue, which is resolved recently - it is planned for |  | 2014-12-01 | Only Delhi CX migration 2 servers, completed. There was capacity issue, which is resolved recently - it is planned for | Capacity issue resolved - pending migration from India platform team- expected to complete before year end freeze as per plan
ASPAC | Centera Technology refresh SG/HK | 2014-06-01 | green | completed- pending project closure/rollout

## SAN-RFP MIGRATION
WS17900061 - CIS-SGHK-Distributed Strg 2014 Strategic Tech Refresh - Migration Schedule
Loc/ Env | SL | Model | Serial Number | Location | Env | Capacity | Migrated | Pending | No of Servers | Schedule | Priority | % Completed | Remarks
HK COB/UAT HDS | 1 | 1 | 45141 | HK - iAD | COB | 41.62 |  | 41.62 | 14 | Aug'14 | 1 | 82% | Left over 2 servers to be migrated during Nov'14
| 2 | VSP | 53587 | HK - iAD | COB | 218.27 | 2.4 | 215.87 | 128 | Oct'14 | 1 | 21%
| 3 | VSP | 53732 | HK - iAD | COB | 164.60 | 38.48 | 126.11 | 124 | Nov'14 | 1 | 61%
| 4 | VSP | 53789 | HK - AST | COB | 168.18 |  | 168.18 | 176 | Nov'14 | 1 | 0%
| 5 | VSP | 53796 | HK - AST | COB | 90.49 |  | 90.49 | 58 | Oct'14 | 1 | 12%
| 6 | VSP | 53755 | HK - iAD | UAT | 186.87 | 3.08 | 183.79 | 423 | Dec'14 | 2 | 15%
| 7 | VSP | 53799 | HK - AST | UAT | 274.00 | 31.6 | 242.4 | 507 | Dec'14 | 2 | 24%
SG PROD HDS | 8 | USPV | 17395 | SG | PRD | 29.68 |  | 29.68 | 18 | 2014-08-01 | 1 | 87% | Left over 2 servers to be migrated during Nov'14
| 9 | VSP | 53762 | SG | PRD | 171.76 |  | 171.76 | 144 | Nov'14 | 1 | 13%
| 10 | VSP | 53643 | SG | PRD | 136.06 | 23.88 | 112.18 | 235 | Dec'14 | 1 | 37%
| 11 | VSP | 53630 | SG | PRD | 78.72 |  | 78.72 | 77 | Oct'14 | 1 | 0%
| 12 | VSP | 53584 | SG | PRD | 52.17 |  | 52.17 | 82 | Oct'14 | 1 | 10%
| 13 | VSP | 53744 | SG | UAT | 17.89 |  | 17.89 | 25 | Sep'14 | 1 | 86%
SG Prod CX/VNX | 14 | CX3-80 | CK200081900324 | SG - Cnt | PRD | 18.38 |  | 18.38 | 9 | Jan'14 | 3
| 15 | CX3-80 | CK200072400943 | SG - Cnt | PRD | 40.13 |  | 40.13 | 33 | Dec'14 | 3
| 16 | CX3-80 | CK200081900323 | SG - Cnt | PRD | 11.18 |  | 11.18 | 11 | Nov'14 | 3
| 17 | CX 700 | CK200063500092 | SG - Cnt | PRD | 16.43 | 5.84 | 10.59 | 5 | Aug'14 | 3 |  | Completed
| 18 | CX3-80 | CK200071500503 | SG - Cnt | PRD | 11.18 |  | 11.18 | 3 | Sep'14 | 3
| 19 | CX-480 | CKM00101800043 | SG - Cnt | PRD | 28.66 | 4.24 | 24.43 | 18 | Nov'14 | 3
| 20 | VNX | CKM00121900293 | SG - Cnt | PRD | 7.75 |  | 7.75 | 5 | Feb'15 | 3
HK Prod CX | 21 | CX4-120 | FCNCX101000064 | HK - iAD | PRD | 38.31 | 0.44 | 37.87 | 29 | Feb'15 | 3
| 22 | CX-480 | CKM00102100004 | HK - iAD | PRD | 61.18 |  | 61.18 | 31 | Mar'15 | 3
SG Prod DMX/VMAX | 23 | VMAX | 292600268 | SG - Tpk | Bunker | 32.38 |  | 32.38 | 0 | Jan'15 | 4
| 24 | DMX | 290105366 | SG - Cnt | PRD | 32.38 |  | 32.38 | 21 | Feb'15 | 4
| 25 | DMX950 | 290300751 | SG - Tpk | PRD | 6.16 |  | 6.16 | 1 | Jan'15 | 4
| 26 | DMX950 | 290301222 | SG - Cnt | PRD | 7.72 |  | 7.72 | 2 | Jan'15 | 4
| 27 | VMAX | 292600224 | SG - Cnt | PRD | 19.83 |  | 19.83 | 22 | Feb'15 | 4
| 28 | VMAX | 292602662 | SG - Cnt | PRD | 76.61 |  | 76.61 | 178 | Apr'15 | 4
| 29 | VMAX | 492600122 | SG - Cnt | PRD | 107.22 |  | 107.22 | 40 | Mar'15 | 4
| 30 | VMAX | 492600146 | SG - Cnt | PRD | 54.53 | 15.9 | 38.63 | 60 | Apr'15 | 4
| 31 | VMAX | 292603943 | SG - Cnt | PRD | 188.81 | 6.12 | 182.69 | 95 | Jul'15 | 4
| 32 | VMAX | 292603979 | SG - Cnt | PRD | 86.19 |  | 86.19 | 12 | May'15 | 4
HK COB DMX/VMAX | 33 | DMX | 290105338 | HK - iAD | COB | 64.75 |  | 64.75 | 6 | Mar'15 | 4
| 34 | DMX | 290103014 | HK - AST | COB | 64.75 |  | 64.75 | 4 | Mar'15 | 4
| 35 | DMX950 | 290301196 | HK - iAD | COB | 12.32 |  | 12.32 | 2 | Mar'15 | 4
| 36 | VMAX | 292600269 | HK - iAD | COB | 39.66 |  | 39.66 | 12 | Mar'15 | 4
| 37 | VMAX | 492600105 | HK - iAD | COB | 152.22 |  | 152.22 | 114 | Jun'15 | 4
| 38 | VMAX | 492600106 | HK - iAD | COB | 236.05 |  | 236.05 | 10 | May'15 | 4
| 39 | VMAX | 492600150 | HK - AST | COB | 108.08 | 31.8 | 76.28 | 35 | Apr'15 | 4
| 40 | VMAX | 292604132 | HK - AST | COB | 323.61 | 12.25 | 311.37 | 103 | Jul'15 | 4
| 41 | VMAX | 292604047 | HK - AST | COB | 107.56 |  | 107.56 | 11 | May'15 | 4
Completed Frames | 42 | DMX | 290103429 | SG - Cnt | PRD | 41.47 | 41.47 | 0 | 3 | Jun'14 | 0 |  | Completed
| 43 | DMX | 290103486 | SG - Cnt | PRD | 38.69 | 38.69 | 0 | 2 | Jun'14 | 0 |  | Completed
| 44 | DMX | 290103762 | HK - iAD | COB | 77.38 | 77.38 | 0 | 2 | Jun'14 | 0 |  | Completed
| 45 | USPV | 17111 | SG | PRD | 30.86 | 30.86 | 0 | 11 | Jun'14 | 0 |  | Completed
| 46 | USPV | 17422 | SG | PRD | 26.54 | 26.54 | 0 | 19 | Jun'14 | 0 |  | Completed
| 47 | USPV | 45152 | HK - iAD | COB | 42.13 | 42.13 | 0 | 8 | Jun'14 | 0 |  | Completed
Note on J2: Author: Detailed server list is provided in next sheet

## MDS 2014
Phases | ID | Key Milestone/ Activity | Start | End | Owner | Status | Remarks
| 1 | Initiation | 2014-09-08 | 2014-09-08
| 1.1 | Kick-off | 2014-09-08 | 2014-09-08 | Joseph/ PM | Completed
| 2 | Plan | 2014-09-18 | 2015-01-21
Plan | 2.1 | Storage requirements finalization | 2014-09-18 | 2014-09-18 | Requester/ Platforms | Completed
| 2.2 | SG DC (CT) Requirements finalization | 2014-09-25 | 2014-09-25 | Sunil/ Storage | Completed
| 2.3 | HK DC (AST/iAD) requirements finalization | 2014-10-02 | 2014-10-02 | Sunil/ Storage | Completed
| 2.4 | Management IP provisioning | 2014-11-17 | 2014-11-21 | Sherryl/ Network
| 2.5 | Network Replication 10G design and implementation | 2014-11-21 | 2015-01-21 | Sherryl/ Network
| 2.6 | MjPC submission | 2014-11-28 | 2014-11-28 | Joseph/ PM
| 2.7 | MjPC approved | 2014-12-05 | 2014-12-05 | Sponsor
| 2.8 | MjPP submission | 2014-12-05 | 2014-12-05 | Joseph/ PM
| 2.9 | MjPP approved | 2014-12-12 | 2014-12-12 | Sponsor
| 3 | Execute | 2014-11-07 | 2015-08-30 |  |  | Split into Two phases (Phase - I will be the hosting and configuration) (Phase-II will be migrations of ports)
Phase - I | 3.1 | Hosting at SG DC (CT2) Level 1 | 2014-11-07 | 2014-12-14 | DC team
| 3.1.1 | Open Rack Readiness in CT2 L1 to mount the new EDGE Switches | 2014-11-07 | 2014-11-07 | Edwin/ Cabling | Completed
| 3.1.2 | Delivery Confirmation for Edge Switches to CT2 L1 & Rack Mount to Open Racks | 2014-11-07 | 2014-11-07 | Stephen / Facilities | Completed
| 3.1.3 | Power Readiness for the Edge Switches in CT2 L1 | 2014-11-23 | 2014-11-23 | Stephen / Facilities | Completed
| 3.1.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.1.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in CT2 L1 | 2014-11-21 | 2014-11-21 | Edwin/ Cabling | Completed
| 3.1.6 | Delivery Confirmation for CORE & FCIP Switches to CT2 L1 | 2014-11-21 | 2014-11-21 | Stephen / Facilities | Completed
| 3.1.7 | Power Readiness for CORE & FCIP Switches to CT2 L1 | 2014-11-23 | 2014-11-23 | Stephen / Facilities | Completed
| 3.1.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-11-21 | 2014-11-21 | Sherryl / Network
| 3.1.9 | Configuration of CORE & Edge Switches in CT2 L1 once switches are installed | 2014-12-14 | 2014-12-14 | Sunil / Storage
| 3.1.10 | Delivery Confirmation for Two New G2C Storage Frames to CT2 L1 | 2014-12-14 | 2014-12-14 | Stephen / Facilities
| 3.1.11 | Power Readiness for the New Storage frames in CT2 L1 | 2014-12-14 | 2014-12-14 | Stephen / Facilities
| 3.1.12 | Network Readiness for the Mgt Connectivity for the new Storage frames | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.2 | Hosting at SG DC (CT2) B 1 | 2014-12-05 | 2014-12-07
| 3.2.1 | Open Rack Readiness in CT2 B1 to mount the new EDGE Switches | 2014-12-05 | 2014-12-05 | Edwin/ Cabling
| 3.2.2 | Delivery Confirmation for Edge Switches to CT2 B1 & Rack Mount to Open Racks | 2014-12-05 | 2014-12-05 | Stephen / Facilities
| 3.2.3 | Power Readiness for the Edge Switches in CT2 B1 | 2014-12-07 | 2014-12-07 | Stephen / Facilities
| 3.2.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-12-07 | 2014-12-07 | Sherryl / Network
| 3.2.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in CT2 B1 | 2014-12-05 | 2014-12-05 | Edwin/ Cabling
| 3.2.6 | Delivery Confirmation for CORE & FCIP Switches to CT2 B1 | 2014-12-05 | 2014-12-05 | Stephen / Facilities
| 3.2.7 | Power Readiness for CORE & FCIP Switches to CT2 B1 | 2014-12-07 | 2014-12-07 | Stephen / Facilities
| 3.2.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-12-07 | 2014-12-07 | Sherryl / Network
| 3.2.9 | Configuration of CORE,Edge & FCIP Switches in CT2 B1 once switches are installed | 2014-12-07 | 2014-12-07 | Sunil / Storage
| 3.3 | Hosting at AST - DC1 | 2014-11-21 | 2014-11-28
| 3.3.1 | Open Rack Readiness in AST DC1 to mount the new EDGE Switches | 2014-11-21 | 2014-11-21 | Edwin/ Cabling
| 3.3.2 | Delivery Confirmation for Edge Switches to AST DC1 & Rack Mount to Open Racks | 2014-11-21 | 2014-11-28 | Asterix / Facilities
| 3.3.3 | Power Readiness for the Edge Switches in AST DC1 | 2014-11-23 | 2014-11-28 | Asterix / Facilities
| 3.3.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.3.5 | Configuration of Edge Switches in AST DC1 once switches are installed | 2014-11-23 | 2014-11-23 | Sunil / Storage
| 3.4 | Hosting at AST - DC2 | 2014-11-21 | 2014-12-14
| 3.4.1 | Open Rack Readiness in AST DC2 to mount the new EDGE Switches | 2014-11-21 | 2014-11-21 | Edwin/ Cabling
| 3.4.2 | Delivery Confirmation for Edge Switches to AST DC2 & Rack Mount to Open Racks | 2014-11-21 | 2014-11-28 | Asterix / Facilities
| 3.4.3 | Power Readiness for the Edge Switches in AST DC2 | 2014-11-23 | 2014-11-23 | Asterix / Facilities
| 3.4.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.4.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in AST DC2 | 2014-11-21 | 2014-11-28 | Edwin/ Cabling
| 3.4.6 | Delivery Confirmation for CORE & FCIP Switches to AST DC2 | 2014-11-21 | 2014-11-21 | Asterix / Facilities
| 3.4.7 | Power Readiness for CORE & FCIP Switches to AST DC2 | 2014-11-23 | 2014-11-23 | Asterix / Facilities
| 3.4.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.4.9 | Configuration of CORE,Edge & FCIP Switches in AST DC2 once switches are installed | 2014-12-14 | 2014-12-14 | Sunil / Storage
| 3.5 | Hosting at AST - DC6 | 2014-11-21 | 2014-12-14
| 3.5.1 | Open Rack Readiness in AST DC6 to mount the new EDGE Switches | 2014-11-21 | 2014-11-21 | Edwin/ Cabling
| 3.5.2 | Delivery Confirmation for Edge Switches to AST DC6 & Rack Mount to Open Racks | 2014-11-21 | 2014-11-28 | Asterix / Facilities
| 3.5.3 | Power Readiness for the Edge Switches in AST DC6 | 2014-11-23 | 2014-11-23 | Asterix / Facilities
| 3.5.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.5.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in AST DC6 | 2014-11-21 | 2014-11-28 | Edwin/ Cabling
| 3.5.6 | Delivery Confirmation for CORE & FCIP Switches to AST DC6 | 2014-11-21 | 2014-11-21 | Asterix / Facilities
| 3.5.7 | Power Readiness for CORE & FCIP Switches to AST DC6 | 2014-11-23 | 2014-11-23 | Asterix / Facilities
| 3.5.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-11-23 | 2014-11-23 | Sherryl / Network
| 3.5.9 | Configuration of CORE,Edge & FCIP Switches in AST DC6 once switches are installed | 2014-12-14 | 2014-12-14 | Sunil / Storage
| 3.6 | Hosting at iAD - 22 | 2014-12-12 | 2014-12-21
| 3.6.1 | Open Rack Readiness in IAD 22 to mount the new EDGE Switches | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.6.2 | Delivery Confirmation for Edge Switches to IAD 22 & Rack Mount to Open Racks | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.6.3 | Power Readiness for the Edge Switches in IAD 22 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.6.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.6.5 | Configuration of Edge Switches in IAD 22 once switches are installed | 2014-12-21 | 2014-12-21 | Sunil / Storage
| 3.7 | Hosting at iAD - 23 | 2014-12-12 | 2014-12-21
| 3.7.1 | Open Rack Readiness in IAD 23 to mount the new EDGE Switches | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.7.2 | Delivery Confirmation for Edge Switches to IAD 23 & Rack Mount to Open Racks | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.7.3 | Power Readiness for the Edge Switches in IAD 23 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.7.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.7.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in IAD 23 | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.7.6 | Delivery Confirmation for CORE & FCIP Switches to IAD 23 | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.7.7 | Power Readiness for CORE & FCIP Switches to IAD 23 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.7.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.7.9 | Configuration of CORE,Edge & FCIP Switches in IAD 23 once switches are installed | 2014-12-21 | 2014-12-21 | Sunil / Storage
| 3.8 | Hosting at iAD - 25 | 2014-12-12 | 2014-12-21
| 3.8.1 | Open Rack Readiness in IAD 25 to mount the new EDGE Switches | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.8.2 | Delivery Confirmation for Edge Switches to IAD 25 & Rack Mount to Open Racks | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.8.3 | Power Readiness for the Edge Switches in IAD 25 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.8.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.8.5 | Enclosed Rack Readiness to mount the CORE & FCIP Switches in IAD 25 | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.8.6 | Delivery Confirmation for CORE & FCIP Switches to IAD 25 | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.8.7 | Power Readiness for CORE & FCIP Switches to IAD 25 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.8.8 | Network Readiness for the Mgt Connectivity for CORE & FCIP Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.8.9 | Configuration of CORE,Edge & FCIP Switches in IAD 25 once switches are installed | 2014-12-21 | 2014-12-21 | Sunil / Storage
| 3.9 | Hosting at iAD - 27 | 2014-12-12 | 2014-12-21
| 3.9.1 | Open Rack Readiness in IAD 27 to mount the new EDGE Switches | 2014-12-12 | 2014-12-12 | Edwin/ Cabling
| 3.9.2 | Delivery Confirmation for Edge Switches to IAD 27 & Rack Mount to Open Racks | 2014-12-12 | 2014-12-12 | Asterix / Facilities
| 3.9.3 | Power Readiness for the Edge Switches in IAD 27 | 2014-12-14 | 2014-12-14 | Asterix / Facilities
| 3.9.4 | Network Readiness for the Mgt Connectivity for the Edge Switches | 2014-12-14 | 2014-12-14 | Sherryl / Network
| 3.9.5 | Configuration of Edge Switches in IAD 27 once switches are installed | 2014-12-21 | 2014-12-21 | Sunil / Storage
Phase - II | 3.1 | Port migration at CT2 - L1 (Total Ports - 2516) | 2015-01-02 | 2015-08-30
| 3.10.1 | Production server Migrations | 2015-01-02 | 2015-08-30 | Sunil/ Storage
| 3.10.2 | UAT server Migrations | 2015-01-02 | 2015-08-30 | Sunil/ Storage
| 3.11 | Port migration at CT2 - B1 (Total Ports - 4244) | 2015-02-02 | 2015-08-30
| 3.11.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.11.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.12 | Port migration at CT AST - DC1 (Total Ports - 374) | 2015-02-02 | 2015-08-30
| 3.12.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.12.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.13 | Port migration at CT AST - DC2 (Total Ports - 2445) | 2015-02-02 | 2015-08-30
| 3.13.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.13.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.14 | Port migration at CT AST - DC6 (Total Ports - 1360) | 2015-02-02 | 2015-08-30
| 3.14.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.14.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.15 | Port migration at CT iAD-22 (Total Ports - 798) | 2015-02-02 | 2015-08-30
| 3.15.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.15.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.16 | Port migration at CT iAD-23 (Total Ports - 508) | 2015-02-02 | 2015-08-30
| 3.16.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.16.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.17 | Port migration at CT iAD-25 (Total Ports - 828) | 2015-02-02 | 2015-08-30
| 3.17.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.17.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.18 | Port migration at CT iAD-27 (Total Ports - 793) | 2015-02-02 | 2015-08-30
| 3.18.1 | Production server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 3.18.2 | UAT server Migrations | 2015-02-02 | 2015-08-30 | Sunil/ Storage
| 4 | Closure | 2015-09-01 | 2015-12-15
Closure | 4.1 | Prepare and Approve MjRAD | 2015-09-01 | 2015-09-30 | PM/ Sponsor
| 4.2 | Project QA | 2015-09-30 | 2015-10-31 | PM/ QA
| 4.3 | Project Closure | 2015-11-01 | 2015-12-15 | PM

## CENTERA REFRESH
# | Info | Title | Expected Start | % Complete
0 |  | Centera Tech Refresh Phase 2
1 |  | Phase I: Planning and Design
2 |  | Delivery
3 |  | Singapore | 2013-07-09 08:00 | 100%
4 |  | Hong Kong | 2013-07-09 08:00 | 100%
5 |  | Activity and Task Planning
6 |  | Site Readiness Singapore | 2013-07-09 08:00 | 100%
7 |  | Site Readiness Hong Kong | 2013-07-09 08:00 | 100%
8 |  | Finalize CICM and Restore Plans | 2013-07-09 08:00 | 100%
9 |  | Phase II: Implementation and Migration
10 |  | Hardware installation and upgrades
11 |  | TRIMS/RAPIDS Cluster | 2013-11-26 08:00 | 100%
12 |  | Japan Documentum Cluster | 2013-11-26 08:00 | 100%
13 |  | ON-DEMAND/ROD/DOCUMENTUM Cluster | 2013-11-26 08:00 | 100%
14 |  | NICE Cluster | 2013-11-26 08:00 | 100%
15 |  | Migrations
16 |  | Nice Cluster
17 |  | Singapore
30 |  | Data Erasure Cubes 2, 1, 6, 5, 8, 7 | 2014-11-03 | 100%
31 |  | Roll out Cubes 2, 1, 6, 5, 8, 7 | 2014-11-03 | 100%
32 |  | Hong Kong
45 |  | Data Erasure Cubes 2, 1, 6, 5, 8, 7 | 2014-11-10 | 100%
46 |  | Roll out Cubes 2, 1, 6, 5, 8, 7 | 2014-11-10 | 100%
47 |  | TRIMS/RAPIDS Cluster
48 |  | Singapore Cluster #0682 Restore Activities | 2014-11-27 13:00 | 100%
49 |  | Hong Kong Cluster #0693 Replication Activities | 2014-11-27 13:00 | 100%
50 |  | Cutover and Data Verification | 2014-11-27 13:00 | 100%
51 |  | Data erasure | 2014-12-05 | 100%
52 |  | Roll out | 2014-12-05 | 0%
53 |  | OnDemand Cluster
54 |  | Singapore @ TPK - Restore #1758 --> #0215 | 2014-11-27 13:00 | 100%
55 |  | Singapore @ CT2 - Restore #1756 --> #0031 | 2014-11-27 13:00 | 100%
56 |  | Hong Kong - Replication #0031 --> #0651 | 2014-11-27 13:00 | 100%
57 |  | Cutover and Data Verification | 2015-03-27 13:00 | 100%
58 |  | Data Erasure | 2014-12-05 | 100%
59 |  | Roll out | 2014-12-05 | 0%
60 |  | Phase III: Documentation, Functional Overview, and Acceptance
61 |  | Perform Operational Review and Functional Overview | 2014-12-05 | 0%
62 |  | Project closeout, review, and sign-off | 2014-12-05 | 0%

## INDIA TECH REFRESH
# | Info | Title | Expected Start | % Complete
0 |  | Mumbai Tech Refresh
1 |  | VMAX SE Relocation from NKP to FIFC
2 |  | Phase I: Planning and Design
3 |  | Delivery of Temporary Infrastructure to FIFC
4 |  | VMAX 10K | 2013-08-12 13:00 | 100%
5 |  | MDS 95xx | 2013-08-12 13:00 | 100%
6 |  | FCIP or DWDM Link | 2013-08-12 13:00 | 100%
7 |  | Activity and Task Planning
8 |  | Site Readiness Mumbai Site NKP | 2013-08-12 13:00 | 100%
9 |  | Site Readiness Mumbai Site FIFC | 2013-08-12 13:00 | 100%
10 |  | Backup and Restore Infrastructure | 2013-08-12 13:00 | 100%
11 |  | Finalize Configuration Guide for Implementation and Migration | 2013-08-12 13:00 | 100%
12 |  | Phase II: Implementation and Migration
13 |  | Phase 1 - Implementating VMAX 10K and SAN Infrastructure @ FIFC | 2013-09-09 13:00 | 100%
14 |  | Roll In, Power up and Configuration | 2013-09-09 13:00 | 100%
15 |  | Phase 2 - Establishing SRDF/A via DWDM or FCIP between Site NKP and FIFC
16 |  | SRDF/A between VMAX SE and VMAX 10K | 2013-09-11 08:00 | 100%
17 |  | Pair and syncronize devices | 2013-09-11 08:00 | 100%
18 |  | Phase 3 - Server Relocation to FIFC
19 |  | 14 Equity servers | 2013-09-20 13:00 | 100%
20 |  | Data Verification and UAT | 2013-09-20 13:00 | 100%
21 |  | 12 GWM Servers | 2013-09-20 13:00 | 100%
22 |  | Data Verification and UAT | 2013-09-20 13:00 | 100%
23 |  | Phase 4 - Relocation of VMAX SE and MDS 9222i to FIFC
24 |  | Secure Data Erasure | 2013-09-23 13:00 | 100%
25 |  | Power Down and relocate VMAX SE and MDS 9222i | 2013-09-26 13:00 | 100%
26 |  | Relocation, Power Up and configuration of VMAX SE and MDS 9222i at FIFC | 2013-09-26 13:00 | 100%
27 |  | Stabilization period | 2013-09-27 13:00 | 100%
28 |  | Establish SRDF/A Pairing | 2013-09-27 13:00 | 100%
29 |  | Phase 5 - Server cutover to VMAX SE
30 |  | 14 Equity servers | 2013-10-03 13:00 | 100%
31 |  | Data Verification and UAT | 2013-10-03 13:00 | 100%
32 |  | 12 GWM Servers | 2013-10-03 13:00 | 100%
33 |  | Data Verification and UAT | 2013-10-03 13:00 | 100%
34 |  | Stabilization period | 2013-10-04 13:00 | 100%
35 |  | Phase 6 - Decommisioning VMAX 10K and MDS 95xx
36 |  | Secure Data Erasure | 2014-12-01 | 0%
37 |  | Power Down and roll out VMAX 10K and MDS 95xx | 2014-12-01 | 0%
38 |  | Phase III: Documentation, Functional Overview, and Acceptance
39 |  | Perform Operational Review and Functional Overview | 2014-12-01 | 0%
40 |  | Project closeout, review, and sign-off | 2014-12-01 | 0%
41 |  | ICG Chennai MER CX700 Tech Refresh
42 |  | Phase I: Planning and Design
43 |  | Delivery of VNX5100 | 2013-08-12 13:00 | 100%
44 |  | Site Readiness Chennai Site MER | 2013-08-12 13:00 | 100%
45 |  | Backup and Restore Infrastructure | 2013-08-12 13:00 | 100%
46 |  | Phase II: Implementation and Migration
47 |  | Roll In, Power up and Configuration | 2013-09-03 08:00 | 100%
48 |  | FC Cabling | 2013-09-04 08:00 | 100%
49 |  | Host Connectivity | 2013-09-10 08:00 | 100%
50 |  | Host Based Migration | 2013-09-11 08:00 | 100%
51 |  | Host Based Replication to Mumbai Site FIFC | 2013-09-11 08:00 | 100%
52 |  | Decommisioning CX700
53 |  | Secure Data Erasure | 2014-12-01 | 0%
54 |  | Power Down and roll out | 2014-12-01 | 0%
55 |  | Phase III: Documentation, Functional Overview, and Acceptance
56 |  | Perform Operational Review and Functional Overview | 2014-12-01 | 0%
57 |  | Project closeout, review, and sign-off | 2014-12-01 | 0%
58 |  | HDS9990+CX300 Technology Refresh for Mumbai Site NKP
59 |  | Phase I: Planning and Design
60 |  | Delivery of VMAX10K to NKP | 2013-08-12 13:00 | 100%
61 |  | Site Readiness Mumbai Site NKP | 2013-08-12 13:00 | 100%
62 |  | Backup and Restore Infrastructure | 2013-08-12 13:00 | 100%
63 |  | Phase II: Implementation and Migration
64 |  | Roll In, Power up and Configuration | 2013-09-10 08:00 | 100%
65 |  | FC Cabling | 2013-09-10 08:00 | 100%
66 |  | Host Connectivity | 2013-09-10 08:00 | 100%
67 |  | Open Replictor Migration | 2013-09-11 08:00 | 100%
68 |  | Server Cutover | 2013-09-24 08:00 | 100%
69 |  | Decommisioning HDS9990+CX300
70 |  | Secure Data Erasure | 2014-12-01 | 0%
71 |  | Power Down and roll out | 2014-12-01 | 0%
72 |  | Phase III: Documentation, Functional Overview, and Acceptance
73 |  | Perform Operational Review and Functional Overview | 2014-12-01 | 0%
74 |  | Project closeout, review, and sign-off | 2014-12-01 | 0%
75 |  | VMAX10K COB at Chennei Site MER
76 |  | Phase I: Planning and Design
77 |  | Delivery of VMAX10K to MER | 2013-08-12 13:00 | 100%
78 |  | Site Readiness Chennei Site MER | 2013-08-12 13:00 | 100%
79 |  | Backup and Restore Infrastructure | 2013-08-12 13:00 | 100%
80 |  | Phase II: Implementation and Migration
81 |  | Roll In, Power up and Configuration | 2013-09-10 08:00 | 100%
82 |  | FC Cabling | 2013-09-10 08:00 | 100%
83 |  | SRDF/A Replication from VMAX10K Mumbai Site NKP | 2013-09-10 08:00 | 100%
84 |  | Open Replictor Migration | 2013-09-10 08:00 | 100%
85 |  | Host Connectivity | 2013-09-23 13:00 | 100%
86 |  | Server Cutover | 2013-09-23 13:00 | 100%
87 |  | Decommisioning HDS9990+CX300+USP VM
88 |  | Secure Data Erasure | 2014-12-01 | 0%
89 |  | Power Down and roll out | 2014-12-01 | 0%
90 |  | Phase III: Documentation, Functional Overview, and Acceptance
91 |  | Perform Operational Review and Functional Overview | 2014-12-01 | 0%
92 |  | Project closeout, review, and sign-off | 2014-12-01 | 0%
93 |  | Delhi CX300 Tech Refresh
94 |  | Phase I: Planning and Design
95 |  | Delivery of VNX5100 | 2013-08-12 13:00 | 100%
96 |  | Site Readiness Delhi Site | 2013-08-12 13:00 | 100%
97 |  | Backup and Restore Infrastructure | 2013-08-12 13:00 | 100%
98 |  | Phase II: Implementation and Migration
99 |  | Roll In, Power up and Configuration | 2013-09-03 08:00 | 100%
100 |  | FC Cabling | 2013-09-03 08:00 | 100%
101 |  | Host Connectivity | 2013-09-03 08:00 | 100%
102 |  | Host Based Migration | 2013-09-04 08:00 | 100%
103 |  | Decommisioning CX700 | 2013-09-18 08:00 | 100%
104 |  | Secure Data Erasure | 2014-12-01 | 0%
105 |  | Power Down and roll out | 2014-12-01 | 0%
106 |  | Phase III: Documentation, Functional Overview, and Acceptance |  | 0%
107 |  | Perform Operational Review and Functional Overview | 2014-12-01 | 0%
108 |  | Project closeout, review, and sign-off | 2014-12-01 | 0%

## NAS Phase2
# | Info | Title | Expected Start | % Complete
0 |  | NAS Tech Refresh Phase 2
1 |  | Phase I: Planning and Design
2 |  | Delivery
3 |  | Singapore | 2014-11-27 | 100%
4 |  | Hong Kong | 2014-12-05 | 0%
5 |  | China | 2015-01-16 | 0%
6 |  | Japan | 2015-01-16 | 0%
7 |  | Korea | 2015-01-16 | 0%
8 |  | Taiwan | 2015-01-16 | 0%
9 |  | Indonesia | 2015-01-16 | 0%
10 |  | Australia | 2014-11-05 | 100%
11 |  | India | 2014-11-16 | 100%
12 |  | Activity and Task Planning
13 |  | Site Readiness
14 |  | IP Addresses | 2014-01-30 | 0%
15 |  | Network Connectivity | 2014-01-30 | 0%
16 |  | WAN Link | 2014-01-30 | 0%
17 |  | Power Requirements | 2014-01-30 | 0%
18 |  | Rack Locations | 2014-01-30 | 0%
19 |  | Migration Infrastructure
20 |  | Servers for EMCopy and CAVA | 2014-01-30 | 0%
21 |  | Finalize Configuration Guide for Implementation and Migration
22 |  | Hostname changes - impact and contingencies | 2014-01-30 | 0%
23 |  | Usage of DFS for multiple file shares | 2014-01-30 | 0%
24 |  | CATE Standard applied
25 |  | Layout | 2014-01-30 | 0%
26 |  | Network connectivity - FSN & Aggregation | 2014-01-30 | 0%
27 |  | CAVA Exclusions | 2014-01-30 | 0%
28 |  | DART Codes | 2014-01-30 | 0%
29 |  | VDM Segregation | 2014-01-30 | 0%
30 |  | Tree Quota | 2014-01-30 | 0%
31 |  | Special sizing requirements | 2014-01-30 | 0%
32 |  | Data Segregation
33 |  | Home Directories | 2015-02-15 | 0%
34 |  | Migration Plans
35 |  | Copy baselines | 2015-02-20 | 0%
36 |  | Segregation Tracking sheet | 2015-02-20 | 0%
37 |  | Tools - EMCopy, Beyond Compare | 2015-02-20 | 0%
38 |  | Data integrity and security verification | 2015-02-20 | 0%
39 |  | Phase II: Implementation and Migration Via EMCopy
40 |  | Singapore | 2015-03-01 | 0%
41 |  | Hong Kong | 2015-03-01 | 0%
42 |  | China | 2015-03-01 | 0%
43 |  | Japan | 2015-03-01 | 0%
44 |  | Korea | 2015-03-01 | 0%
45 |  | Taiwan | 2015-03-01 | 0%
46 |  | Indonesia | 2015-03-01 | 0%
47 |  | Australia | 2015-03-01 | 0%
48 |  | India | 2015-03-01 | 0%
49 |  | Phase III: Documentation, Functional Overview, and Acceptance
50 |  | Perform Operational Review and Functional Overview | 2105-07-01 | 0%
51 |  | Project closeout, review, and sign-off | 2105-07-01 | 0%