## Sheet1
|  |  |  | EMEA | Installs | Tracker |  |  |  |  | 2014
[11 empty] | Total Installs: 28 |  | On-Hold: 0 | Live: 18
Item ID | Location | Description | Vendor | Array/Switch Type | Array/Switch - Serial # | Usable TB or Ports | EMC Notes | Agreed VMAX Install Dates | EMC ESRS - Configured | EMC BIN Applied | Proposed/Live/OnHold | Priority | Vendor Engagement Date | % age done | Status | PO Received by Supplier | Delivery & Power Up | Network and FC Cabling | Firewall Rules SetUp | Citi Audit Check-List and Hand Over to BAU - Y/N | Citi-Audit Inventory Updated - Y/N | Comments
1 | CGC | 2014 Tech Refresh Project | EMC | VMAX40k (Silver Non Rep). 4 Engine - 5 Bay FAST | CK295700703 | 217 | 23/06: Instalation completed16/06: Bin loads to be completed by the close of this week. 10/06: Box has now been cabled and made ready for Bin file deployment. 09/06: Array has been positioned and powered on. Cabling has been started. 03/06: Lupprians has been scheduled for Sat 7th June. 20/05: Apeture updates have been applied, but no dates as to when these will be ready. Sal to chase up on issues stopping these installs commencing. Power, Floor cut out's, Which way to face the array's and which array will be place in which floor location. Once these items are addressed and agreed dates for their resolution EMC and Citi can plan the remaining install activities for EMC. 19/05: No citi attendance at weekly call. 15/05: Response issued to Sal and Simon -covering installs. BIN Spec Supllied by Simon 12/05: MT to request resource for this weekend to complete this install | 2014-05-17 | Yes | Due 19/06/14 | Live | Med |  | 50% | Green | No. 14/05/14 - Following up with Gary B. | Powered Up 8th June May 2014 | What core switches will we need for connections - as well as # of CPS and coppers ports? - KV to send reply to DCSM and Cabling team. 25/02/14 |  | N | N | 09/06/14 - Located in place and powered up - now awaiting FC cabling work. FC cabling to be carried out weekend of 21st/22nd June. 02/07/14 - SG working on final config tasks. To go live 5th/6th July. SG to complete Installation Checklist once handed over for BAU/Prod use. 18/07/14 - All work completed and handed over for Prod use. Exceptions are that Log Review config and addition to ECC still pending. Harbinder, to complete Checklist.
2 | CGC | 2014 Tech Refresh Project | EMC | VMAX40k – 4Engine 5 bay - Silver-Replicated. Paired with array - CK295700688 | CK295700705 | 152 | 16/06: Bin loads to be completed by the close of this week. 10/06: Box has now been cabled and made ready for Bin file deployment. 09/06: Array has been positioned and powered on. Cabling has been started. 03/06: Lupprians has been scheduled for Sat 7th June. 20/05: Apeture updates have been applied, but no dates as to when these will be ready. Sal to chase up on issues stopping these installs commencing. Power, Floor cut out's, Which way to face the array's and which array will be place in which floor location. Once these items are addressed and agreed dates for their resolution EMC and Citi can plan the remaining install activities for EMC. 19/05: No citi attendance at weekly call. 15/05: Response issued to Sal and Simon -covering installs. BIN Spec Supllied by Simon 12/05: MT to request resource for this weekend to complete this install | 2014-05-17 | Yes | Due 19/06/14 | Live | Med |  | 50% | Green | No. 14/05/14 - Following up with Gary B. | Powered Up 8th June May 2014 | What core switches will we need for connections - as well as # of CPS and coppers ports? - - KV to send reply to DCSM and Cabling team. 25/02/14 |  | N | N | 09/06/14 - Located in place and powered up - now awaiting FC cabling work. FC cabling to be carried out weekend of 21st/22nd June. 02/07/14 - SG working on final config tasks. To go live 5th/6th July. ZK to complete Installation Checklist once handed over for BAU/Prod use.
3 | RDC | 2014 Tech Refresh Project | EMC | VMAX40k – 4Engine 5 bay - Silver-Replicated | CK295700688 | 217 | 20/05: BIN File to be prepare on the basis of what Simon has supplied and past history. Bin File to be update this week, with view Bin File Deployment next week. 19/05: No citi attendance at weekly call. 15/05: Box pre-installation work completed - BIN file spec to be provided by Citi. EMC to complete drive swap (Compass drive issue ). Jon will complete the drive swaps in W/c 19th May 2014. BIN Spec Supllied by Simon 12/05: Dates to be confirmed by Citi with 10 working days lead time. | TBC |  |  | Live | Med |  | 50% | Green | yes | Power Up 3rd May 2014. EMC to bolt together during week prior to weekend. | REPLICATED GBOKE002R0688 169.186.192.185 Netmask 255.255.255.192 Gateway: 169.186.192.129 |  | N | N | 14/05/14 - Powered up. Now work on going with install and configuration. 02/07/14 - SG working on final config tasks. To go live 5th/6th July. SG to complete Installation Checklist once handed over for BAU/Prod use. 18/07/14 - All work completed and handed over for Prod use. Exceptions are that Log Review config and addition to ECC still pending. Zbyszek to complete Checklist.
4 | RDC | 2014 Tech Refresh Project | EMC | VMAX40k – 4Engine 5 bay FAST - Silver-Non-Replicated | CK295700669 CK295700699 | 217 | 23/06: Connectrix frames still in the way of the VMAX deployments. Citit to arrange getting these moved. 16/06: Jon to check and feedback. Simon has confirmed no urgency, but keen to get the completed. 03/06: No change connectrix frame still in the way. 20/05: No dates yet available - Sal to work getting dates for the Connetrix frame move sorted. 15/05: Array has Connectrix frame in the final position to be removed by Citi. Dates to be agreed? BIN Spec Supllied by Simon 12/05: Dates to be confirmed by Citi with 10 working days lead time. | TBC |  |  | Live | Med |  | 50% | Green | yes | Power Up dependent on moving McData Racks first in order to make space. |  |  | N | N | 14/05/14 - Power Up dependent on moving McData Racks first in order to make space. 02/07/14 - DCSM planning to move into final location in CGc for the weekend of the 5th/6th July. Therefore, Go-Live expected 12th/13th July 2014. 18/07/14 - Cabling work still pending. Final LAN cables expected to be fitted and connected on 26th/27th July 2014. Therefore, go-live now expected 01/08/14. 29/07/14 – will be availble by this weekend
5 | RDC | Silver Replicated Project. Paired with - DEOLE002R0710 | EMC | VMAX40k - 4Engine 3 bay - Silver Replicated | CK295700689 (GBOKE002R0689) | 98 | Completed | n/a | Yes | Yes | Complete | High |  | 95% | Green | yes | Delivered & Powered Up |  | IP addresses for Service Processor - ZK to follow up. SA to forward exact location details and subnet info. CK295700689 – GBOKE002R0689 – 169.186.192.186 Netmask 255.255.255.192, gateway 169.186.192.129 | N | N | Installation Checklist - SG to complete. Handed over for Prod/BAU - 2nd May 2014. Ashok, has completed Checklist with L2.
6 | RDC | Silver Replicated Project. Paired with DEOLE003R0712 | EMC | VMAX40k - 4Engine 3 bay - Silver Replicated | CK295700706 (GBOKE003R0706) | 98 | Completed | n/a | Yes | Yes | Complete | High |  | 95% | Green | yes | Power Up - 26th April 2014 |  | IP addresses for Service Processor - ZK to follow up. SA to forward exact location details and subnet info. CK295700689 – GBOKE002R0689 – 169.186.192.186 Netmask 255.255.255.192, gateway 169.186.192.129 | N | N | Installation Checklist - SG to complete. Handed over for Prod/BAU - 2nd May 2014. Krishnam, has completed handover checklist with L2.
7 | RDC |  | EMC | VMAX40k – 4Engine 5 bay FAST - Silver Non-Replicated | CK295700704 | 217 | 23/06: Box fully installed. 16/06: Cabling still needs to be checked. Simon will chase if not there! 03/06: IP cable not yet supllied, Citi need to provide IP cable before config can be completed for ESRS. 20/05: Device name is wrong in the apeture ticket. Bin File to written and submitted this week to CCA. With a view to install 28th May. 19/05: No citi attendance at weekly call. 15/05: Box pre-installation work completed - BIN file spec to be provided by Citi. EMC to complete drive swap (Compass drive issue ). Jon will complete the drive swaps in W/c 19th May 2014. BIN Spec Supllied by Simon 12/05: Dates to be confirmed by Citi with 10 working days lead time. | TBC |  |  | Live | Med |  | 50% | Green | yes | Power Up 3rd May 2014. EMC to bolt together during week prior to weekend. | NONREP GBOKE004N0704 169.186.192.183 For both: Netmask 255.255.255.192 Gateway: 169.186.192.129 |  | N | N | 14/05/14 - Powered on, fibre cabling in place but unable to connect cables as the Aperture ticket hasn’t been raised. 09/06/14 - Aperture requests in place now awaiting FC cabling to be completed. 02/07/14 - SG working on final config tasks. To go live 5th/6th July. SG to complete Installation Checklist once handed over for BAU/Prod use. 18/07/14 - All work completed and handed over for Prod use. Exceptions are that Log Review config and addition to ECC still pending. Harbinder, to complete Checklist.
8 | FDC |  | EMC | VMAX40k – 4Engine 5 bay FAST - Silver Non-Replicated | CK295700709 (DEOLE002N0709) | 317 | 20/05: Dial home is working. Citi to now move this into Production. 15/05: Dial home not yet working, but being investigated by EMC Customer Services. 12/05: MT to check with Olga | 2014-05-12 |  |  | Complete | Med |  | 95% | Green | yes | Power Up 10th May 2014 - TBC |  |  | N | N | 14/05/14 - Have Apertures for Cabling work been raised?? 19/06/14 - Up and running already in SANScreen. Pending ECC and Log Review Checks. SG to complete Checklist.
9 | FDC | Silver Replicated Project. Paired with GBOKE002R0689 | EMC | VMAX40k – 4Engine 5 bay - Silver Replicated | CK295700710 (DEOLE002R0710) |  | Completed | n/a | Yes | Yes | Complete | High |  | 95% | Green | yes | Delivered & Powered Up |  | IP addresses for Service Processor - ZK to follow up. SA to forward exact location details and subnet info. CK295700710 – DEOLE002R0710 – 10.159.28.75 Netmask 255.255.255.224, gateway 10.159.28.65 | N | N | Installation Checklist - Ashok to complete. 18/07/14 - Checklist done and now being verified by L2 Ashok, has completed checklist with L2
10 | FDC | Silver Replicated Project. Paired with GBOKE003R0706 | EMC | VMAX40k – 4Engine 5 bay - Silver Replicated | CK295700712 (DEOLE003R0712) |  | Completed | n/a | Yes | Yes | Complete | High |  | 75% | Green | yes | Power Up - 26th April 2014 |  | IP addresses for Service Processor - ZK to follow up. SA to forward exact location details and subnet info. CK295700712 – DEOLE003R0712 – 10.159.28.76 Netmask 255.255.255.224, gateway 10.159.28.65 | N | N | Installation Checklist - SG to complete.
11 | RDC | 2014 Tech Refresh Project | EMC | VMAX40k – 4Engine 5 bay FAST - GOLD Non-Replicated | CK295700485 | 217 | 23/06: Connectrix frames still in the way of the VMAX deployments. Citit to arrange getting these moved. 16/06: Jon to check and feedback. Simon has confirmed no urgency, but keen to get the completed. 03/06: No change connectrix frame still in the way. 20/05: No dates available - Sal to work getting dates for the Connetrix frame move sorted. 15/05: Array has Connectrix frame in the final position to be removed by Citi. Dates to be agreed? BIN Spec Supllied by Simon 12/05: Dates to be confirmed by Citi with 10 working days lead time. | TBC |  |  | Live | High |  | 50% | Red | yes | Power Up dependent on moving McData Racks first in order to make space. |  |  | N | N | 14/05/14 - Power Up dependent on moving McData Racks first in order to make space. 02/07/14 - DCSM suggested that we perform the location task separately i.e. do 3 bays first and the remaining 2 bays. SG to find out with EMC if this is feasible. Also, need to factor in the actual need for GOLD (non-rep) storage. As of yet there is no need for such tier of storage from any clients. 29/07/14 – Middle of August 2014 05/08/2014 - cabling request need to raise
12 | RDC | Leg1A and 2A Rainbow Project | EMC | VMAX40k – 4Engine 5 bay - Silver Replicated | CK295700671 | 98 | Completed |  | Yes | Yes | Complete | High |  | 100% | Green | Yes | All Completed | Installed & Configured | Installed & Configured | Y | Y | Installation Checklist completed and Approved by SAN Management Team.
13 | FDC | 2014 Tech Refresh Project | EMC | VMAX40k – 4Engine 5 bay FAST - GOLD Non-Replicated | CK295700713 | 217 | 03/06: MT to chase the status of this install. 20/05: Jon to re-write Bin File and re-submit to CCA. 19/05: No citi attendance at weekly call. 15/05: BIN file written and in CCA for approval, Array physical moced scheduled for 15th May 2014 and engineer has been booked as requested for 31st May 2014 install. 12/05: Mt to request resource for 31/05/14. Simon to provide BIN file requirements before clos of week. | May 31st 2014 |  |  | Live | High |  | 50% | Red | yes | Power Up 31st May 2014 - TBC |  | NONREP DEOLE003N0713 10.159.28.78 Gateway is 10.159.28.65 And Netmask is 27 bit (255.255.255.224) | N | N | 14/05/14 - Have Apertures for Cabling work been raised?? 02/07/14 - SG working on final config tasks. To go live 5th/6th July. SG to complete Installation Checklist once handed over for BAU/Prod use.
14 | FDC | Leg1A and 2A Rainbow Project | EMC | VMAX40k – 4Engine 3 bay - Silver Replicated | CK295700667 | 98 | Completed |  | Yes | Yes | Complete | High |  | 100% | Green | Yes | All Completed | Installed & Configured | Installed & Configured | Y | Y | Installation Checklist completed and Approved by SAN Management Team.
15 | RDC | 2014 Tech Refresh Project | EMC/Cisco | 4 x MDS-PBFADV48U – 48 port advanced modules | FOX1648Q0MY | Existing MDS9513 | Completed |  |  |  | Live | Med |  | 50% | Green | N/A |  |  |  | N | N
16 | RDC | 2014 Tech Refresh Project | EMC/Cisco | 4 x MDS-PBFADV48U – 48 port advanced modules | FOX1648Q0MQ | Existing MDS9513 | Completed |  |  |  | Live | Med |  | 50% | Green | N/A |  |  |  | N | N
17 | RDC | 2014 Tech Refresh Project | EMC/Cisco | 8 x MDS9148 | AMS17100641 | 8 x new 9148 – 48 fixed ports switches | Completed |  | Yes | n/a | Live | Med |  | 50% | Green | N/A |  |  |  |  | N
[5 empty] | AMS17080867 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17100246 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17100429 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17100422 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17080809 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17080940 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
[5 empty] | AMS17100432 |  | Completed |  | Yes | n/a | Live | [9 empty] | N
18 | FDC | 2014 Tech Refresh Project | EMC/Cisco | 8 x MDS9148 | AMS17170240 | 8 x new 9148 – 48 fixed ports switches | 20/05: Citi not ready yet. | t.b.c | No | n/a |  | Med |  | 50% | Green | N/A |  |  |  |  | N
[5 empty] | AMS17170632 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170644 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170083 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170603 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170588 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170583 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
[5 empty] | AMS17170602 |  | 20/05: Citi not ready yet. | t.b.c | No | n/a | [10 empty] | N
19 | RDC | McData Decom Project | EMC/Cisco | 6 pairs x MDS9148 | AMS17170240 AMS17170632 AMS17170644 AMS17170083 AMS17170603 AMS17170588 AMS17170583 AMS17170602 | 6 new pairs x 9148 – 48 fixed ports switches | Completed |  |  |  | Complete | High |  | 100% | Green | yes | All Completed | Installed & Configured | Installed & Configured |  | N
20 | RDC | VNX for Exchange Project | EMC | VNX for RDC | RDC - CKM00121300390 RDC - CKM00121201737 |  | Completed |  |  |  | Complete | High |  | 0% | Green | N/A | N/A | N/A | N/A |  | N | Completed 10-11 May 2014
21 | RDC | VNX for Exchange Project | EMC | VNX for FDC | FDC - CKM00121400374 FDC - CKM00121400375 |  | 23/06: No progress on this issue at this stage. Citi to agree next steps. 16/06: Witek to decide which way to go, all information has been provide. Cat have come back and said they will not be supporting this for another 2 months. Meeting to be held on Wednesday this week to agree way forward. 03/06: Wrong code level was specified, awaiting a confirmation Citi on next steps. 20/05: Schedule for this weekend upgrade of code. Notes to be added to service request that local on site engineer maybe needed in case failure. RCM to pre-copy upgrade files before upgrade window. Aran/dirk to provide standby engineer name. |  |  |  | Live | High |  | 0% | Green | N/A | N/A | N/A | N/A |  | N

## Sheet2
Green | N/A |  | Low | Live | Storage | Yes | FDC
Amber | Salauddin Ahmed | Chris Marshall | Med | On-Hold | Switch | No | RDC
Red | SMART421 | Colin Mead | High | Proposed |  |  | CGC
N/A | Krishnam Vathsavai | Thomas Hans |  | Complete
| Simon Gibbs | Self Managed
Dawid Orczyk
Zbigniew Klos
Harbinder Dhinsa
Other
SAN Projects
SAN BAU Operations
??? - TBD
Primary Resource
Secondary Resource