## Rainbow Server Info. Leg1-Leg2
Env Label | Description | Type | Existing Server? | Hostname | Server Model | O/S | STORAGE FRAME | Remarks | RU/CZ Cluster | RU/CZ Standalone | UKC-Cluster | UKC- Standalone | OCI-F2F-Cluster | OCI-F2F Standalone | TCRS to be raise for Total Requirment for Wave-2 | Storage - Aug 2013 | Leg1-Cluster | Leg2 | Leg2-Cluster | Non-Replicated(#3004) | Non-Replicated - Cluster(#3004) | Storage Match for all servers | Storage Match - 27TB Excel | Diff. | Migration type | Aperture rqs for storage config | Migration RFC# | Migration target date | Migration status | Storage release Aperture / RFC# | Storage release target date | Storage release status
PAT | Oracle RAC -CLMS, CitiPlanner, TCON, URS, CitiOption, citiwatch | DB | Yes - Outside this BoM | fdcgcgracad31p | IBM p7 p795 | AIX 6.1 | NR | NA | [7 empty] | 202.3008 | 0 | 0 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A |  |  |  |  | planning
PAT | Oracle RAC -CLMS, CitiPlanner, TCON, URS, CitiOption, citiwatch | DB | Yes - Outside this BoM | fdcgcgracad32p | IBM p7 p795 | AIX 6.1 | NR | NA | [7 empty] | 202.3008 | 0 | 0 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A |  |  |  |  | planning
PAT | Oracle RAC IVR , ESB, MemFis, WPS, | DB | Yes - Outside this BoM | fdcgcgracad33p | IBM p7 p795 | AIX 6.1 | NR | NA | [7 empty] | 202.3008 | 0 | 0 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A |  |  |  |  | planning
PAT | Oracle RAC IVR , ESB, MemFis, WPS, | DB | Yes - Outside this BoM | fdcgcgracad34p | IBM p7 p795 | AIX 6.1 | NR | NA | [7 empty] | 202.3008 | 0 | 0 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A |  |  |  |  | planning
PAT/PROD | BOXI | AP | Yes - Outside this BoM | fdcgcgboxaa01p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | 90 | 30 | 60 |  |  |  | 180 | 202.3008 | 0 | 0 | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 |  |  |  |  | planning
PAT/PROD | BOXI | AP | Yes - Outside this BoM | fdcgcgboxaa02p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration |  | 30 |  |  |  |  | 30 | 202.3008 | 0 | 0 | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 |  |  |  |  | planning
PAT/PROD | CMR AB Initio 1 | AP | Yes - Outside this BoM | fdcgcgcmraa01p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  |  | 360 |  |  |  | 360 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0 |  |  |  |  | planning
PAT/PROD | CMR AB Initio 2 | AP | Yes - Outside this BoM | fdcgcgcmraa02p | IBM p7 p795 | AIX 6.1 | LEG1 | [7 empty] | 0 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - UAE, UK IPB (Primary) | AP | Yes - Outside this BoM | fdcgcgetlaa01p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration |  |  | 400 |  |  |  | 400 | 641.67 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 607.9532 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - UAE, UK IPB (Secondary) | AP | Yes - Outside this BoM | fdcgcgetlaa02p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 33.7168 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 0 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - Hungary,Czech (Secondary) | AP | Yes - Outside this BoM | fdcgcgetlaa03p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | 400 |  | 0 |  |  |  | 400 | 843.97 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 810.2532 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier Hungary,Czech (Primary) | AP | Yes - Outside this BoM | fdcgcgetlaa04p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration |  |  | 0 |  |  |  |  | 33.7168 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 0 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - Poland (Seconday) | AP | Yes - Outside this BoM | fdcgcgetlaa05p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 1316 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 1282.2832 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - Poland (Primary) | AP | Yes - Outside this BoM | fdcgcgetlaa06p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 33.7168 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 0 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - , , Czech HA -(Secondary) | AP | Yes - Outside this BoM | fdcgcgetlaa07p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 203 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 169.2832 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - , , Czech -DEDICATED I/O | AP | Yes - Outside this BoM | fdcgcgetlaa08p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 33.72 | 0 | 0 | #N/A | #N/A | #N/A | 33.7168 | 33.7168 | 0.0032031 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier Russia (Primary) | AP | Yes - Outside this BoM | fdcgcgetlaa09p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | 1100 |  | 0 |  | 200 |  | 1300 | 978 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 134.8672 | 843.1328 |  |  |  |  | planning
PAT/PROD | ETL Engine Tier - Russia (Secondary) | AP | Yes - Outside this BoM | fdcgcgetlaa10p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration |  |  | 0 |  |  |  |  | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 134.8672 | 0
PAT/PROD | ETL -Service Tier Active -Active | WW | Yes - Outside this BoM | fdcgcgetlaa15p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration | [7 empty] | 236.0176 | 0 | 0 | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0
PAT/PROD | ETL -Service Tier Active -Active | WW | Yes - Outside this BoM | fdcgcgetlaa16p | IBM p7 p780 | AIX 6.1 | LEG2 | 2013-12-08 | [7 empty] | 236.0176 | 0 | 0 | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | Kana Connect/Response | AP | Yes - Outside this BoM | fdcgcgkanaa01p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 60 |  |  |  |  | 60 | 438.3184 | 0 | 0 | #N/A | #N/A | #N/A | 438.3184 | 0 | 0 |  |  |  | 2013-12-08
PAT/PROD | Kana Webserver - DMZ 1 | WW | Yes - Outside this BoM | fdcgcgkanaw01p | IBM p7 p795 | AIX 6.1 | standalone | [8 empty] | #N/A | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | #N/A |  |  |  | 2013-12-08
PAT/PROD | Kana Webserver - DMZ 2 | WW | Yes - Outside this BoM | fdcgcgkanaw02p | IBM p7 p795 | AIX 6.1 | standalone | [8 empty] | #N/A | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | #N/A |  |  |  | 2013-12-08
PAT/PROD | Kana Websphere | AP | Yes - Outside this BoM | fdcgcgkanaw03p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 60 |  |  |  |  | 60 | 236.0176 | 0 | 0 | #N/A | #N/A | #N/A | 236.0176 | 0 | 0 |  |  |  | 2013-12-08
PAT/PROD | Kana Websphere | AP | Yes - Outside this BoM | fdcgcgkanaw04p | IBM p7 p795 | AIX 6.1 | LEG2 | 2013-12-08 |  | 60 |  |  |  |  | 60 | 337.168 | 0 | 0 | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | DWH Portal- Active-Active | WW | Yes - Outside this BoM | fdcgcgporaw01p | IBM p7 p780 | AIX 6.1 | LEG1 | Confirmed - No Migration |  | 30 | 0 | 30 |  |  | 60 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 269.7344 | 0 |  |  |  | 2013-12-08
PAT/PROD | DWH Portal / SAS Web-Tier | WW | Yes - Outside this BoM | fdcgcgsasaw01p | IBM p7 p780 | AIX 6.1 | LEG2 | 2013-12-08 |  | 30 | 0 | 30 |  |  | 60 | 438.3184 | 0 | 0 | #N/A | #N/A | #N/A | 438.3184 | 438.3184 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | SAS - Meta Tier | AP | Yes - Outside this BoM | fdcgcgsasaa02p | IBM p7 p780 | AIX 6.1 | NR | 2013-12-01 |  | 60 |  | 30 |  |  | 60 | 337.168 | 0 | 0 | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | SAS - Compute Tier | AP | Yes - Outside this BoM | fdcgcgsasaa03p | IBM p7 p780 | AIX 6.1 | NR | 2013-12-01 |  | 700 |  | 700 |  |  | 1400 | 6945.6602 | 0 | 0 | #N/A | #N/A | #N/A | 6945.6602 | 6945.6602 | 0 | Storage | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | Integration Layer - Ab Initio - Node 1 | AP | Yes - Outside this BoM | fdcgcgrilaa01p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  |  | 100 |  |  |  | 100 | 101.1504 | 0 | 0 | #N/A | #N/A | #N/A | 101.1504 | 0 | 0 |  |  |  | SA to provide
PAT/PROD | Integration Layer - Ab Initio - Node 2 | AP | Yes - Outside this BoM | fdcgcgrilaa02p | IBM p7 p795 | AIX 6.1 | LEG1 | [8 empty] | 101.1504 | 0 | 0 | #N/A | #N/A | #N/A | 101.1504 | 0 | 0 |  |  |  | SA to provide
PAT/PROD | Integration Layer - Websphere - Node 1 | WW | Yes - Outside this BoM | fdcgcgrilaw01p | IBM p7 p795 | AIX 6.1 | LEG1 | [8 empty] | 101.1504 | 0 | 0 | #N/A | #N/A | #N/A | 101.1504 | 0 | 0 |  |  |  | SA to provide
PROD | CDE | AP | Yes - Outside this BoM | FDCGCGCDELA02P | BL460c | RHEL 5.6 | LEG2 | 2013-12-01 |  | 80 |  | 60 |  |  | 140 | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 269.7344 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PAT/PROD | Oracle HACMP - Tibco, RMAN | DB | Yes - Outside this BoM | fdcgcgticad01p | IBM p7 p780 | AIX 6.1 | LEG1 | [5 empty] | 90 |  | 90 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PAT/PROD | Oracle HACMP - Tibco, RMAN | DB | Yes - Outside this BoM | fdcgcgticad02p | IBM p7 p780 | AIX 6.1 | LEG1 | [7 empty] | 0 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC-ESB, MemFis, WPS | DB | Yes - Outside this BoM | fdcgcgdtgad14p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 630 |  | 300 |  | 90 | 1020 | 1756.46 | 0 | 1753.2734 | #N/A | 3.1582 | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC- Kana, WPS-Leg2 | DB | Yes - Outside this BoM | fdcgcgdtgad16p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 240 |  | 150 |  |  | 390 | 977.7871 | 0 | 977.7871 | #N/A | 3.1582 | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC-iProcess -Node | DB | Yes - Outside this BoM | fdcgcgdtgad18p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 730 |  | 300 |  | 400 | 1430 | 1382.3887 | 0 | 1382.3887 | #N/A | #N/A | #N/A | 3.1582 | 3.1582 | 1379.2305 |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC-Ci/SAO , Integration Layer | DB | Yes - Outside this BoM | fdcgcgdtgad20p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 930 |  | 400 |  |  | 1330 | 1921.8574 | 0 | 1921.8574 | #N/A | #N/A | #N/A | 3.1582 | 3.1582 | 1918.6992 |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC - EDW | DB | Yes - Outside this BoM | fdcgcgdtgad22p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 120 |  |  |  |  | 120 | 1416.1055 | 0 | 1416.1055 | #N/A | 3.1582 | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard -Oracle RAC - TCON, URS, CO,CW | DB | Yes - Outside this BoM | fdcgcgdtgad24p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 990 |  | 600 |  |  | 1590 | 2056.7246 | 0 | 2056.7246 | #N/A | 3.1582 | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard- Oracle RAC - COPS | DB | Yes - Outside this BoM | fdcgcgdtgad26p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 5470 |  | 1500 |  |  | 6970 | 7184.84 | 0 | 7080.5273 | #N/A | 104.3086 | #N/A | #N/A | 0 | #N/A |  |  |  | SA to provide
PROD | Dataguard-Oracle RAC - CLMS, CitiPlanner | DB | Yes - Outside this BoM | fdcgcgdtgad28p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 1230 |  | 700 |  |  | 1930 | 2124.1582 | 0 | 2124.1582 | #N/A | #N/A | #N/A | 3.1582 | 3.1582 | 2121 |  |  |  | SA to provide
PROD | Dataguard-Oracle RAC- ECR | DB | Yes - Outside this BoM | fdcgcgdtgad30p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed |  | 970 |  | 750 |  |  | 1720 | 2495.043 | 0 | 2495.043 | #N/A | #N/A | #N/A | 3.1582 | 3.1582 | 2491.8848 |  |  |  | SA to provide
PROD | Oracle RAC- IVR -NODE 1 | DB | Yes - Outside this BoM | fdcgcgracad01p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 180 |  | 60 |  |  |  | 240 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0 |  |  |  | SA to provide
PROD | Oracle RAC- IVR- NODE 2 | DB | Yes - Outside this BoM | fdcgcgracad02p | IBM p7 p795 | AIX 6.1 | LEG1 | [7 empty] | 0 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Dataguard-Oracle RAC - IVR -Node 1 | DB | Yes - Outside this BoM | fdcgcgracad03p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed | 180 |  | 60 |  |  |  | 240 | 134.8672 | 0 | 134.8672 | #N/A | #N/A | #N/A | 134.8672 | 134.8672 | 0
PROD | Dataguard-Oracle RAC - IVR -Node 2 | DB | Yes - Outside this BoM | fdcgcgracad04p | IBM p7 p795 | AIX 6.1 | LEG2 | Completed | [6 empty] | 0 | 134.8672 | 0 | 134.8672 | #N/A | #N/A | #N/A | 134.8672 | 134.8672 | 0
PROD | Oracle RAC - Eclipse/CMR -NODE 1 | DB | Yes - Outside this BoM | fdcgcgracad05p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 650 | 30 | 650 |  |  |  | 1330 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - Eclipse/CMR -NODE 2 | DB | Yes - Outside this BoM | fdcgcgracad06p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Dataguard-Oracle RAC- Eclipse/CMR -Node 1 | DB | Yes - Outside this BoM | fdcgcgracad07p | IBM p7 p795 | AIX 6.1 | LEG2 | 2013-11-16 | 650 | 30 | 650 |  |  |  | 1330 | 2127.32 | 0 | 168.584 | #N/A | #N/A | #N/A | 168.584 | 168.584 | 1958.736 | Storage | Completed | 17673239 |  | Completed |  |  | Completed
PROD | Dataguard-Oracle RAC- Eclipse/CMR -Node 2 | DB | Yes - Outside this BoM | fdcgcgracad08p | IBM p7 p795 | AIX 6.1 | LEG2 | 2013-11-16 |  | 30 |  |  |  |  | 30 | 168.584 | 0 | 168.584 | #N/A | #N/A | #N/A | 168.584 | 168.584 | 0 | Host | Completed | 17673239 |  | Completed |  |  | Completed
PROD | Oracle RAC - ESB, MemFis, WPS Node 1 | DB | Yes - Outside this BoM | fdcgcgracad13p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 600 | 30 | 300 |  | 90 |  | 1020 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - ESB, MemFis, WPS Node 2 | DB | Yes - Outside this BoM | fdcgcgracad14p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - Kana, WPS-Leg2-Node 1 | DB | Yes - Outside this BoM | fdcgcgracad15p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 210 | 30 | 150 |  |  |  | 390 | 168.584 | 0 | 0 | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | Oracle RAC - Kana, WPS-Leg2-Node 2 | DB | Yes - Outside this BoM | fdcgcgracad16p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 168.584 | 0 | 0 | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | Oracle RAC - iProcess -Node 1 | DB | Yes - Outside this BoM | fdcgcgracad17p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 700 | 30 | 300 |  | 400 |  | 1430 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - iProcess -Node 2 | DB | Yes - Outside this BoM | fdcgcgracad18p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - Ci/SAO , Integration Layer-Node 1 | DB | Yes - Outside this BoM | fdcgcgracad19p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 900 | 30 | 400 |  |  |  | 1330 | 168.584 | 0 | 0 | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | Oracle RAC - Ci/SAO , Integration Layer-Node2 | DB | Yes - Outside this BoM | fdcgcgracad20p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 168.584 | 0 | 0 | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | Oracle RAC - EDW -Node 1 | DB | Yes - Outside this BoM | fdcgcgracad21p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 120 | [5 empty] | 120 | 539.4688 | 0 | 0 | #N/A | #N/A | #N/A | 539.4688 | 0 | 0
PROD | Oracle RAC - EDW -Node 1 | DB | Yes - Outside this BoM | fdcgcgracad22p | IBM p7 p795 | AIX 6.1 | LEG1 | [7 empty] | 0 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - TCON, URS, CO,CW- Node 1 | DB | Yes - Outside this BoM | fdcgcgracad23p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 960 | 30 | 600 |  |  |  | 1590 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - TCON, URS, CO,CW- Node 2 | DB | Yes - Outside this BoM | fdcgcgracad24p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - COPS-Node 1 | DB | Yes - Outside this BoM | fdcgcgracad25p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 5440 | 30 | 1500 |  |  |  | 6970 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - COPS-Node 2 | DB | Yes - Outside this BoM | fdcgcgracad26p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 269.7344 | 0 | 0 | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | Oracle RAC - CLMS, CitiPlanner-Node 1 | DB | Yes - Outside this BoM | fdcgcgracad27p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 1200 | 30 | 700 |  |  |  | 1930 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - CLMS, CitiPlanner-Node 2 | DB | Yes - Outside this BoM | fdcgcgracad28p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - ECR-Node 1 | DB | Yes - Outside this BoM | fdcgcgracad29p | IBM p7 p795 | AIX 6.1 | LEG1 |  | 940 | 30 | 750 |  |  |  | 1720 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PROD | Oracle RAC - ECR-Node 2 | DB | Yes - Outside this BoM | fdcgcgracad30p | IBM p7 p795 | AIX 6.1 | LEG1 |  |  | 30 |  |  |  |  | 30 | 134.8672 | 0 | 0 | #N/A | #N/A | #N/A | 134.8672 | 0 | 0
PAT | CMR/CDE/CLMS/IVR/WM Fix / Swift Engine App / SNF | AP | Yes - Outside this BoM | FDCGCGCMRLA03P | BL460c | RHEL 5.6 | NR | [8 empty] | 606.9023 | 0 | #N/A | #N/A | #N/A | #N/A | 606.9023 | 0 | 0
PAT | CMR/CDE/CLMS/IVR/WM Fix / Swift Engine App / SNF | AP | Yes - Outside this BoM | FDCGCGCMRLA04P | BL460c | RHEL 5.6 | NR | [8 empty] | 1146.3711 | 0 | #N/A | #N/A | #N/A | #N/A | 1146.3711 | 1146.3711 | 0
PAT/PROD | OCI | AP | Yes - Outside this BoM | FDCGCGOCILA01P | BL460c | RHEL 5.6 | LEG1 |  |  |  | 0 |  |  | 560 | 560 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT/PROD | OCI | AP | Yes - Outside this BoM | FDCGCGOCILA02P | BL460c | RHEL 5.6 | LEG2 |  |  |  | 0 |  |  | 560 | 560 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA05P | BL460c | RHEL 5.6 | NR | [8 empty] | 202.3008 | 0 | #N/A | #N/A | 134.8672 | #N/A | 202.3008 | 0 | 0
PAT | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA06P | BL460c | RHEL 5.6 | NR | [8 empty] | 202.3008 | 0 | #N/A | #N/A | 134.8672 | #N/A | 202.3008 | 202.3008 | 0
PAT | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLW18P | BL460c | RHEL 5.6 | NR | [8 empty] | 202.3008 | 0 | #N/A | #N/A | 33.7168 | #N/A | 202.3008 | 0 | 0
PAT | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLW19P | BL460c | RHEL 5.6 | NR | [8 empty] | 202.3008 | 0 | #N/A | #N/A | 33.7168 | #N/A | 202.3008 | 202.3008 | 0
PAT | F2F | WW | Yes - Outside this BoM | FDCGCGF2FLA01P | BL460c | RHEL 5.6 | LEG1 |  |  |  | 0 |  |  | 300 | 300 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | F2F | WW | Yes - Outside this BoM | FDCGCGF2FLA02P | BL460c | RHEL 5.6 | LEG2 |  |  |  | 0 |  |  | 300 | 300 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | ESB-BW-PL | AP | Yes - Outside this BoM | FDCGCGTIBLA21P | BL620C G7 | RHEL 5.6 | LEG1 | NA | [7 empty] | 0 | 0 | #N/A | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A
PAT | ESB-BW-PL | AP | Yes - Outside this BoM | FDCGCGTIBLA22P | BL620C G7 | RHEL 5.6 | LEG1 | NA | [7 empty] | 269.7344 | 0 | 269.7344 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A
PAT | ESB-BW-PL | AP | Yes - Outside this BoM | FDCGCGTIBLA29P | BL620C G7 | RHEL 5.6 | LEG2 | NA | [7 empty] | 202.3008 | 0 | #N/A | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A
PAT | ESB-BW-PL | AP | Yes - Outside this BoM | FDCGCGTIBLA30P | BL620C G7 | RHEL 5.6 | LEG2 | NA | [7 empty] | 0 | 0 | 269.7344 | #N/A | 202.3008 | #N/A | #N/A | 0 | #N/A
PAT/PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW16P | BL460c | RHEL 5.6 | NR | NA | [7 empty] | 67.4336 | 0 | #N/A | #N/A | 67.4336 | #N/A | #N/A | 0 | #N/A
PAT/PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW17P | BL460c | RHEL 5.6 | NR | [8 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0
PROD | CI-CP-BW | AP | No | FDCGCGTIBLA37P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  | 30 | 290 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | CI-CP-BW | AP | No | FDCGCGTIBLA38P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  | 30 | 290 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | SNF-BW | AP | No | FDCGCGTIBLA35P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | SNF-BW | AP | No | FDCGCGTIBLA36P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | ESB-PAT | AP | No | FDCGCGTIBLA39P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | ESB-PAT | AP | No | FDCGCGTIBLA40P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | ESB-PAT | AP | No | FDCGCGTIBLA41P | BL620C G7 | RHEL 5.6 | LEG2 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PAT | ESB-PAT | AP | No | FDCGCGTIBLA42P | BL620C G7 | RHEL 5.6 | LEG2 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB-BW-RU | AP | No | FDCGCGTIBLA31P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB-BW-RU | AP | No | FDCGCGTIBLA32P | BL620C G7 | RHEL 5.6 | LEG1 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB-BW-RU | AP | No | FDCGCGTIBLA33P | BL620C G7 | RHEL 5.6 | LEG2 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB-BW-RU | AP | No | FDCGCGTIBLA34P | BL620C G7 | RHEL 5.6 | LEG2 | New Servers. Need to Request Storage Acc. |  | 260 |  |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | CDE | AP | Yes - Outside this BoM | FDCGCGCDELA01P | BL460c | RHEL 5.6 | LEG1 |  |  | 80 |  | 60 |  |  | 140 | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | CLMS | AP | Yes - Outside this BoM | FDCGCGCLMLA02P | BL460c | RHEL 5.6 | LEG2 | 2013-12-01 |  | 100 |  | 30 |  |  | 130 | 404.6016 | 0 | #N/A | #N/A | #N/A | #N/A | 404.6016 | 404.6016 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PROD | CLMS | AP | Yes - Outside this BoM | FDCGCGCLMLA01P | BL460c | RHEL 5.6 | LEG1 |  |  | 200 |  | 90 |  |  | 290 | 404.6016 | 0 | #N/A | #N/A | #N/A | #N/A | 404.6016 | 0 | 0
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA02P | BL460c | RHEL 5.6 | LEG2 | 2013-12-08 | [7 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 269.7344 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PROD | CMR | AP | Yes - Outside this BoM | FDCGCGCMRLA01P | BL460c | RHEL 5.6 | LEG1 |  |  | 30 |  | 30 |  |  | 60 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA04P | BL460c | RHEL 5.6 | LEG2 | 2013-12-08 | [7 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 269.7344 | 0 | Host | Completed | 17695788 | 2013-12-08 | Completed | Aperture raised | 2014-01-12 | SAN to provide
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA01P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PAT/PROD | Integration Layer - Websphere - Node 2 | WW | Yes - Outside this BoM | fdcgcgrilaw02p | IBM p7 p795 | AIX 6.1 | LEG2 | 2014-01-12 | [7 empty] | 101.1504 | 0 | 0 | #N/A | #N/A | #N/A | 101.1504 | 101.1504 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA03P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | CMR | AP | Yes - Outside this BoM | FDCGCGCMRLA02P | BL460c | RHEL 5.6 | LEG2 | 2014-01-12 |  | 30 |  | 30 |  |  | 60 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA07P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 0 | 0
PROD | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA08P | BL460c | RHEL 5.6 | LEG2 | 2014-01-12 | [7 empty] | 269.7344 | 0 | #N/A | #N/A | #N/A | #N/A | 269.7344 | 269.7344 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA09P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 0 | 0
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA10P | BL460c | RHEL 5.6 | LEG2 | 2014-01-12 | [7 empty] | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA11P | BL460c | RHEL 5.6 | LEG1 |  |  | 230 | 0 |  |  |  | 230 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA12P | BL460c | RHEL 5.6 | LEG2 |  |  | 230 | 0 |  |  |  | 230 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA13P | BL460c | RHEL 5.6 | LEG1 |  |  | 230 | 0 |  |  |  | 230 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | Eclipse Portal | WW | Yes - Outside this BoM | FDCGCGECLLA14P | BL460c | RHEL 5.6 | LEG2 |  |  | 230 | 0 |  |  |  | 230 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA15P | BL460c | RHEL 5.6 | LEG1 |  |  | 260 | 0 |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | FDS - EclipseLite/CI/MEMFIS/ACACS | AP | Yes - Outside this BoM | FDCGCGECLLA16P | BL460c | RHEL 5.6 | LEG2 | 2014-01-12 |  | 260 | 0 |  |  |  | 260 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGECLLA64P | BL620C G7 | RHEL 5.6 | LEG1 |  | 120 | 30 | 90 |  |  |  | 240 | 370.8848 | 0 | #N/A | #N/A | #N/A | #N/A | 370.8848 | 0 | 0
PROD | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGECLLA74P | BL620C G7 | RHEL 5.6 | LEG1 |  |  | 30 |  |  |  |  | 30 | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 0 | 0
PROD | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGTCOLA64P | BL620C G7 | RHEL 5.6 | LEG1 |  | 120 | 30 | 90 |  |  |  | 240 | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 0 | 0
PROD | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGTCOLA74P | BL620C G7 | RHEL 5.6 | LEG1 |  |  | 30 |  |  |  |  | 30 | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 0 | 0
PAT | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGTCOLA65P | BL620C G7 | RHEL 5.6 | NR | [8 empty] | 303.4512 | 0 | #N/A | #N/A | 303.4512 | #N/A | #N/A | 0 | #N/A
PAT | Citioptions/TCON/URS/Citiwatch | AP | Yes - Outside this BoM | FDCGCGTCOLA75P | BL620C G7 | RHEL 5.6 | NR | [8 empty] | 168.584 | 0 | #N/A | #N/A | 168.584 | #N/A | #N/A | 0 | #N/A
PROD | Eclipse Portal -Pre rainbow | WW | Yes - Outside this BoM | FDCGCGECLLW05P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | Eclipse Portal -Pre rainbow | WW | Yes - Outside this BoM | FDCGCGECLLW06P | BL460c | RHEL 5.6 | LEG2 | 2014-01-12 | [7 empty] | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0 | Host | Completed | 17802165 | 2014-01-12 | Completed | Aperture raised | SAN to provide | SAN to provide
PROD | FDS-Pre rainbow | AP | Yes - Outside this BoM | FDCGCGECLLW07P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 0 | 0
PROD | FDS-Pre rainbow | AP | Yes - Outside this BoM | FDCGCGECLLW08P | BL460c | RHEL 5.6 | LEG2 | 2014-01-19 | [7 empty] | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW12P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW13P | BL460c | RHEL 5.6 | LEG2 | 2014-01-19 | [7 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW14P | BL460c | RHEL 5.6 | LEG1 | [8 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | Eclipse & FDS HTTP | WW | Yes - Outside this BoM | FDCGCGECLLW15P | BL460c | RHEL 5.6 | LEG2 | 2014-01-19 | [7 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | Wily | AP | Yes - Outside this BoM | FDCGCGECLLW22P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | IVR | AP | Yes - Outside this BoM | FDCGCGIVRLA02P | BL460c | RHEL 5.6 | LEG1 |  |  | 90 |  | 60 |  |  | 150 | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 0 | 0
PROD | IVR | AP | Yes - Outside this BoM | FDCGCGIVRLA03P | BL460c | RHEL 5.6 | LEG2 | 2014-01-19 |  | 90 |  | 60 |  |  | 150 | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | MQ | AP | Yes - Outside this BoM | FDCGCGMQMLA19P | BL620C G7 | RHEL 5.6 | LEG1 | Need to discuss with MQ team |  | 60 |  |  |  | 60 | 120 | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 0 | 0
PROD | MQ | AP | Yes - Outside this BoM | FDCGCGMQMLA20P | BL620C G7 | RHEL 5.6 | LEG2 | Need to discuss with MQ team |  | 60 |  |  |  | 60 | 120 | 236.0176 | 0 | #N/A | #N/A | #N/A | #N/A | 236.0176 | 236.0176 | 0
PROD | MQ | AP | Yes - Outside this BoM | FDCGCGMQMLA65P | BL620C G7 | RHEL 5.6 | LEG1 | NA |  | 60 |  |  |  | 30 | 90 | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | MQ | AP | Yes - Outside this BoM | FDCGCGMQMLA75P | BL620C G7 | RHEL 5.6 | LEG2 | NA |  | 60 |  |  |  | 30 | 90 | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | WM Fix / Swift Engine App / SNF | AP | Yes - Outside this BoM | FDCGCGSWFLA01P | BL460c | RHEL 5.6 | LEG1 |  |  | 130 | 0 |  |  |  | 130 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | WM Fix / Swift Engine App / SNF | AP | Yes - Outside this BoM | FDCGCGSWFLA02P | BL460c | RHEL 5.6 | LEG2 | 2014-01-19 |  | 130 | 0 |  |  |  | 130 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 202.3008 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | ESB [V5]-CMR - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA01P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 1011.5039 | 0 | #N/A | #N/A | #N/A | #N/A | 1011.5039 | 0 | 0
PROD | ESB [V5]-CMR - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA02P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0
PROD | ESB [V5]-CMR - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA03P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-19 | [7 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 0 | 0 | Host | Raised, not completed | 17802181 | 2014-01-19 | Cancelled, pending reschedule | pending migration | SAN to provide | SAN to provide
PROD | ESB [V5]-CMR - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA04P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-26 | [7 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0 | Host | pending | pending | 2014-01-26 | planning | pending migration | SAN to provide | SAN to provide
PROD | ESB [V5, V6], Pre-Rainbow/WLM - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA05P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 0 | 0
PROD | ESB [V5, V6], Pre-Rainbow/WLM - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA06P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0
PROD | ESB [V5, V6], Pre-Rainbow/WLM - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA07P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-26 | [7 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 0 | 0 | Host | pending | pending | 2014-01-26 | planning | pending migration | SAN to provide | SAN to provide
PROD | ESB [V5, V6], Pre-Rainbow/WLM - APPS | AP | Yes - Outside this BoM | FDCGCGTIBLA08P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-26 | [7 empty] | 337.168 | 0 | #N/A | #N/A | #N/A | #N/A | 337.168 | 337.168 | 0 | Host | pending | pending | 2014-01-26 | planning | pending migration | SAN to provide | SAN to provide
PROD | ESB -WAVE2 | AP | Yes - Outside this BoM | FDCGCGTIBLA25P | BL620C G7 | RHEL 5.6 | LEG1 |  |  | 260 | 0 |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB -WAVE2 | AP | Yes - Outside this BoM | FDCGCGTIBLA26P | BL620C G7 | RHEL 5.6 | LEG1 |  |  | 260 | 0 |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB -WAVE2 | AP | Yes - Outside this BoM | FDCGCGTIBLA27P | BL620C G7 | RHEL 5.6 | LEG2 |  |  | 260 | 0 |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | ESB -WAVE2 | AP | Yes - Outside this BoM | FDCGCGTIBLA28P | BL620C G7 | RHEL 5.6 | LEG2 |  |  | 260 | 0 |  |  |  | 260 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA09P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 1213.8047 | 0 | #N/A | #N/A | #N/A | #N/A | 1213.8047 | 0 | 0
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA10P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 404.6016 | 0 | #N/A | #N/A | #N/A | #N/A | 404.6016 | 404.6016 | 0
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA11P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 505.752 | 0 | #N/A | #N/A | #N/A | #N/A | 505.752 | 0 | 0
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA12P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 303.4512 | 0
PROD | CI-CP | AP | Yes - Outside this BoM | FDCGCGTIBLA13P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 0 | 0
PROD | CI-CP | AP | Yes - Outside this BoM | FDCGCGTIBLA14P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 303.4512 | 0
PROD | CI-CP-COP | AP | Yes - Outside this BoM | FDCGCGTIBLA15P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 0 | 0
PROD | CI-CP-COP | AP | Yes - Outside this BoM | FDCGCGTIBLA16P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 303.4512 | 0 | #N/A | #N/A | #N/A | #N/A | 303.4512 | 303.4512 | 0
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA17P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 1786.9902 | 0 | #N/A | #N/A | #N/A | #N/A | 1786.9902 | 0 | 0
PROD | COP | AP | Yes - Outside this BoM | FDCGCGTIBLA18P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 370.8848 | 0 | #N/A | #N/A | #N/A | #N/A | 370.8848 | 370.8848 | 0
PROD | ESB [V5,V6], CMR, COP, SNF - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA61P | BL620C G7 | RHEL 5.6 | LEG1 |  | -180 |  | 30 |  |  |  | -150 | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | ESB [V5,V6], CMR, COP, SNF - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA71P | BL620C G7 | RHEL 5.6 | LEG1 | [8 empty] | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | ESB [V5,V6], CMR, COP, SNF - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA81P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-26 | -180 |  | 30 |  |  |  | -150 | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 168.584 | 0 | Host | pending | pending | 2014-01-26 | planning | pending migration | SAN to provide | SAN to provide
PROD | ESB [V5,V6], CMR, COP, SNF - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA91P | BL620C G7 | RHEL 5.6 | LEG2 | 2014-01-26 | [7 empty] | 505.752 | 0 | #N/A | #N/A | #N/A | #N/A | 505.752 | 505.752 | 0 | Host | pending | pending | 2014-01-26 | planning | pending migration | SAN to provide | SAN to provide
PROD | COPS--EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA19P | BL620C G7 | RHEL 5.6 | Leg1 |  | 450 | 60 | 0 |  |  |  | 510 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | COPS--EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA20P | BL620C G7 | RHEL 5.6 | Leg1 |  |  | 60 | 0 |  |  |  | 60 | #N/A | 0 | #N/A | #N/A | #N/A | #N/A | #N/A | 0 | #N/A
PROD | CI-CP - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA62P | BL620C G7 | RHEL 5.6 | LEG1 |  | 60 |  | 0 |  | 60 |  | 120 | 202.3008 | 0 | #N/A | #N/A | #N/A | #N/A | 202.3008 | 0 | 0
PROD | CI-CP - EMS | AP | Yes - Outside this BoM | FDCGCGTIBLA72P | BL620C G7 | RHEL 5.6 | LEG1 |  |  |  | 0 |  |  |  |  | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | CI-iProcess | AP | Yes - Outside this BoM | FDCGCGTIBLA63P | BL620C G7 | RHEL 5.6 | LEG1 |  | 120 |  | 0 |  | 60 |  | 180 | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
PROD | CI-iProcess | AP | Yes - Outside this BoM | FDCGCGTIBLA73P | BL620C G7 | RHEL 5.6 | LEG1 |  |  |  | 0 |  |  |  |  | 168.584 | 0 | #N/A | #N/A | #N/A | #N/A | 168.584 | 0 | 0
[14 empty] | Total Cap.= | 51350
[11 empty] | Buffer |  | Buffer |  | 10000
13958.7539
[8 empty] | To release from Leg1 | [7 empty] | 13.6316
Note on J18: rp11857 Pre Rainbow storage need to release
Note on J165: rp11857: Need to release COPS EMS storage

## 27TB Excel
Hostname | Size | Remarks | CSI ID | App name | Acronym | App Mgr | App Mgr SOEID | App Architect | Business Criticality
fdcgcgboxaa01p | 207156 | Either on leg1/leg2/-. Means can be moved to leg-2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgboxaa01p_2p | 379786 | Either on leg1/leg2/-. Means can be moved to leg-2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgboxaa02p | 207156 | Either on leg1/leg2/-. Means can be moved to leg-2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgcdela01p | 276208 | Leg1
fdcgcgcdela02p | 276208 | Leg2 | 164693, 164509 | Collateral and Limit Management System - CEEMEA | CLMS | Krishnan, Venkata | KV49666 | Ramesh Babu, Munuswamy Rajendran (MR88872) | MEDIUM
fdcgcgclmla01p | 414312 | Leg1
fdcgcgclmla02p | 414312 | Leg2 | 164693, 164509 | EL, CLMS
fdcgcgcmraa01p | 138104 | Leg1
fdcgcgcmraa01p_2p | 1108066 | Leg1
fdcgcgcmraa02p | 138104 | Leg1
fdcgcgcmrla01p | 207156 | Leg1
fdcgcgcmrla02p | 207156 | Leg2 | 163477, 164509 | CMR, CLMS
fdcgcgcmrla03p | 621468 | Leg1
fdcgcgcmrla04p | 1173884 | Leg2 | 163477 | Customer Management Repository - EMEA | CMR | Kadalmangalam Ramanujachari, Ramaswamy | KR42319 | Counce, David | LOW
fdcgcgdtgad18p | 3234 | Leg2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgdtgad20p | 3234 | Leg2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgdtgad28p | 3234 | Leg2 | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgdtgad30p | 3234 | Leg2 | 163124 | Centralized Offer Palette - EMEA | COP | Ramakrishna, Acharya Rohitashwa | AR98725 | Stepien, Renata | MEDIUM
fdcgcgeclla01p | 276208 | Leg1
fdcgcgeclla02p | 276208 | Leg2 | 165601 | Advanced Fraud Early Warning Services - Ceemea | AFEWS | Premchander, Mukund | MP64983 | Stepien, Renata | HIGH
fdcgcgeclla03p | 276208 | Leg1
fdcgcgeclla04p | 276208 | Leg2 | 165601, 164693 | AFEWS, EL
fdcgcgeclla05p | 207156 | Leg1
fdcgcgeclla06p | 207156 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgeclla07p | 276208 | Leg1
fdcgcgeclla08p | 276208 | Leg2 | 164693 158762 165282 165303 165304 | EL Advanced Computer Assisted Collection - UAE MEMFIS - Investments MF - UAE MEMFIS-Insurance Product Processor - Hungary, Poland, UAE | EL ACACS - Intranet MEMFIS - Inv MEMFIS - IPP | Guirey, Alvin Raynatus Raval Tan, Victor Chee Wee Thangamani, Muthurajan | AG59468 VT59418 MT26567 | Stepien, Renata Stepien, Renata Stepien, Renata | HIGH HIGH
fdcgcgeclla09p | 241682 | leg1
fdcgcgeclla10p | 241682 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgeclla16p | 207156 | Leg2 | Not in Aperture
fdcgcgeclla64_74p | 313968 | Leg1
fdcgcgeclla64p | 379786 | Leg1
fdcgcgeclla74p | 310734 | Leg1
fdcgcgecllw01p | 241682 | Need to check rainbow server or not
fdcgcgecllw03p | 276208 | Need to check rainbow server or not
fdcgcgecllw05p | 207156 | Leg1
fdcgcgecllw06p | 241682 | Leg2 | 161468,162618 | Eclipse - Russia ASPAC SCPIER | Eclipse - Russia ASPAC SCPIER | Kallam, Vamsi Mohan Gudimella, Udaya Kumar | KV00223 UG72318 | Stepien, Renata | HIGH LOW
fdcgcgecllw07p | 241682 | Leg1
fdcgcgecllw08p | 241682 | Leg2 | 161468,162618 | Eclipse - Russia ASPAC SCPIER | Eclipse - Russia ASPAC SCPIER | Kallam, Vamsi Mohan Gudimella, Udaya Kumar | KV00223 UG72318 | Stepien, Renata | HIGH LOW
fdcgcgecllw12p | 207156 | Leg1
fdcgcgecllw13p | 207156 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgecllw14p | 207156 | Leg1
fdcgcgecllw15p | 207156 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgecllw17p | 207156 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgecllw18p | 207156 | Leg1
fdcgcgecllw19p | 207156 | Leg2 | 164693 | Eclipse - Hugary, Poland, IPB | EL | Ling, Weibing | WL25461 | Stepien, Renata | HIGH
fdcgcgecllw22p | 207156 | Leg1
fdcgcgetlaa01p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa01p_02p | 622546 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa02p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa03p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa03p_04p | 829702 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa04p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa05p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa05p_6p | 1313066 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa06p | 34526 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa07p | 34526 | Leg1/Leg2-DWH do not require COB (sunset) | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa07p_8p | 173708 | Leg1/Leg2-DWH do not require COB (sunset) | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa08p | 34526 | Leg1/Leg2-DWH do not require COB (sunset) | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa09p | 138104 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa09p_10p | 864228 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa10p | 138104 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa15p | 241682 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgetlaa16p | 241682 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgivrla02p | 345260 | Leg1
fdcgcgivrla03p | 345260 | Leg2 | 164693,164509 | EL, CMLS | EL, CMLS
fdcgcgkanaa01p | 448838 | Leg1
fdcgcgkanaw03p | 241682 | Leg1
fdcgcgkanaw04p | 345260 | Leg2 | 163202 | Kana Connect - EMEA Rainbow : HU,UK,UAE,RU,PL | KC | Raghunandanan, Prem Sekhar | PS38925 | An, Tao Rao, Shankar | LOW
fdcgcgmqmla19p | 241682 | Leg1
fdcgcgmqmla20p | 241682 | Leg2 | 161467,162864 | Enterprise Service Bus - Russia CitiPlanner - EMEA | ESB Citiplanner | Jacob, Sam Joseph Machadi, Ravinder Rao | JS08928 RR49713 | Meyer, Joseph Ramesh Babu, Munuswamy Rajendran | HIGH LOW
fdcgcgmqmla65_75p | 172630 | Leg1
fdcgcgmqmla65p | 172630 | Leg1
fdcgcgmqmla75p | 172630 | Leg1
fdcgcgporaw01p | 276208 | Leg1/Leg2-DWH do not require COB | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgracad01p | 138104 | Leg1
fdcgcgracad01p_2p | 424014 | Leg1
fdcgcgracad02p | 138104 | Leg1
fdcgcgracad03p | 138104 | Leg2 | 164652 | Phoenix IVR 2.0 - EMEA | IVR | Subramaniam, Ramachandran | SR37807 | Stepien, Renata | HIGH
fdcgcgracad03p_4p | 141338 | Leg2 | 164652 | Phoenix IVR 2.0 - EMEA | IVR | Subramaniam, Ramachandran | SR37807 | Stepien, Renata | HIGH
fdcgcgracad04p | 138104 | Leg2 | 164652 | Phoenix IVR 2.0 - EMEA | IVR | Subramaniam, Ramachandran | SR37807 | Stepien, Renata | HIGH
fdcgcgracad05p | 276208 | Leg1
fdcgcgracad05p_06p | 2351002 | Leg1
fdcgcgracad05p_06p_PG_05F0_12F0 | 2351002 | Leg1
fdcgcgracad06p | 276208 | Leg1
fdcgcgracad07p | 172630 | Leg2 | 163454,163106 | DWH Customer Management Repository - Asia Pacific | CMR | Kadalmangalam Ramanujachari, Ramaswamy | KR42319 | Counce, David | HIGH
fdcgcgracad07p_8p | 2005742 | Leg2 | 163454,163107 | DWH Customer Management Repository - Asia Pacific | CMR | Kadalmangalam Ramanujachari, Ramaswamy | KR42320 | Counce, David | HIGH
fdcgcgracad08p | 172630 | Leg2 | 163454,163108 | DWH Customer Management Repository - Asia Pacific | CMR | Kadalmangalam Ramanujachari, Ramaswamy | KR42321 | Counce, David | HIGH
fdcgcgracad13p | 276208 | Leg1
fdcgcgracad13p_14p | 1695008 | Leg1
fdcgcgracad14p | 138104 | Leg1
fdcgcgracad15p | 172630 | Leg1
fdcgcgracad15p_16p | 624702 | Leg1
fdcgcgracad16p | 172630 | Leg1
fdcgcgracad17p | 138104 | Leg1
fdcgcgracad17p_18p | 1108066 | Leg1
fdcgcgracad18p | 138104 | Leg1
fdcgcgracad19p | 172630 | Leg1
fdcgcgracad19p_20p | 2040268 | Leg1
fdcgcgracad20p | 172630 | Leg1
fdcgcgracad21p | 552416 | Leg1
fdcgcgracad21p_22p | 797332 | Leg1
fdcgcgracad22p | 276208 | Leg1
fdcgcgracad23p | 276208 | Leg1
fdcgcgracad23p_24p | 2489106 | Leg1
fdcgcgracad24p | 276208 | Leg1
fdcgcgracad25p | 276208 | Leg1
fdcgcgracad25p_26p | 7888108 | Leg1
fdcgcgracad26p | 276208 | Leg1
fdcgcgracad27p | 138104 | Leg1
fdcgcgracad27p_28p | 2005742 | Leg1
fdcgcgracad28p | 138104 | Leg1
fdcgcgracad29p | 138104 | Leg1
fdcgcgracad29p_30p | 2592684 | Leg1
fdcgcgracad30p | 138104 | Leg1
fdcgcgrilaa01p | 103578 | Leg1
fdcgcgrilaa01p_2p | 1140436 | Leg1
fdcgcgrilaa02p | 103578 | Leg1
fdcgcgrilaw01p | 103578 | Leg1
fdcgcgrilaw02p | 103578 | Leg2 | 164901 | EMEA Integration Layer | EMEAIL | Rao, Raghuram Prabhakar | RR41956 | Counce, David | HIGH
fdcgcgsasaa02p | 345260 | Non Replicated Storage–moved to any frame | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgsasaa03p | 7112356 | Non Replicated Storage- moved to any frame | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgsasaw01p | 448838 | Leg1/Leg2-DWH do not require COB- to any frame | 163454 | Data Warehouse - EMEA | DWH | Balamurugan, Pitchai | BP41588 | Stepien, Renata | LOW
fdcgcgswfla01p | 207156 | Leg1
fdcgcgswfla02p | 207156 | Leg2 | 164693,164509 | EL CMLS
fdcgcgtcola64p | 241682 | Leg1
fdcgcgtcola64p_74p | 244916 | Leg1
fdcgcgtcola74p | 241682 | Leg1
fdcgcgtibla01p | 1035780 | Leg1 – need to be confirmed by TIBCO team
fdcgcgtibla02p | 345260 | Leg2 | 161467,161502,162733,163477 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA | ESB Turkey ESB EMEA | Jacob, Sam Joseph Jacob, Sam Joseph | JS08928 JS08928 | Meyer, Joseph Meyer, Joseph | HIGH LOW
fdcgcgtibla03p | 345260 | Leg1
fdcgcgtibla04p | 345260 | Leg2 | 161467,161502,162733,163477 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA | ESB Turkey ESB EMEA | Jacob, Sam Joseph Jacob, Sam Joseph | JS08928 JS08928 | Meyer, Joseph Meyer, Joseph | HIGH LOW
fdcgcgtibla05p | 345260 | Leg1
fdcgcgtibla06p | 345260 | Leg2 | 161467,161502,162733,163477 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA | ESB Turkey ESB EMEA | Jacob, Sam Joseph Jacob, Sam Joseph | JS08928 JS08928 | Meyer, Joseph Meyer, Joseph | HIGH LOW
fdcgcgtibla07p | 345260 | Leg1
fdcgcgtibla08p | 345260 | Leg2 | 161467,161502,162733,163477, 163530 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA SNF Gateway - EMEA | ESB Turkey ESB EMEA SNFG-EMEA | Jacob, Sam Joseph Jacob, Sam Joseph Palanikumar, Nagarathinavelu | JS08928 JS08928 PN25718 | Meyer, Joseph Meyer, Joseph Uthaman, Sureshbabu | HIGH LOW HIGH
fdcgcgtibla09p | 1242936 | Leg1
fdcgcgtibla10p | 414312 | Leg2 | 163124 | Centralized Offer Palette - EMEA | COP | Ramakrishna, Acharya Rohitashwa | AR98725 | Stepien, Renata | MEDIUM
fdcgcgtibla11p | 517890 | Leg1
fdcgcgtibla12p | 310734 | Leg2 | 163124 | Centralized Offer Palette - EMEA | COP | Ramakrishna, Acharya Rohitashwa | AR98725 | Stepien, Renata | MEDIUM
fdcgcgtibla13p | 310734 | Leg1
fdcgcgtibla14p | 310734 | Leg2 | 162864,163124 | Citiplanner EMEA Centralized Offer Palette | Citiplanner EMEA COP
fdcgcgtibla15p | 310734 | Leg1
fdcgcgtibla16p | 310734 | Leg2 | 162864,163124 | Citiplanner EMEA Centralized Offer Palette | Citiplanner EMEA COP
fdcgcgtibla17p | 1829878 | Leg1
fdcgcgtibla18p | 379786 | Leg2 | 163124 | Centralized Offer Palette - EMEA | COP | Ramakrishna, Acharya Rohitashwa | AR98725 | Stepien, Renata | MEDIUM
fdcgcgtibla61_71p | 624702 | Leg1
fdcgcgtibla61p | 172630 | Leg1
fdcgcgtibla62_72p | 521124 | Leg1
fdcgcgtibla62p | 207156 | Leg1
fdcgcgtibla63_73p | 345260 | Leg1
fdcgcgtibla63p | 172630 | Leg1
fdcgcgtibla71p | 172630 | Leg1
fdcgcgtibla72p | 172630 | Leg1
fdcgcgtibla73p | 172630 | Leg1
fdcgcgtibla81_91p | 624702 | Leg2 | 161467,161502,162733,163477, 163530, 163124 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA SNF Gateway - EMEA COP | ESB Russia ESB Turkey ESB EMEA SNFG-EMEA COP | Jacob, Sam Joseph Jacob, Sam Joseph Palanikumar, Nagarathinavelu Ramakrishna, Acharya Rohitashwa | JS08928 JS08928 PN25718 AR98725 | Meyer, Joseph Meyer, Joseph Uthaman, Sureshbabu Stepien, Renata | HIGH LOW HIGH MEDIUM
fdcgcgtibla81p | 172630 | Leg2 | 161467,161502,162733,163477, 163530, 163124 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA SNF Gateway - EMEA COP | ESB Russia ESB Turkey ESB EMEA SNFG-EMEA COP | Jacob, Sam Joseph Jacob, Sam Joseph Palanikumar, Nagarathinavelu Ramakrishna, Acharya Rohitashwa | JS08928 JS08928 PN25718 AR98726 | Meyer, Joseph Meyer, Joseph Uthaman, Sureshbabu Stepien, Renata | HIGH LOW HIGH MEDIUM
fdcgcgtibla91p | 517890 | Leg2 | 161467,161502,162733,163477, 163530, 163124 | ESB Russia Enterprise Service Bus Turkey Enterprise Service Bus - EMEA CMR EMEA SNF Gateway - EMEA COP | ESB Russia ESB Turkey ESB EMEA SNFG-EMEA COP | Jacob, Sam Joseph Jacob, Sam Joseph Palanikumar, Nagarathinavelu Ramakrishna, Acharya Rohitashwa | JS08928 JS08928 PN25718 AR98727 | Meyer, Joseph Meyer, Joseph Uthaman, Sureshbabu Stepien, Renata | HIGH LOW HIGH MEDIUM
fdcgcgticad01p | 138104 | Leg1
fdcgcgticad01p_2p | 1174962 | Leg1
fdcgcgticad02p | 138104 | Leg1
01p 02 p

## Others
Hostname | Size | Storage Info. Tally
fdcgcgboxaa01p | 207156 | 6
fdcgcgboxaa01p_2p | 379786 | #N/A
fdcgcgboxaa02p | 207156 | 7
fdcgcgcdela02p | 276208 | 34
fdcgcgclmla02p | 414312 | 101
fdcgcgcmrla02p | 207156 | 109
fdcgcgcmrla04p | 1173884 | 73
fdcgcgdtgad18p | 3234 | 39
fdcgcgdtgad20p | 3234 | 40
fdcgcgdtgad28p | 3234 | 44
fdcgcgdtgad30p | 3234 | 45
fdcgcgeclla02p | 276208 | 103
fdcgcgeclla04p | 276208 | 105
fdcgcgeclla06p | 207156 | 77
fdcgcgeclla08p | 276208 | 111
fdcgcgeclla10p | 241682 | 113
fdcgcgeclla16p | 207156 | 119
fdcgcgecllw06p | 241682 | 127
fdcgcgecllw08p | 241682 | 129
fdcgcgecllw13p | 207156 | 131
fdcgcgecllw15p | 207156 | 133
fdcgcgecllw17p | 207156 | 87
fdcgcgecllw19p | 207156 | 79
fdcgcgetlaa01p | 34526 | 10
fdcgcgetlaa01p_02p | 622546 | #N/A
fdcgcgetlaa02p | 34526 | 11
fdcgcgetlaa03p | 34526 | 12
fdcgcgetlaa03p_04p | 829702 | #N/A
fdcgcgetlaa04p | 34526 | 13
fdcgcgetlaa05p | 34526 | 14
fdcgcgetlaa05p_6p | 1313066 | #N/A
fdcgcgetlaa06p | 34526 | 15
fdcgcgetlaa07p | 34526 | 16
fdcgcgetlaa07p_8p | 173708 | #N/A
fdcgcgetlaa08p | 34526 | 17
fdcgcgetlaa09p | 138104 | 18
fdcgcgetlaa09p_10p | 864228 | #N/A
fdcgcgetlaa10p | 138104 | 19
fdcgcgetlaa15p | 241682 | 20
fdcgcgetlaa16p | 241682 | 21
fdcgcgivrla03p | 345260 | 136
fdcgcgkanaw04p | 345260 | 26
fdcgcgmqmla20p | 241682 | 138
fdcgcgporaw01p | 276208 | 27
fdcgcgracad03p | 138104 | 48
fdcgcgracad03p_4p | 141338 | #N/A
fdcgcgracad04p | 138104 | 49
fdcgcgracad07p | 172630 | 52
fdcgcgracad07p_8p | 2005742 | #N/A
fdcgcgracad08p | 172630 | 53
fdcgcgrilaw02p | 103578 | 107
fdcgcgsasaa02p | 345260 | 29
fdcgcgsasaa03p | 7112356 | 30
fdcgcgsasaw01p | 448838 | 28
fdcgcgswfla02p | 207156 | 142
fdcgcgtibla02p | 345260 | 144
fdcgcgtibla04p | 345260 | 146
fdcgcgtibla06p | 345260 | 148
fdcgcgtibla08p | 345260 | 150
fdcgcgtibla10p | 414312 | 156
fdcgcgtibla12p | 310734 | 158
fdcgcgtibla14p | 310734 | 160
fdcgcgtibla16p | 310734 | 162
fdcgcgtibla18p | 379786 | 164
fdcgcgtibla81_91p | 624702 | #N/A
fdcgcgtibla81p | 172630 | 167
fdcgcgtibla91p | 517890 | 168
27130938