## NAM Current Sched
NAM Migration activities
Hostname | Tech Team SN# | Project | Replicated | Site | Primary SA | Migration Contact | TYPE | Business Area | Destination Array | Storage in Scope | Migration TC | Migration Date | Migration Time | Duration | Type | Status | Comment
gtsviotx11 | BAU | NAM2013-9 | Non-Rep | Roanoke | Kumar, Arvind [CCC-OT_IT NE] |  | Contingency | CTI | USOUE081R1703 | 151.7265 | Edwards | 2014-08-12 |  |  | Host Based-Provision | Completed
gtsviotx12 | BAU | NAM2013-9 | Non-Rep | Roanoke | Kumar, Arvind [CCC-OT_IT NE] |  | Contingency | CTI | USOUE081R1703 | 151.7265 | Edwards | 2014-08-12 |  |  | Host Based-Provision | Completed
gtsviotx15 | BAU | NAM2013-9 | Non-Rep | Roanoke | Kumar, Arvind [CCC-OT_IT NE] |  | Contingency | CTI | USOUE081R1703 | 151.7265 | Edwards | 2014-08-12 |  |  | Host Based-Provision | Completed
gtsviotx16 | BAU | NAM2013-9 | Non-Rep | Roanoke | Kumar, Arvind [CCC-OT_IT NE] |  | Contingency | CTI | USOUE081R1703 | 151.7265 | Edwards | 2014-08-12 |  |  | Host Based-Provision | Completed
mdmwdacsdbp1-1 | BAU | NAM2013-9 | Rep | MWDC | Martinez, Daniel Albert [CCC-OT_IT] | *CIBIS NAM Markets Unix Server | Production | ICG | USOME081R1656 | 303.453 | Edwards | 2014-08-12 |  |  | Host Based-Provision | Completed
webgtdcsson01s-cd | CHG0000327977 | NAM2014-1 | Non-Rep | GTDC | Kumar, Rishi [CCC-OT_IT NE] | *GT US Web SA Services | UAT | CTI | USOGE015N2004 | 337.17 | Edwards | 2014-08-14 | 21:00 | 4 hours | Array | Incomplete
webgtdcsson02s-cd | CHG0000327977 | NAM2014-1 | Non-Rep | GTDC | Kumar, Rishi [CCC-OT_IT NE] | *GT US Web SA Services | UAT | CTI | USOGE015N2004 | 337.17 | Edwards | 2014-08-14 | 21:00 | 4 hours | Array | Incomplete
webgtdcsson03s-cd | CHG0000327977 | NAM2014-1 | Non-Rep | GTDC | Kumar, Rishi [CCC-OT_IT NE] | *GT US Web SA Services | UAT | CTI | USOGE015N2004 | 337.17 | Edwards | 2014-08-14 | 21:00 | 4 hours | Array | Incomplete
hcpww-trn4400 | BAU | Bronze | Non-Rep | MWDC | Junghare, Chaitanya [CCC-OT_ITNE] |  | Lab/Test | GCG |  | 236.019 | Ramaraju | 2014-08-15 |  |  | Future Decom | Incomplete
efdap-uat3800 | CHG0000332204 | NAM2013-2 | Non-Rep | GTDC | Kannappan, Saravanan [CCC-OT_IT NE] | *CBNA US CBNA US EFD Production Support | UAT | GCG | USOGE013N1411 | 134.868 | Edwards | 2014-08-15 | 18:00 | 4 hours | Array | Incomplete
efdap-uat3810 | CHG0000332204 | NAM2013-2 | Non-Rep | GTDC | Kannappan, Saravanan [CCC-OT_IT NE] | *CBNA US CBNA US EFD Production Support | UAT | GCG | USOGE013N1411 | 134.868 | Edwards | 2014-08-15 | 18:00 | 4 hours | Array | Incomplete
webgtdcsson04s-cd | CHG0000331987 | NAM2014-1 | Non-Rep | GTDC | Kumar, Rishi [CCC-OT_IT NE] | *GT US Web SA Services | UAT | CTI | USOGE015N2004 | 741.774 | Chlasani | 2014-08-15 | 21:00 | 4 hours | Array | Incomplete
cftswbld2 | BAU | Bronze | Non-Rep | Roanoke | Wazir, Dalbir [CCC-OT_IT] | *CTINAMCTSISPaymentSA | Development | ICG |  | 606.906 | Ramaraju | 2014-08-15 |  |  | Future Decom | Incomplete
eqcpmpatsqdr1 | CHG0000332155 | NAM2013-2 | Non-Rep | 390 | Ananthapadmanaban, Balaji [CCC-OT_IT NE] |  | Contingency | ICG | USOEH055N4427 | 763.158 | Ramaraju | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
mwcoeiqdb3d | CHG0000334236 | Bronze | Non-Rep | MWDC | Gobinathan, Praveen [CCC-OT_IT NE] | *GT NAM GFTS UNIX SA | Development | CTO | USOME034N1349 | 760.212 | Chlasani | 2014-08-16 | 1:00 | 4 hours | Array | Incomplete
mwcoeiqdb4d | CHG0000334236 | Bronze | Non-Rep | MWDC | Gobinathan, Praveen [CCC-OT_IT NE] | *GT NAM GFTS UNIX SA | Development | CTO | USOME034N1349 | 760.212 | Chlasani | 2014-08-16 | 1:00 | 4 hours | Array | Incomplete
gctmwapp3 | CHG0000334775 | NAM2014-1 | Non-Rep | MWDC | Iyer, Santosh [CCC-OT_IT NE] |  | Production | CTI | USOMH018N4095 | 5293.569 | Ramaraju | 2014-08-16 | 15:00 | 4 hours | Host Based-Provision | Incomplete
gctmwapp3 | CHG0000334775 | FAST-VP-1 | Non-Rep | MWDC | Iyer, Santosh [CCC-OT_IT NE] | Iyer, Santosh[CCC-OT_ITNE] | Production | CTI | USOMH018N4095 | 67.434 | Ramaraju | 2014-08-16 | 15:00 | 4 hours | Host Based-Provision | Incomplete
gctmwapp3 | CHG0000334775 | NAM2013-9 | Non-Rep | MWDC | Iyer, Santosh [CCC-OT_IT NE] |  | Production | CTI | USOME081R1656 | 308.313 | Ramaraju | 2014-08-16 | 15:00 | 4 hours | Host Based-Provision | Incomplete
gctswapud2 | CHG0000334775 | NAM2013-9 | Non-Rep | Roanoke | Iyer, Santosh [CCC-OT_IT NE] |  | Production | CTI | USOUE081R1703 | 67.434 | Ramaraju | 2014-08-16 | 15:00 | 4 hours | Host Based-Provision | Incomplete
webgtdcsson05s-cd | CHG0000332042 | NAM2014-1 | Non-Rep | GTDC | Kumar, Rishi [CCC-OT_IT NE] | *GT US Web SA Services | UAT | CTI | USOGE015N2004 | 741.774 | Chlasani | 2014-08-16 | 21:00 | 4 hours | Array | Incomplete
icg-rth-frm1p | CHG0000334281 | NAM2013-9 | Non-Rep | Rutherford | Liu, Yansheng [CCC-OT_IT] |  | Production | CTI | ORE048R3114 | 168.585 | Chlasani | 2014-08-16 | 8:00 |  | Host Based-Reclaim | Incomplete
icg-rth-frm1p | CHG0000334281 | NAM2014-4 | Non-Rep | Rutherford | Liu, Yansheng [CCC-OT_IT] |  | Production | CTI | USORE008N0262 | 2191.644 | Chlasani | 2014-08-16 | 8:00 |  | Host Based-Reclaim | Incomplete
icg-sw-frm1 | CHG0000334281 | Bronze | Non-Rep | Roanoke | Liu, Yansheng [CCC-OT_IT] |  | Development | CTI | OUE048R3116 | 876.642 | Chlasani | 2014-08-16 | 8:00 |  | Host Based-Reclaim | Incomplete
icg-sw-frm1 | CHG0000334281 | NAM2013-9 | Non-Rep | Roanoke | Liu, Yansheng [CCC-OT_IT] |  | Development | CTI | OUE048R3116 | 337.17 | Chlasani | 2014-08-16 | 8:00 |  | Host Based-Reclaim | Incomplete
mwamdb2p | CHG0000275316 | NAM2013-9 | Non-Rep | MWDC | Manoharan, Suresh [CCC-OT_IT NE] |  | Production | CTO | USOMH018N4095 | 6868.422 | Ramaraju | 2014-08-16 | 6:00 | 8 hours | Array | Incomplete
gsrswdb1u | CHG0000334245 | FAST-VP-4 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 2299.4994 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
gsrswdb1u | CHG0000334245 | NAM2013-9 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 967.607 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
gsrswdb2u | CHG0000334245 | FAST-VP-4 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 2299.4994 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
gctswapud2 | CHG0000334775 | NAM2013-2 | Non-Rep | Roanoke | Iyer, Santosh [CCC-OT_IT NE] |  | Production | CTI | USOUH060N3341 | 5445.201 | Ramaraju | 2014-08-16 | 15:00 | 4 hours | Host Based-Provision | Incomplete
gsrswdb2u | CHG0000334245 | NAM2013-9 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 967.607 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
gsrswdb3u | CHG0000334245 | FAST-VP-4 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 2299.4994 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
gsrswdb3u | CHG0000334245 | NAM2013-9 | Non-Rep | Roanoke | Rc, Balaji [CCC-OT_IT NE] |  | UAT | ICG | USOUH067N1530 | 967.607 | Muttadi | 2014-08-16 | 10:00 | 28 hours | Array | Incomplete
eqtems10c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems10p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 101.151 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems11c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems11p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 101.151 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems12c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems12p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 101.151 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems13c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems13p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems14c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems14p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems9c-phys | CHG0000334648 | NAM2014-4 | Rep | 390 | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Contingency | ICG | USOEE012R1666 | 102.7305 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
eqtems9p-phys | CHG0000334648 | NAM2014-4 | Rep | Rutherford | Tadapaneni, Sunitha [CCC-OT_IT NE] | *GT Capital Markets EQ Unix Server Support | Production | ICG | USORE012R1695 | 101.151 | Patel | 2014-08-16 | 10:00 | 4 hours | Array | Incomplete
cfmdbspmrt01 | CHG0000324517 | NAM2014-1 | Non-Rep | GTDC | Banala, Raja [CCC-OT_IT NE] | *GCG CIS NA EX SERVER Wintel Support | Production | GCG | USOGE016N2025 | 9171.024 | Ramaraju | 2014-08-17 | 12:00 | 8 hours | Array | Incomplete
latx51 | CHG0000332348 | NAM2014-1 | Non-Rep | GTDC | Hitchcock, James [CCC-OT_IT] | Hitchcock, James [CCC-OT_IT] | Production | GCG | USOGE016N2025 | 3607.719 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
amlmme2d | CHG0000334914 | Bronze | Non-Rep | Roanoke | K K, Satish [CCC-OT_IT NE] | *GT NAM GFTS UNIX SA | Development | CTO | US0UH0064N1278 | 438.321 | Ramaraju | 2014-08-17 | 17:00 | 5 hours | Array | Incomplete
rmxap-prd3901 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 134.868 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxap-prd3902 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 134.868 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxap-prd3903 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 134.868 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxap-prd3904 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 134.868 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxap-prd3905 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 102.7305 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxap-prd3906 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 102.7305 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxww-prd3901 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 404.604 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxww-prd3902 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 404.604 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxww-prd3903 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 404.604 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxww-prd3904 | CHG0000334986 | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 269.736 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete
rmxww-prd3905 | CHG0000334986 - registration | NAM2014-1 | Non-Rep | GTDC | Sivakumar, Sridevi [CCC-OT_IT NE] |  | Production | GCG | USOGE015N2004 | 269.736 | Chlasani | 2014-08-17 | 0:01 | 6 hours | Array | Incomplete

## EMEA Current Sched
Hostname | Tech Team RFC# | Project | Replicated | Site | Primary SA | Migration Contact | TYPE | Business Area | Schedule Status | RFC Status | SA RFC # | Source Array | Destination Array | Storage in Scope | Migration TC | Migration Date | Migration Time | Duration | Migration Type | Status | Comment
fioradb25c | CHG0000317819 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292600623 | 295700703 | 269.7344 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
fioradb16d | CHG0000336642 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski | Development | TBC | Completed | Approved | 0 | 292600623 | 295700703 | 1550.9727 | Venkat/Ravi | 2014-08-16 | 14:00 | 4 hours | Host Based-Reclaim | Completed
fiaredb1u | CHG0000336642 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | UAT | TBC | Completed | Approved | 0 | 292600623 | 295700703 | 0 | Venkat/Ravi | 2014-08-16 | 14:00 | 0 | Host Based-Reclaim | Completed
fxemsap1c | CHG0000317819 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292600623, 292600745 | 295700703 | 236.0176 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
fxemsap2p | CHG0000317819 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 | 295700688 | 67.4336 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
fxemsap1p | CHG0000317819 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 | #NUM! | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
fisyb1c6p | CHG0000336642 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 |  | 4248.3164 | 0 | 2014-08-16 | 14:00 | 0 | Host Based-Reclaim | Completed
fisyb2c6p | CHG0000336642 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 |  | 0 | 0 | 2014-08-16 | 14:00 | 0 | Host Based-Reclaim | Completed
ficvcpap5p | CHG0000331910 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 |  | 505.752 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Array | Completed
ficvcpap6p | CHG0000331910 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 | 295700688 | 202.3008 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Array | Completed
eqitrs2p | CHG0000317819 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600552 | 295700688 | 67.4336 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
rdcgtsgtawd01p | CHG0000303372 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 741.7695 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
rdcgtsgtawa01p | CHG0000303372 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 236.0176 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
gminfra1d2d | 0 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Development | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 0 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Host Based-Reclaim | Completed
fxepfdb1p | CHG0000317819 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 404.6016 | Venkat/Ravi | 2014-08-16 | 20:00 | 4 hours | Array | Completed
eqd1ap4u | CHG0000317819 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | UAT | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 101.1504 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
eqd1ap4p | CHG0000317819 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 101.1504 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
eqd1ap5p | CHG0000317819 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292600678 | 295700704 | 101.1504 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
gccashsyb2u-new | 0 | EMEA2014 | Non-Rep | FDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | UAT | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Host Based-Reclaim | Completed
fdcgtsmfawa02c | CHG0000309144 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 101.1504 | Venkat/Ravi | 2014-08-16 | 15:00 | 4 hours | Array | Completed
fdcgtsmfawa01c | CHG0000309144 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 101.1504 | Venkat/Ravi | 2014-08-16 | 15:00 | 4 hours | Array | Completed
fdcgtsmfaad07u | CHG0000331888 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 4248.3164 | Venkat/Ravi | 2014-08-16 | 8:00 | 0 | Host Based-Reclaim | Completed
fdcgtsmfaad08u | CHG0000331888 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 0 | Host Based-Reclaim | Completed
fdcgtsmfaad09u | CHG0000331888 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 9879.0215 | Venkat/Ravi | 2014-08-16 | 8:00 | 0 | Host Based-Reclaim | Completed
fdcgtsmfaad10u | CHG0000331888 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 0 | Host Based-Reclaim | Completed
gccashora1u | CHG0000336642 | EMEA2014 | Non-Rep | FDC | *GT EMEA Markets UNIX SA | Marek Zukowski | UAT | TBC | Completed | Approved | 0 | 292600879 | #NUM! | 0 | Venkat/Ravi | 2014-08-16 | 14:00 | 4 hours | Host Based-Reclaim | Completed
fdcgdscrewa02c | CHG0000316141 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 101.1504 | Venkat/Ravi | 2014-08-16 | 15:00 | 0 | Array | Completed
fdcgdscrewa01c | CHG0000316141 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 101.1504 | Venkat/Ravi | 2014-08-16 | 15:00 | 0 | Array | Completed
fdcgtstanwd01c | CHG0000316182 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | #NUM! | 0 | Venkat/Ravi | 2014-08-16 | 15:00 | 0 | Array | Completed
fdcgtstanwd02c | CHG0000316182 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-16 | 15:00 | 0 | Array | Completed
fdcgtsfmswd01c | CHG0000316206 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Completed | Approved | 0 | 292600879 | 295700709 | 269.7344 | Venkat/Ravi | 2014-08-16 | 15:00 | 0 | Array | Completed
gccssyb1p | CHG0000323934 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292602230 | 295700688 | 404.6016 | Venkat/Ravi | 2014-08-16 | 12:00 | 4 hours | Array | Completed
gccssyb2p | CHG0000323934 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292602230 | 295700688 | 0 | Venkat/Ravi | 2014-08-16 | 12:00 | 4 hours | Array | Completed
rdcgdsdbcvd01p | CHG0000323934 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292602230 | 295700688 | 2157.875 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
rdcgdsdbcvd02p | CHG0000323934 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Production | TBC | Completed | Approved | 0 | 292602230 | 295700688 | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
gccssyb1c | CHG0000323934 | EMEA2014 | Rep | FDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292602231 | 295700710/ 295700712 | 404.6016 | Venkat/Ravi | 2014-08-16 | 12:00 | 4 hours | Array | Completed
fdcgdsdbcvd01c | CHG0000323934 | EMEA2014 | Rep | FDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292602231 | #NUM! | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
fdcgdsdbcvd02c | CHG0000323934 | EMEA2014 | Rep | FDC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292602231 | #NUM! | 0 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed
ficvcpap5c | CHG0000331910 | EMEA2014 | Rep | CGC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292600745 | 295700705 | 505.752 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Array | Completed
ficvcpap6c | CHG0000331910 | EMEA2014 | Rep | CGC | *GT EMEA Markets UNIX SA | Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292600745 | 295700705 | 202.3008 | Venkat/Ravi | 2014-08-16 | 0:00 | 0 | Array | Completed
eqitrs2c | CHG0000317819 | EMEA2014 | Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Completed | Approved | 0 | 292600745 | 295700705 | 67.4336 | Venkat/Ravi | 2014-08-16 | 8:00 | 4 hours | Array | Completed

## EMEA Future Sched
Hostname | Tech Team RFC# | Project | Replicated | Site | Primary SA | Migration Contact | TYPE | Business Area | Schedule Status | RFC Status | SA RFC # | Source Array | Destination Array | Storage in Scope | Migration TC | Migration Date | Migration Time | Duration | Migration Type | Status | Comment
fdcgtsabnaa01c | CHG0000194031 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 1753.99 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtsabnaa02c | CHG0000194031 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 33.72 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtsabnaa03c | CHG0000194031 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 270.45 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtsabnaa04c | CHG0000194031 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 33.72 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtscswad01c | CHG0000273164 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 18779 | fdchds_0365 | 769.03 | Venkat/Ravi | 2014-09-13 | 8:00 | 0 | Future Decom | Incomplete
fdcgtscswad01u | CHG0000179527 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | UAT | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103943 | 295700709 | 1150.67 | Venkat/Ravi | 2014-09-13 | 12:00 | 4 hours | Future Decom | Incomplete
fdcgtscswad02c | CHG0000273164 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Contingency | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 18779 | fdchds_0365 | 69.38 | Venkat/Ravi | 2014-09-13 | 8:00 | 0 | Future Decom | Incomplete
fdcgtscswad02u | CHG0000179527 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | UAT | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103564, 290103943 | 295700709 | 33.72 | Venkat/Ravi | 2014-09-13 | 12:00 | 4 hours | Future Decom | Incomplete
fdcgtsfccad09c | CHG0000287776 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Contingency | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 2799.2 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtsfccad10c | CHG0000287776 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Contingency | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 0.035156 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtsfcmad09c | CHG0000287776 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Contingency | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 2934.13 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtsfcmad10c | CHG0000287776 | EMEA2013-1 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Contingency | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103564, 290103544 | 295700709 | 0 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtstfiad01c_new | CHG0000195162 | EMEA2013-1 | Rep | FDC | TBC | PIOTR MICHALSKI/Michal Zochowski | Contingency | 0 | Scheduled | Pending | 0 | 78398 | 295700709 | 277.521 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Host Based-Reclaim | Incomplete
rdcctioraad01p | CHG0000195236 | EMEA2013-1 | Non-Rep | RDC | Global UNIX Infrastructure EMEA | Rawski, Piotr/CTI EMEA DCIS IAAS Operations | Production | 0 | Scheduled | Pending | 0 | 290103452 | 295700704 | 44.9557 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Host Based-Reclaim | Incomplete
RDCGCGAD002N01C | CHG0000204474 | EMEA2013-1 | Non-Rep | RDC | 0 | Sreenivasulu Pokala/Dirk Busch | Contingency | 0 | Scheduled | Approved | 0 | 18850, 290103452, 78378 | 295700688 | 0 | Venkat/Ravi | 2014-08-26 | 14:00 | 0 | Host Based-Provision | Incomplete
RDCGCGEBSAA01D | CHG0000204474 | EMEA2013-1 | Non-Rep | RDC | 0 | Sreenivasulu Pokala/Dirk Busch | Development | 0 | Scheduled | Approved | 0 | 290103452, 78378 | 295700688 | 0 | Venkat/Ravi | 2014-08-26 | 14:00 | 0 | Host Based-Reclaim | Incomplete
RDCGCGEBSAA01U | CHG0000204474 | EMEA2013-1 | Non-Rep | RDC | 0 | Sreenivasulu Pokala/Dirk Busch | UAT | 0 | Scheduled | Approved | 0 | 290103452, 78378 | 295700688 | 0 | Venkat/Ravi | 2014-08-26 | 14:00 | 0 | Host Based-Reclaim | Incomplete
RDCGCGEBSAA02U | CHG0000204474 | EMEA2013-1 | Non-Rep | RDC | 0 | Sreenivasulu Pokala/Dirk Busch | UAT | 0 | Scheduled | Approved | 0 | 290103452, 78378 | 295700688 | 0 | Venkat/Ravi | 2014-08-26 | 14:00 | 0 | Host Based-Reclaim | Incomplete
rdcgtsabnaa01p | CHG0000194031 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700688 | 1753.99 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
rdcgtsabnaa02p | CHG0000194031 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700704 | 33.72 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
rdcgtsabnaa03p | CHG0000194031 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700688 | 270.44 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
rdcgtsabnaa04p | CHG0000194031 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700704 | 33.72 | Venkat/Ravi | 2014-08-30 | 14:00 | 4 hours | Host Based-Reclaim | Incomplete
rdcgtscswad01p | CHG0000194032 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700704 | 712.4 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Array | Incomplete
rdcgtscswad02p | CHG0000194032 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Hubert Olczyk (Konrad Drabik [kd55572]) | Production | Global Transaction Systems (GTS) | Scheduled | Pending | 0 | 290103452 | 295700704 | 33.72 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Array | Incomplete
rdcgtsfccad09p | CHG0000287776 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Production | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103452 | 295700688 | 2799.24 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
rdcgtsfccad10p | CHG0000287776 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Production | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103452 | 295700704 | 0.04 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
rdcgtsfcmad09p | CHG0000287776 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Production | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103452 | 295700688 | 2934.1 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
rdcgtsfcmad10p | CHG0000287776 | EMEA2013-1 | Non-Rep | RDC | *CTI EMEA CTSIS Unix BAU | Michal Pytka | Production | ICG EU Securitized Markets | Scheduled | Pending | 0 | 290103452 | 295700704 | 0.02 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
rdcgtstfiad01p_new | CHG0000195162 | EMEA2013-1 | Non-Rep | RDC | TBC | PIOTR MICHALSKI/Michal Zochowski | Production | 0 | Scheduled | Pending | 0 | 18850, 78378 |  | 0 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Host Based-Reclaim | Incomplete
tifarmcd5ffc | CHG0000134677 | EMEA2013-1 | Non-Rep | FDC | *CTI EU Global Unix Platform Solaris Linux/*CTI GLOBAL EX CIS HIA L3 FRAME 4 | Browarski, Maciej | Contingency | CTI / Shared Customer Use | Scheduled | 0 | 17579121 | 290103943, 78398, 290103564 | 295700709 | 2042.5076 | Venkat/Ravi | 2014-08-23 | 0:00 | 0 | Host Based-Reclaim | Incomplete
tifarmcd5lnp | CHG0000134677 | EMEA2013-1 | Non-Rep | RDC | *CTI EU Global Unix Platform Solaris Linux/*CTI GLOBAL EX CIS HIA L3 FRAME 4 | Browarski, Maciej | Production | CTI / Shared Customer Use | Scheduled | 0 | 17579355 | 18850, 290103943, 78398, 78378, 290103452 | rdchds_5362 | 2355.64 | Venkat/Ravi | 2014-08-23 | 0:00 | 0 | Host Based-Reclaim | Incomplete
tifarmcd6lnp | CHG0000134677 | EMEA2013-1 | Non-Rep | RDC | *CTI EU Global Unix Platform Solaris Linux/*CTI GLOBAL EX CIS HIA L3 FRAME 4 | Browarski, Maciej | Production | CTI / Shared Customer Use | Scheduled | 0 | 17579141 | 18850, 290103943, 290103564, 78378, 290103452 | rdchds_5362 | 67.43 | Venkat/Ravi | 2014-08-23 | 0:00 | 0 | Host Based-Reclaim | Incomplete
ldneqtsaex500 | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 101.1504 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Future Decom | Incomplete
ldneqtsdmo501c | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 303.4512 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Future Decom | Incomplete
ldneqtsdqps500p | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600623 | #NUM! | 809.2031 | Venkat/Ravi | 2014-08-23 | 22:00 | 4 hours | Array | Incomplete
ldnfi94sapr | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 303.4512 | Venkat/Ravi | 2014-08-23 | 7:30 | 4 hours | Array | Incomplete
fisybdb11c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 2191.5918 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
firiskdb1c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 1078.9375 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fioradb23c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 1820.707 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fioradb15c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 539.4688 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fisybdb15c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 1213.8047 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
ficvdb1c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 1517.2559 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fidbadb11c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 202.3008 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fimaccadb1c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 101.1504 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fiimcdb1c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 67.4336 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
firefdb1c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 236.0176 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fibpadb2c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 134.8672 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fisybdb12c | CHG0000336769 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 337.168 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fioradb17c | CHG0000317785 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 1820.707 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ficvdb2c | CHG0000336711 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 3776.2812 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fiswapdb1c | CHG0000317785 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 236.0176 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
cgcgctdplwa04c | 0 | EMEA2014 | Non-Rep | CGC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Contingency | TBC | Scheduled | TBC | TBC | 292600623, 292600745 | 295700703 | 404.6016 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
ldneqtsamaw601c | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 236.0176 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldnfi96saua | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | UAT | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 505.752 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
cgcgctdplwd02c | 0 | EMEA2014 | Non-Rep | CGC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Contingency | TBC | Scheduled | TBC | TBC | 292600623, 292600745 | 295700703 | 5833.0059 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
cgcgctdplwa03c | 0 | EMEA2014 | Non-Rep | CGC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Contingency | TBC | Scheduled | TBC | TBC | 292600623, 292600745 | 295700703 | 2899.6445 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
ldneqtsdsc551dr | CHG0000336509 | EMEA2014 | Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600623, 292600745 | 295700703 | 1011.5039 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldnfi37sadr | CHG0000336509 | EMEA2014 | Non-Rep | CGC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 606.9023 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
eqd1ap4c | CHG0000317785 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 101.1504 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
eqd1ap5c | CHG0000317785 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 101.1504 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fisimpcal1c | CHG0000317785 | EMEA2014 | Non-Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600623 | 295700703 | 1045.2207 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
firefdb1p | CHG0000336769 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 236.0176 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fiedlfs1p | CHG0000317785 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 438.3184 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fiedlfs2p | CHG0000317785 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fioradb15p | CHG0000336711 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552, 292600678 | 295700688 | 539.4688 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
ldnfi39sapr | CHG0000336509 | EMEA2014 | Rep | RDC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 303.4512 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fiswapdb1p | CHG0000317785 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 236.0176 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldnfi37sdpr | CHG0000336509 | EMEA2014 | Rep | RDC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 977.7871 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fidspdb2p | CHG0000317785 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292603073, 295700347, 53518 | #NUM! | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fimaccadb1p | CHG0000336769 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 101.1504 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
rdcgctdplwa04p | 0 | EMEA2014 | Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Production | TBC | Scheduled | TBC | TBC | 292600552 | 295700688 | 202.3008 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
fioradb23p | CHG0000336711 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 1820.707 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fisybdb11p | CHG0000336711 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552, 292600678 | 295700688 | 2191.5918 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fisybdb12p | CHG0000336769 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552, 292600678 | 295700688 | 337.168 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fibpadb2p | CHG0000336769 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 134.8672 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
ldneqtsdsc550 | CHG0000336509 | EMEA2014 | Rep | RDC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 505.752 | Venkat/Ravi | 2014-08-23 | 12:00 | 4 hours | Array | Incomplete
ldneqtsdds651 | CHG0000336509 | EMEA2014 | Rep | RDC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 910.3535 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldneqtsacs668 | CHG0000336509 | EMEA2014 | Rep | RDC | *CIBIS Global Markets Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 674.3359 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fisybdb15p | CHG0000336711 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552, 292600678 | 295700688 | 1213.8047 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fioradb17p | CHG0000317785 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 910.3535 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
rdcgctdplwd02p | 0 | EMEA2014 | Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Production | TBC | Scheduled | TBC | TBC | 292600552, 292600678 | 295700688 | 5833.0059 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
rdcgctdplwa03p | 0 | EMEA2014 | Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Production | TBC | Scheduled | TBC | TBC | 292600552, 292600678 | 295700688 | 2899.6445 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
firiskdb1p | CHG0000336711 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 1078.9375 | Venkat/Ravi | 2014-09-20 | 8:00 | 4 hours | Array | Incomplete
fiimcdb1p | CHG0000336769 | EMEA2014 | Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600552 | 295700688 | 67.4336 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
rdcgtsdocwa01p | CHG0000337072 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292600678 | 295700704 | 101.1504 | Venkat/Ravi | 2014-09-06 | 8:00 | 4 hours | Array | Incomplete
rdccibwste1n01p | CHG0000316085 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292600678 | 295700704 | 3742.5645 | Venkat/Ravi | 2014-08-23 | 16:00 | 4 hours | Array | Incomplete
rdccibwste1n02p | CHG0000316085 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292600678 | 295700704 | 0 | Venkat/Ravi | 2014-08-23 | 16:00 | 4 hours | Array | Incomplete
rdccibwste1n03p | CHG0000316085 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292600678 | 295700704 | 0 | Venkat/Ravi | 2014-08-23 | 16:00 | 4 hours | Array | Incomplete
rdcgctdplwd02u | 0 | EMEA2014 | Non-Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | UAT | TBC | Scheduled | TBC | TBC | 292600678 |  | 0 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
rdcgctdplwa03u | 0 | EMEA2014 | Non-Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | UAT | TBC | Scheduled | TBC | TBC | 292600678 | 295700704 | 2967.0781 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
gcfrcap1lnp | CHG0000323934 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600678, 292602230 | 295700704 | 303.4512 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
gcfrcap2lnp | CHG0000323934 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600678, 292602230 | 295700704 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fidbadb11p | CHG0000336769 | EMEA2014 | Non-Rep | RDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Production | TBC | Scheduled | Pending | TBC | 292600678 | 295700704 | 202.3008 | Venkat/Ravi | 2014-10-04 | 8:00 | 4 hours | Array | Incomplete
fdcgtsfccad09u | CHG0000287776 | EMEA2014 | Non-Rep | FDC | *EM PL BH System Admins Unix-DBA | Michal Pytka | UAT | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 12036.8965 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtsfccad10u | CHG0000287776 | EMEA2014 | Non-Rep | FDC | *EM PL BH System Admins Unix-DBA | Michal Pytka | UAT | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-30 | 14:00 | 0 | Future Decom | Incomplete
fdcgtsmfaad01u | 0 | EMEA2014 | Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | 0 | TBC | 295700349 | #NUM! | 0 | Venkat/Ravi | 2014-08-30 | 0:00 | 0 | Host Based-Reclaim | Incomplete
fdcgtsmfaad02u | 0 | EMEA2014 | Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | 0 | TBC | 295700349 | #NUM! | 0 | Venkat/Ravi | 2014-08-30 | 0:00 | 0 | Host Based-Reclaim | Incomplete
fdcgtsmfaad03u | 0 | EMEA2014 | Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | 0 | TBC | 295700349, 292603004 | #NUM! | 0 | Venkat/Ravi | 2014-08-30 | 0:00 | 0 | Host Based-Reclaim | Incomplete
fdcgtsmfaad04u | 0 | EMEA2014 | Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | 0 | TBC | 295700349, 292603004 | #NUM! | 0 | Venkat/Ravi | 2014-08-30 | 0:00 | 0 | Host Based-Reclaim | Incomplete
fdcgtsmfaad05u | 0 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | Pending | TBC | 292600879 | EMC Only | 5799.2891 | Venkat/Ravi | 2014-08-30 | 8:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtsmfaad06u | 0 | EMEA2014 | Non-Rep | FDC | *CTI EMEA CTSIS Unix BAU | ADRIAN TRYZNA | UAT | TBC | Scheduled | Pending | TBC | 292600879 | EMC Only | 0 | Venkat/Ravi | 2014-08-30 | 8:00 | 4 hours | Host Based-Reclaim | Incomplete
fdcgtsdocwa01c | CHG0000309163 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 101.1504 | Venkat/Ravi | 2014-09-13 | 15:00 | 4 hours | Array | Incomplete
fdccibwste1n01c | CHG0000316115 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 3742.5645 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdccibwste1n02c | CHG0000316115 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdccibwste1n03c | CHG0000316115 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292600879 | 295700709 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
gcfrcap1ffc | CHG0000323934 | EMEA2014 | Non-Rep | FDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600879, 292602231 | 295700709 | 438.3184 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
gcfrcap2ffc | CHG0000323934 | EMEA2014 | Non-Rep | FDC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600879, 292602231 | 295700709 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdcctslnaad03c | CHG0000332049 | EMEA2014 | Non-Rep | FDC | EMEA CIBIS GTS UNIX Projects | Bartosz Jabłoński/Przemyslaw Maciuszko | Contingency | TBC | Scheduled | Pending | TBC | 292600879, 292602231 | 295700709 | 11463.7109 | Venkat/Ravi | 2014-09-06 | 8:00 | 6 hours | Array | Incomplete
fdcctslnaad04c | CHG0000332049 | EMEA2014 | Non-Rep | FDC | EMEA CIBIS GTS UNIX Projects | Bartosz Jabłoński/Przemyslaw Maciuszko | Contingency | TBC | Scheduled | Pending | TBC | 292600879, 292602231 | 295700709 | 67.4336 | Venkat/Ravi | 2014-09-06 | 8:00 | 6 hours | Array | Incomplete
rdcctslnaad03p | CHG0000332049 | EMEA2014 | Rep | RDC | EMEA CIBIS GTS UNIX Projects | Bartosz Jabłoński/Przemyslaw Maciuszko | Production | TBC | Scheduled | Pending | TBC | 292602230 |  | 5226.1035 | Venkat/Ravi | 2014-09-06 | 8:00 | 6 hours | Array | Incomplete
rdcctslnaad04p | CHG0000332049 | EMEA2014 | Rep | RDC | EMEA CIBIS GTS UNIX Projects | Bartosz Jabłoński/Przemyslaw Maciuszko | Production | TBC | Scheduled | Pending | TBC | 292602230 |  | 0 | Venkat/Ravi | 2014-09-06 | 8:00 | 6 hours | Array | Incomplete
rdcctseftwd01p | CHG0000317472 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292602230 | 295700704 | 472.0352 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
rdcctseftwd02p | CHG0000317472 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292602230 | 295700704 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
rdcgtsnetwd01p | CHG0000316223 | EMEA2014 | Non-Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292602230 | 295700688 | 171.5049 | Venkat/Ravi | 2014-09-06 | 15:00 | 4 hours | Array | Incomplete
rdcgctgftwa01p | 0 | EMEA2014 | Rep | RDC | *GT EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Production | TBC | Scheduled | TBC | TBC | 292602230 | 295700688 | 208.1426 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
rdcgtsdocwd01p | CHG0000317436 | EMEA2014 | Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292602230 | 295700688 | 4370.9941 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
rdcgtsorbwd01p | 0 | EMEA2014 | Rep | RDC | EMEA Wintel G3 SA | Dariusz Kulak | Production | TBC | Scheduled | Pending | TBC | 292602230 | 295700688 | 2254.8779 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Future Decom | Incomplete
fdcctseftwd01c | CHG0000317472 | EMEA2014 | Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292602231 | 295700710/ 295700712 | 944.0703 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdcctseftwd02c | CHG0000317472 | EMEA2014 | Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292602231 | 295700710/ 295700712 | 0 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdcgtsnetwd01c | CHG0000316223 | EMEA2014 | Non-Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292602231 | #NUM! | 0 | Venkat/Ravi | 2014-09-06 | 15:00 | 4 hours | Array | Incomplete
fdcgctgftwa01c | 0 | EMEA2014 | Non-Rep | FDC | EMEA GFTS WINTEL | ADAM SZAFRANSKI (AS15321 ) | Contingency | TBC | Scheduled | TBC | TBC | 292602231 | #NUM! | 0 | Venkat/Ravi | 2014-09-30 | 0:00 | 0 | Future Decom | Incomplete
fdcgtsdocwd01c | CHG0000317436 | EMEA2014 | Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292602231 | 295700710/ 295700712 | 4370.9941 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
fdcgtsorbwd01c | 0 | EMEA2014 | Rep | FDC | EMEA Wintel G3 SA | Dariusz Kulak | Contingency | TBC | Scheduled | Pending | TBC | 292602231 | 295700710/ 295700712 | 2254.8779 | Venkat/Ravi | 2014-08-23 | 6:00 | 4 hours | Future Decom | Incomplete
fiedlfs1c | CHG0000317785 | EMEA2014 | Rep | CGC | *GT EMEA Markets UNIX SA | Marek Zukowski/Marcin Rulewicz | Contingency | TBC | Scheduled | Pending | TBC | 292600745 | 295700705 | 438.3184 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldnfi39sadr | CHG0000336509 | EMEA2014 | Rep | CGC | Global Markets EMEA Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600745 | 295700705 | 303.4512 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldnfi37sddr | CHG0000336509 | EMEA2014 | Rep | CGC | Global Markets EMEA Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600745 | 295700705 | 977.7871 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
ldneqtsdds550dr | CHG0000336509 | EMEA2014 | Rep | CGC | Global Markets EMEA Wintel Server | Lukasz Slonawski/Rafal Czajkowski/*CIBIS Global Markets Wintel Serve | Contingency | TBC | Scheduled | Pending | TBC | 292600745 | 295700705 | 910.3535 | Venkat/Ravi | 2014-08-23 | 8:00 | 4 hours | Array | Incomplete
Note on N1: nd69093: to either non-replicated HDS Arrays: 1. RDC GBOKH006N5362 (BAU-TR VSP) 2. FDC DEOLH005N0365 (BAU-TR VSP) or Replicated EMC Arrays: 3. RDC Rep 000292604330 (EMC VMAX) 4. FDC Rep 000292604652 (EMC VMAX)

## Frames with a few remaining
Hostname | Source Frame | Site | Primary SA | Line Manager | Manager | Executive Manager | Migration date | Migration Type
tx87vio01 | 3715 | GTDC | Milton Johnson |  |  |  |  | Host Based-Reclaim | 1/31-SA Milton response-- This is the project where we have to move 5 LPARs off the 2 frames, then we will decomm the frames along with the vio servers. - Yesterday I received the replacement LPARs from the build team. - I will notify the DBA team and begin the work of migrating to the new hardware. 1/28 sent request for an update, no response yet. 12/5 Rob and DD had call with Milton. Host are being moved to a new frame sometime in 2014. TCRS is open. Milton will update us with status around 12/13 Goal is to reclaim by end of Jan.
tx87vio02 | 3715 | GTDC | Milton Johnson |  |  |  |  | Host Based-Reclaim
tx87vio03 | 3715 | GTDC | Milton Johnson |  |  |  |  | Host Based-Reclaim
tx87vio04 | 3715 | GTDC | Milton Johnson |  |  |  |  | Host Based-Reclaim