## SRM
Type | Location | Task | Task Assigned | Status
VMAX | Singapore | need to get a confirmation from Matthew for Singapore VMAX3 #0057 discovery Status in SRM | Matthew
VMAX | india | need to get a confirmation from Matthew for India VMAX array #0651 discovery Status in SRM | Matthew
VMAX | india | need to get a confirmation from Matthew for India VMAX array #1296 discovery Status in SRM | Matthew
VMAX | HK Iad | need to get a confirmation from Matthew for Hk iad VMAX array #0518 discovery Status in SRM | Matthew
VMAX | HK Iad | need to get a confirmation from Matthew for Hk iad VMAX array #1068 discovery Status in SRM | Matthew
SE | Austraila | Recently SE servers sydbk2 migrated from Sun to Linux. So Configured SE V8.0.3.0. But Symauth configuration is pending | Shathish
SE | Austraila | Recently SE servers wphbk1 migrated from Sun to Linux. So Configured SE V8.0.3.0. But Symauth configuration is pending | Shathish
SE | India | Recently upgraded the SE V7.5 to 8.0.3.0 on Inbrdcnkpbkp02. Symauth configuration is pending | Shathish
SE | India | Recently upgraded the SE V7.5 to 8.0.3.0 on INBRDCCGMBKP02. Symauth configuration is pending | Shathish
SE | Taiwan | Waiting for additional HBA cards on TWKHB-SEP01 | Chandran/Saravanan
SE | Taiwan | twkhb-nasc01 - No update for the new linux servers | Chandran/Saravanan
SE | Taiwan | TWSCB-SEP01 - No update for the new linux servers | Chandran/Saravanan
SE | HK/SG | Found low space in root file system. So created a new file system for /usr/emc and rebooted the servers. But now we don’t hqve permissions to /var/symapi/config. So need to talk to SA and resolve the issue | Saravanan/Shathish
U4V | HK/SG | U4V configuration completed but SRM team unable to discover in SRM. So raised EMC SR 74367520. | Matthew/Brijesh
U4V | In-countries | Raised SLTN0000008760 for VMs in Australia – 2 VM’s ,Taiwan – 3 VM’s, India – 3 VM’s & China – 1 VM. | Sunil/Shathish
U4V | HK/SG | Raised CMP WS35547742 for to increase additional 60GB space to C drive | Vivek/Pankaj
CX | HK/Japan | OE versions are low. So need to get the plan for upgrade to latest versions for CKM00102100004, FCNCX093700035, JPN0012CSJ & JPN0011CSJ | Shathish/Sunil
XIV | SG/Hk | XIVs are not showing in SRM. So need to plan for the upgrade to latest versions. | Sunil/Srikanth
VMWare | In-countries | Some of the VMWare devices are not showing in SRM. So need to work with Vivek to verify and complete the pre-requisites | Vivek/Shathish
MDS | SG/Hk | Switch port count is mismatched. So EMC/CaTE recommended to upgrade to latest versions. | Sunil
MDS | SG/Hk | New Tech-refresh switches need to discover in SRM. Pre-requisites completeed | Matthew

## HPNA
Type | Task | Status | Email attachments
Cisco | 36 switches are not showing in HPNA because of IP address is not updated in Aperture. Srikanth is getting errors while updating in Aperture
VNX SP | VNX Block arrays thosc002n0775 ,inochee111n0759, auosc001n0520 are not showing in HPNA. So need to update the pre-requisites. Once it ready then need to request HPNA team for discovery
VNX CS | pre-requisites completed only for 2 arrays and requested for testing but it failed because of its not accpting the domain ( APAC\\)
VNX CS | Need to work with Basker for VMX CS pre-requisites
Symmetrix | India, Australia Solution enablers are not connecting in HPNA. So need to work with HPNA team
Symmetrix | 16 symmetrix are not discovered in HPNA. So need to resolve the issues