STORAGE ACTIVITIES FOR CEEMEA WLM CUTOVER
Distributed Systems

Below are the applications & timelines for CEEMEA WLM cutover:- 
	CEEMEA Application
	GB
	SG-->FDC ESTABLISH
	SG/FDC SPLIT

	
	
	Planned Date/Time
	Executed Date/Time
	Planned Date/Time
	Executed Date/Time

	REG CERT
	33
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	OCI
	330
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	Navigator-Russia (DB)
	132
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	Poland Nav
	33
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	Citiplanner
	1584
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	MEMFIS 
	132
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	KANA
	66
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	CITI OPTIONS
	99
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	URS
	132
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	COPS - DB1
	264
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	COPS - DB2
	132
	15/10 15:00
	15/10 18:30
	21/10 08:30
	TBC

	Dataware house
	13728
	15/10 15:00
	15/10 17:20
	21/10 08:30
	TBC

	SAS
	6138
	15/10 15:00
	15/10 17:20
	21/10 08:30
	TBC

	JFP
	4026
	18/10 20:00
	18/10 17:50
	21/10 07:30
	TBC

	AML QS 
	2673
	21/10 08:00
	TBC
	21/10 10:00
	TBC

	FILENET/ADS
	1122
	15/10 15:00
	15/10 18:30
	21/10 09:30
	TBC

	Mantas PL
	924
	18/10 08:00
	18/10 16:00
	21/10 09:30
	TBC

	
	
	
	
	
	

	STARTUS
	 
	18/10 15:00
	18/10 15:00
	21/10 09:30
	TBC


Device details for the above applications as below
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Detailed timelines found on the below SharePoint go live folder:-

https://commercial.collaborationtools.consumer.citigroup.net/sites/BASM_CAI_CCC/NA_PMO/CTI/CEEMEA%20DC%20Migration/Shared%20Documents/Forms/AllItems.aspx?RootFolder=%2fsites%2fBASM%5fCAI%5fCCC%2fNA%5fPMO%2fCTI%2fCEEMEA%20DC%20Migration%2fShared%20Documents%2fMigration%20Events%2fProduction%20%2d%204%20%2d%20Go%2dLive&FolderCTID=&View=%7b32D3F880%2dAB54%2d4923%2dAB68%2dDF04C739055F%7d
Incremental establish need to perform from SG to FDC as per the above applications
Monday ( 15th Oct 2012 ) : - 
Below files on @fdcsan-mgt2 : /export/home/san/KV13183/CUTOVER_21102012
151012_SASDWH_SG0122_FDC3004_RDFG110
151012_OTHER_SG0122_FDC2804_RDFG100
Execute the below commands

Symrdf –sid 122 –f  151012_SASDWH_SG0122_FDC3004_RDFG110 –rdfg 110 Establish

Symrdf –sid 122 –f 151012_OTHER_SG0122_FDC2804_RDFG100 –rdfg 100 establish
Thursday ( 18th Oct 2012 ) 
Below file on @fdcsan-mgt2 : /export/home/san/KV13183/CUTOVER_21102012
181012_MANTASPL_SG0122_FDC_2804_RDFG100
181012_JFP_SG0122_FDC_2804_RDFG100
Execute the below commands

Symrdf –sid 122 –f 181012_MANTASPL_SG0122_FDC_2804_RDFG100 –rdfg 100 establish

Symrdf –sid 122 –f 181012_JFP_SG0122_FDC_2804_RDFG100–rdfg 100 establish
Sunday ( 21st Oct 2012 ) 
Below files on @fdcsan-mgt2 : /export/home/san/KV13183/CUTOVER_21102012
211012_AMLQS_SG0122_FDC_2804_RDFG100
Execute the below commands

Symrdf –sid 122 –f 211012_AMLQS_SG0122_FDC_2804_RDFG100 –rdfg 100 establish
On CUTOVER day, once received the confirmation to GO then perform the SPLIT activity 

Below files on @fdcsan-mgt2 : /export/home/san/KV13183/CUTOVER_21102012
Symrdf –sid 122 –f  151012_SASDWH_SG0122_FDC3004_RDFG110 –rdfg 110 split 
Symrdf –sid 122 –f 151012_OTHER_SG0122_FDC2804_RDFG100 –rdfg 100 split
Symrdf –sid 122 –f 181012_MANTASPL_SG0122_FDC_2804_RDFG100 –rdfg 100 split
Symrdf –sid 122 –f 181012_JFP_SG0122_FDC_2804_RDFG100–rdfg 100 split
Symrdf –sid 122 –f 211012_AMLQS_SG0122_FDC_2804_RDFG100 –rdfg 100 split

Once after the Confirmations received that Migration Successful then remove SRDF pairing between SG and FDC:-
Symrdf –sid 122 deletepair –rdfg 100 ( Data devices to #2804)
Symrdf –sid 122 deletepair –rdfg 110 ( Data devices to #3004)

Symrdf –sid 122 deletepair –rdfg 200 ( Boot devices to #2804)

Symrdf –sid 122 deletepair –rdfg 210 ( Boot devices to # 3004)

STRATUS Systems
1. Validate the status of R2-BCV devices pair. (APPC)

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symmir -sid 1222 -file 1222_r2bcv query

2. Validate the status of R2BCV-R2 device pair (APPC - EMEA)

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symrdf -sid 1222 -rdfg 150 -file 1222_5349_bcvr1_r2 query

3. Establish the R2-BCV device pair.

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symmir -sid 1222 -file 1222_r2bcv establish

4. After synching R2BCV, resume the replicaiton between R2BCV - R2 (APPC - EMEA)

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symmir -sid 1222 -file 1222_r2bcv split -cons

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symrdf -sid 1222 -rdfg 150 -file 1222_5349_bcvr1_r2 establish

(ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symrdf -sid 1222 -rdfg 150 -file 1222_5349_bcvr1_r2 query 

5. On Wednesday (17th Oct 2012), repeat the steps from 1-4.

6. On Friday (19th Oct 2012), repeat the steps from 1-4.

7. On Sunday (21st Oct 2012  - 06:00 AM), repeat the steps from 1-4.

8. On actual cutover day, once the stratus services are down at APPC. 

· Login to the ssunacs8 

· cd /export/home/pp95975/temp/ceemea/cutover

· pbrun symstat -g str_dr3_devs -i 10 (To check the IOs in production stratus devices). Report any IOs to PM/Lam Cisco.

· Once you received the "Go" signal for split, proceed with next steps. Else repeat above steps to monitor the IO and report PM/Cisco. 

· Repeat steps 1-4 for the last time.(ssunsmm01)

· (ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symrdf -sid 1222 -rdfg 150 -file 1222_5349_bcvr1_r2 query -i 10

· Once the status of RDFG150 is "Synchronized" - Split the devices and inform PM/Bridge.

· (ssunsmm01)/export/home/pp95975/temp/2012/ceemea/prod/stratus $ pbrun symrdf -sid 1222 -rdfg 150 -file 1222_5349_bcvr1_r2 split
cutover data replication

		Replication File Name		OS		Application		SG Server Name		SG#0122		FDC#2804		FDC#3004		FDC Server Name		PM		DR3 PM confirmation		cutover PM confirmation		ESTABLISH Date/time SST		SPLIT Date/time SST

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		REG CERT		ssundbp01_ssundbp02_ssundbp05		04D3		06E0		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04D8		06E5		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04D9		06E6		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DA		06E7		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DB		06E8		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DC		06E9		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DD		06EA		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DE		06EB		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		04DF		06EC		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		0A44		06ED		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		OCI		ssundbp01_ssundbp02_ssundbp05		0A45		06EE		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		Navigator-Russia (DB)		ssundbp01_ssundbp02_ssundbp05		04D4		06E1		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		Navigator-Russia (DB)		ssundbp01_ssundbp02_ssundbp05		04D5		06E2		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		Navigator-Russia (DB)		ssundbp01_ssundbp02_ssundbp05		04D6		06E3		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		SUN		Navigator-Russia (DB)		ssundbp01_ssundbp02_ssundbp05		04D7		06E4		NA		fdcgcgdbcsd01p_fdcgcgdbcsd02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Poland Nav		saixdbp3201_saixdbp3202		0515		0544		NA		fdcgcgdbcad01p_fdcgcgdbcad02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0970		04BD		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0971		04BE		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0972		04BF		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0973		04C0		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0974		04C1		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0975		04C2		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0976		04C3		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0977		04C4		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0978		04C5		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0979		04C6		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097A		04C7		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097B		04C8		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097C		04C9		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097D		04CA		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097E		04CB		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		097F		04CC		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0980		04CD		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0981		04CE		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0982		04CF		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0983		04D0		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0984		04D1		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0985		04D2		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0986		04D3		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0987		04D4		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0988		04D5		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0989		04D6		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098A		04D7		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098B		04D8		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098C		04D9		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098D		04DA		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098E		04DB		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		098F		04DC		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0990		04DD		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0991		04DE		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0992		04DF		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0993		0DBC		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0994		0DBD		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp102_saixdbp103		0995		0DBE		NA		fdcgcgcpldbc01p/fdcgcgcpldbc02p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		0957		04A4		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		0958		04A5		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		0959		04A6		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095A		04A7		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095B		04A8		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095C		04A9		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095D		04AA		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095E		04AB		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		095F		04AC		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		Citiplanner		saixdbp103		0960		04AD		NA		fdcgcgcpldbc02p		Adrianna		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		MEMFIS 		saixdbp235/236		0A96		0AFA		NA		fdcgcgracad13p/14p		Gopa		confirmed to include this		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		MEMFIS 		saixdbp235/236		0A97		0AFB		NA		fdcgcgracad13p/14p		Gopa		confirmed to include this		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		MEMFIS 		saixdbp235/236		0A98		0AFC		NA		fdcgcgracad13p/14p		Gopa		confirmed to include this		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		MEMFIS 		saixdbp235/236		0A99		0AFD		NA		fdcgcgracad13p/14p		Gopa		confirmed to include this		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		KANA		saixdbp235/236		0A9A		0AFE		NA		fdcgcgracad15p/16p		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		KANA		saixdbp235/236		0A9B		0AFF		NA		fdcgcgracad15p/16p		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		CITI OPTIONS		saixdbp237/238		0AA9		0715		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		CITI OPTIONS		saixdbp237/238		0AAA		0716		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		CITI OPTIONS		saixdbp237/238		0AAB		0717		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		URS		saixdbp237/238		0AAC		0718		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		URS		saixdbp237/238		0AAD		0719		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		URS		saixdbp237/238		0AAE		071A		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		URS		saixdbp237/238		0AC6		0732		NA		fdcgcgracad23p/24p		Grzegorz		reconfirmed		reconfirmed		16/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABA		0726		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABB		0727		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABC		0728		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABD		0729		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABE		072A		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0ABF		072B		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0AC0		072C		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB1		saixdbp237/238		0AC1		072D		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB2		saixdbp237/238		0AC2		072E		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB2		saixdbp237/238		0AC3		072F		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB2		saixdbp237/238		0AC4		0730		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		COPS - DB2		saixdbp237/238		0AC5		0731		NA		fdcgcgracad25p/26p		Adrianna		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0751		NA		0625		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0752		NA		0626		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0753		NA		0627		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0754		NA		0628		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0755		NA		0629		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0756		NA		062A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0757		NA		062B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0758		NA		062C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0759		NA		062D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075A		NA		062E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075B		NA		062F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075C		NA		0630		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075D		NA		0631		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075E		NA		0632		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		075F		NA		0633		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0760		NA		0634		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0761		NA		0635		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0762		NA		0636		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0763		NA		0637		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0764		NA		0638		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0765		NA		0639		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0766		NA		063A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0767		NA		063B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0768		NA		063C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0769		NA		063D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076A		NA		063E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076B		NA		063F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076C		NA		0640		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076D		NA		0641		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076E		NA		0642		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		076F		NA		0643		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0770		NA		0644		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0773		NA		0647		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0774		NA		0648		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0775		NA		0649		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0776		NA		064A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0777		NA		064B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0778		NA		064C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0779		NA		064D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077A		NA		064E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077B		NA		064F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077C		NA		0650		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077D		NA		0651		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077E		NA		0652		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		077F		NA		0653		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0780		NA		0654		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0781		NA		0655		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0782		NA		0656		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0783		NA		0657		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0784		NA		0658		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0785		NA		0659		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0786		NA		065A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0787		NA		065B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0788		NA		065C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0789		NA		065D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078A		NA		065E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078B		NA		065F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078C		NA		0660		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078D		NA		0661		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078E		NA		0662		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		078F		NA		0663		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0790		NA		0664		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0791		NA		0665		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0792		NA		0666		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0793		NA		0667		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0794		NA		0668		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0795		NA		0669		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0796		NA		066A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0797		NA		066B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0798		NA		066C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0799		NA		066D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079A		NA		066E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079B		NA		066F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079C		NA		0670		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079D		NA		0671		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079E		NA		0672		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		079F		NA		0673		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A0		NA		0674		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A1		NA		0675		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A2		NA		0676		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A3		NA		0677		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A4		NA		0678		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A5		NA		0679		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A6		NA		067A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A7		NA		067B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A8		NA		067C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07A9		NA		067D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AA		NA		067E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AB		NA		067F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AC		NA		0680		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AD		NA		0681		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AE		NA		0682		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07AF		NA		0683		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B0		NA		0684		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B1		NA		0685		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B2		NA		0686		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B3		NA		0687		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B4		NA		0688		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B5		NA		0689		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B6		NA		068A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B7		NA		068B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B8		NA		068C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07B9		NA		068D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BA		NA		068E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BB		NA		068F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BC		NA		0690		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BD		NA		0691		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BE		NA		0692		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07BF		NA		0693		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C0		NA		0694		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C1		NA		0695		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C2		NA		0696		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C3		NA		0697		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C4		NA		0698		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C5		NA		0699		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C6		NA		069A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C7		NA		069B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C8		NA		069C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07C9		NA		069D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CA		NA		069E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CB		NA		069F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CC		NA		06A0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CD		NA		06A1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CE		NA		06A2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07CF		NA		06A3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D0		NA		06A4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D1		NA		06A5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D2		NA		06A6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D3		NA		06A7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D4		NA		06A8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D5		NA		06A9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D6		NA		06AA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D7		NA		06AB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D8		NA		06AC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07D9		NA		06AD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DA		NA		06AE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DB		NA		06AF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DC		NA		06B0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DD		NA		06B1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DE		NA		06B2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07DF		NA		06B3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E0		NA		06B4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E1		NA		06B5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E2		NA		06B6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E3		NA		06B7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E4		NA		06B8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E5		NA		06B9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E6		NA		06BA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E7		NA		06BB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E8		NA		06BC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07E9		NA		06BD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07EA		NA		06BE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07EB		NA		06BF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07EC		NA		06C0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07ED		NA		06C1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07EE		NA		06C2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07EF		NA		06C3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F0		NA		06C4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F1		NA		06C5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F2		NA		06C6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F3		NA		06C7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F4		NA		06C8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F5		NA		06C9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F6		NA		06CA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F7		NA		06CB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F8		NA		06CC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07F9		NA		06CD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FA		NA		06CE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FB		NA		06CF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FC		NA		06D0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FD		NA		06D1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FE		NA		06D2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		07FF		NA		06D3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0800		NA		06D4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0801		NA		06D5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0802		NA		06D6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0803		NA		06D7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0804		NA		06D8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0805		NA		06D9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0806		NA		06DA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0807		NA		06DB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0808		NA		06DC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0809		NA		06DD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080A		NA		06DE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080B		NA		06DF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080C		NA		06E0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080D		NA		06E1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080E		NA		06E2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		080F		NA		06E3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0810		NA		06E4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0811		NA		06E5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0812		NA		06E6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0813		NA		06E7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0814		NA		06E8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0815		NA		06E9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0816		NA		06EA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0817		NA		06EB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0818		NA		06EC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0819		NA		06ED		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081A		NA		06EE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081B		NA		06EF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081C		NA		06F0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081D		NA		06F1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081E		NA		06F2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		081F		NA		06F3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0820		NA		06F4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0821		NA		06F5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0822		NA		06F6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0823		NA		06F7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0824		NA		06F8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0825		NA		06F9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0826		NA		06FA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0827		NA		06FB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0828		NA		06FC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0829		NA		06FD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082A		NA		06FE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082B		NA		06FF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082C		NA		0700		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082D		NA		0701		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082E		NA		0702		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		082F		NA		0703		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0830		NA		0704		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0831		NA		0705		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0832		NA		0706		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0833		NA		0707		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0834		NA		0708		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0835		NA		0709		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0836		NA		070A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0837		NA		070B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0838		NA		070C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0839		NA		070D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083A		NA		070E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083B		NA		070F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083C		NA		0710		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083D		NA		0711		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083E		NA		0712		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		083F		NA		0713		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0840		NA		0714		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0841		NA		0715		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0842		NA		0716		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0843		NA		0717		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0844		NA		0718		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0845		NA		0719		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0846		NA		071A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0847		NA		071B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0848		NA		071C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0849		NA		071D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084A		NA		071E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084B		NA		071F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084C		NA		0720		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084D		NA		0721		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084E		NA		0722		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		084F		NA		0723		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0850		NA		0724		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0851		NA		0725		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0852		NA		0726		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0853		NA		0727		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0854		NA		0728		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0855		NA		0729		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0856		NA		072A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0857		NA		072B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0858		NA		072C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0859		NA		072D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085A		NA		072E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085B		NA		072F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085C		NA		0730		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085D		NA		0731		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085E		NA		0732		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		085F		NA		0733		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0860		NA		0734		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0861		NA		0735		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0862		NA		0736		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0863		NA		0737		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0864		NA		0738		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0865		NA		0739		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0866		NA		073A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0867		NA		073B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0868		NA		073C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0869		NA		073D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086A		NA		073E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086B		NA		073F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086C		NA		0740		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086D		NA		0741		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086E		NA		0742		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		086F		NA		0743		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0870		NA		0744		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0871		NA		0745		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0872		NA		0746		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0873		NA		0747		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0874		NA		0748		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0875		NA		0749		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0876		NA		074A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0877		NA		074B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0878		NA		074C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0879		NA		074D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087A		NA		074E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087B		NA		074F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087C		NA		0750		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087D		NA		0751		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087E		NA		0752		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		087F		NA		0753		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0880		NA		0754		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0881		NA		0755		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0882		NA		0756		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0883		NA		0757		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0884		NA		0758		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0885		NA		0759		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0886		NA		075A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0887		NA		075B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0888		NA		075C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0889		NA		075D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088A		NA		075E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088B		NA		075F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088C		NA		0760		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088D		NA		0761		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088E		NA		0762		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		088F		NA		0763		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0890		NA		0764		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0891		NA		0765		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0892		NA		0766		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0893		NA		0767		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0894		NA		0768		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0895		NA		0769		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0896		NA		076A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0897		NA		076B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0898		NA		076C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		0899		NA		076D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089A		NA		076E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089B		NA		076F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089C		NA		0770		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089D		NA		0771		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089E		NA		0772		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		089F		NA		0773		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A0		NA		0774		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A1		NA		0775		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A2		NA		0776		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A3		NA		0777		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A4		NA		0778		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A5		NA		0779		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A6		NA		077A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A7		NA		077B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A8		NA		077C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08A9		NA		077D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AA		NA		077E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AB		NA		077F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AC		NA		0780		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AD		NA		0781		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AE		NA		0782		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08AF		NA		0783		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B0		NA		0784		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B1		NA		0785		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B2		NA		0786		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B3		NA		0787		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B4		NA		0788		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B5		NA		0789		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B6		NA		078A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B7		NA		078B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B8		NA		078C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08B9		NA		078D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BA		NA		078E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BB		NA		078F		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BC		NA		0790		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BD		NA		0791		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BE		NA		0792		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08BF		NA		0793		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C0		NA		0794		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C1		NA		0795		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C2		NA		0796		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C3		NA		0797		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C4		NA		0798		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C5		NA		0799		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C6		NA		079A		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C7		NA		079B		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C8		NA		079C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08C9		NA		079D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CA		NA		07AE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CB		NA		07AF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CC		NA		07B0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CD		NA		07B1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CE		NA		07B2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08CF		NA		07B3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D0		NA		07B4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D1		NA		07B5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D2		NA		07B6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D3		NA		07B7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D4		NA		07B8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D5		NA		07B9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D6		NA		07BA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D7		NA		07BB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D8		NA		07BC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08D9		NA		07BD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DA		NA		07BE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DB		NA		07BF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DC		NA		07C0		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DD		NA		07C1		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DE		NA		07C2		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08DF		NA		07C3		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E0		NA		07C4		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E1		NA		07C5		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E2		NA		07C6		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E3		NA		07C7		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E4		NA		07C8		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E5		NA		07C9		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E6		NA		07CA		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E7		NA		07CB		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E8		NA		07CC		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08E9		NA		07CD		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08EA		NA		07CE		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08EB		NA		07CF		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08EC		NA		0810		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08ED		NA		0811		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08EE		NA		0812		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08EF		NA		0813		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08F0		NA		080C		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08F1		NA		080D		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		Dataware house		shpp66		08F2		NA		080E		fdcdwhp3		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08F6		NA		056B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08F7		NA		056C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08F8		NA		056D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08F9		NA		056E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FA		NA		056F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FB		NA		0570		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FC		NA		0571		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FD		NA		0572		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FE		NA		0573		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		08FF		NA		0574		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0900		NA		0575		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0901		NA		0576		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0902		NA		0577		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0903		NA		0578		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0904		NA		0579		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0905		NA		057A		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0906		NA		057B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0907		NA		057C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0908		NA		057D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0909		NA		057E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090A		NA		057F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090B		NA		0580		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090C		NA		0581		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090D		NA		0582		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090E		NA		0583		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		090F		NA		0584		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0910		NA		0585		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0911		NA		0586		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0912		NA		0587		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0913		NA		0588		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0914		NA		0589		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0915		NA		058A		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0916		NA		058B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0917		NA		058C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0918		NA		058D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0919		NA		058E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091A		NA		058F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091B		NA		0590		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091C		NA		0591		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091D		NA		0592		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091E		NA		0593		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		091F		NA		0594		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0920		NA		0595		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0921		NA		0596		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0922		NA		0597		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0923		NA		0598		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0924		NA		0599		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0925		NA		059A		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09A2		NA		059B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09A3		NA		059C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09BC		NA		059D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09BD		NA		059E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09BE		NA		059F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09BF		NA		05A0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C0		NA		05A1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C1		NA		05A2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C2		NA		05A3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C3		NA		05A4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C4		NA		05A5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C5		NA		05A6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C6		NA		05A7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C7		NA		05A8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C8		NA		05A9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09C9		NA		05AA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CA		NA		05AB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CB		NA		05AC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CC		NA		05AD		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CD		NA		05AE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CE		NA		05AF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09CF		NA		05B0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D0		NA		05B1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D1		NA		05B2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D2		NA		05B3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D3		NA		05B4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D4		NA		05B5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D5		NA		05B6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D6		NA		05B7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D7		NA		05B8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D8		NA		05B9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09D9		NA		05BA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DA		NA		05BB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DB		NA		05BC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DC		NA		05BD		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DD		NA		05BE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DE		NA		05BF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09DF		NA		05C0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E0		NA		05C1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E1		NA		05C2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E2		NA		05C3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E3		NA		05C4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E4		NA		05C5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E5		NA		05C6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E6		NA		05C7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E7		NA		05C8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E8		NA		05C9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09E9		NA		05CA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09EA		NA		05CB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09EB		NA		05CC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09EC		NA		05CD		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09ED		NA		05CE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09EE		NA		05CF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09EF		NA		05D0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F0		NA		05D1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F1		NA		05D2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F2		NA		05D3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F3		NA		05D4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F4		NA		05D5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F5		NA		05D6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F6		NA		05D7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F7		NA		05D8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F8		NA		05D9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09F9		NA		05DA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FA		NA		05DB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FB		NA		05DC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FC		NA		05DD		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FD		NA		05DE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FE		NA		05DF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		09FF		NA		05E0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A00		NA		05E1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A01		NA		05E2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A02		NA		05E3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A03		NA		05E4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A04		NA		05E5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A05		NA		05E6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A06		NA		05E7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A07		NA		05E8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A08		NA		05E9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A09		NA		05EA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0A		NA		05EB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0B		NA		05EC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0C		NA		05ED		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0D		NA		05EE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0E		NA		05EF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A0F		NA		05F0		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A10		NA		05F1		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A11		NA		05F2		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A12		NA		05F3		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A13		NA		05F4		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A14		NA		05F5		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A15		NA		05F6		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A16		NA		05F7		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A17		NA		05F8		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A18		NA		05F9		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A19		NA		05FA		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1A		NA		05FB		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1B		NA		05FC		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1C		NA		05FD		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1D		NA		05FE		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1E		NA		05FF		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A1F		NA		0600		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A20		NA		0601		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A21		NA		0602		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A22		NA		0603		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A23		NA		0604		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A24		NA		0605		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A25		NA		0606		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		NA		HP		SAS		shpp39		0A26		NA		0607		fdcsasp4		Ameet		reconfirmed		confirmed to remove		15/Oct 15:00		21/Oct 08:30

		NA		HP		SAS		shpp39		0A27		NA		0608		fdcsasp4		Ameet		reconfirmed		confirmed to remove		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A28		NA		0609		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A29		NA		060A		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2A		NA		060B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2B		NA		060C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2C		NA		060D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2D		NA		060E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2E		NA		060F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A2F		NA		0610		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A30		NA		0611		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A31		NA		0612		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A32		NA		0613		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A33		NA		0614		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A34		NA		0615		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A35		NA		0616		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A36		NA		0617		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A37		NA		0618		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A38		NA		0619		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A39		NA		061A		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3A		NA		061B		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3B		NA		061C		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3C		NA		061D		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3D		NA		061E		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3E		NA		061F		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A3F		NA		0620		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A40		NA		0621		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A41		NA		0622		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A42		NA		0623		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		151012_SASDWH_SG0122_FDC3004_RDFG110		HP		SAS		shpp39		0A43		NA		0624		fdcsasp4		Ameet		reconfirmed		reconfirmed		15/Oct 15:00		21/Oct 08:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E0		03AE		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E1		03AF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E2		03B0		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E3		03B1		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E4		03B2		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E5		03B3		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E6		03B4		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E7		03B5		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E8		03B6		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05E9		03B7		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05EA		03B8		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05EB		03B9		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05EC		03BA		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05ED		03BB		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05EE		03BC		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05EF		03BD		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F0		03BE		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F1		03BF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F2		03C0		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F3		03C1		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F4		03C2		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F5		03C3		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F6		03C4		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F7		03C5		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F8		03C6		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05F9		03C7		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FA		03C8		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FB		03C9		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FC		03CA		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FD		03CB		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FE		03CC		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		05FF		03CD		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0600		03CE		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0601		03CF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0602		03D0		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0603		03D1		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0604		03D2		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0605		03D3		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0606		03D4		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0607		03D5		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0608		03D6		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0609		03D7		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060A		03D8		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060B		03D9		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060C		03DA		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060D		03DB		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060E		03DC		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		060F		03DD		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0610		03DE		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0611		03DF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0612		03E0		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0613		03E1		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0614		03E2		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0615		03E3		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0616		03E4		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0617		03E5		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0618		03E6		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0619		03E7		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061A		03E8		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061B		03E9		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061C		03EA		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061D		03EB		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061E		03EC		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		061F		03ED		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0620		03EE		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0621		03EF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0622		03F0		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0623		03F1		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0624		03F2		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0625		03F3		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0626		03F4		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0627		03F5		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0628		03F6		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0629		03F7		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		062A		03F8		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		062B		03F9		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		062C		03FA		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		062D		03FB		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		062E		03FC		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B5C		046F		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B5D		0470		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B5E		0471		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B5F		0472		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B60		0473		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B61		0474		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B62		0475		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B63		0476		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B64		0477		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B65		0478		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B66		0479		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B67		047A		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B68		047B		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B69		047C		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6A		047D		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6B		047E		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6C		047F		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6D		0480		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6E		0481		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B6F		0482		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B75		0488		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B76		0489		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B77		048A		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B78		048B		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B79		048C		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B7A		048D		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B7B		048E		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B7C		048F		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AF7		03FF		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AF8		0400		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AF9		0401		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFA		0402		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFB		0403		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFC		0404		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFD		0405		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFE		0406		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0AFF		0407		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B00		0408		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B01		0409		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B02		040A		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B03		040B		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B04		040C		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		181012_JFP_SG0122_FDC_2804_RDFG100		AIX		JFP		saixdbp02_saixdbp04		0B05		040D		NA		fdcgcgjfpdbc51p/fdcgcgjfpdbc52p		Andrzej		reconfirmed		reconfirmed		18/Oct 20:00		21/Oct 07:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		053B		621		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		053C		622		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		053D		623		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		053E		624		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		053F		625		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		540		626		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		541		627		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		542		628		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		543		629		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		544		062A		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		545		062B		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		546		062C		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		547		062D		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		548		062E		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054A		630		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054B		631		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054C		632		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054D		633		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054E		634		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		054F		635		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		550		636		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		551		637		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		552		638		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		553		639		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		554		063A		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		555		063B		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		556		063C		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		557		063D		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		558		063E		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		559		063F		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		055A		640		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		055B		641		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		055C		642		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		055D		643		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A4		644		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A5		645		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A6		646		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A7		647		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A8		648		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05A9		649		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05AA		064A		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05AB		064B		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05AC		064C		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05AD		064D		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05AE		064E		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B0		650		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B1		651		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B2		652		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B3		653		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B4		654		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05B5		655		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C1		661		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C2		662		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C3		663		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C4		664		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C5		665		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C6		666		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C7		667		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C8		668		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05C9		669		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CA		066A		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CB		066B		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CC		066C		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CD		066D		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CE		066E		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05CF		066F		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D1		671		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D2		672		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D3		673		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D4		674		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D5		675		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D6		676		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D7		677		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D8		678		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05D9		679		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DA		067A		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DB		067B		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DC		067C		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DD		067D		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DE		067E		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		211012_AMLQS_SG0122_FDC_2804_RDFG100		AIX		AML QS 		SAIXP128		05DF		067F		NA		fdcgcgamlad01p		Abhijit		reconfirmed		reconfirmed		21/Oct 07:00		21/Oct 10:30

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0676		0605		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0677		0606		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0678		0607		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0679		0608		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067A		0609		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067B		060A		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067C		060B		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067D		060C		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067E		060D		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		067F		060E		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0680		060F		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0681		0610		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0682		0611		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0683		0612		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0684		0613		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0685		0614		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0686		0615		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0687		0616		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0688		0DAA		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0689		0DAB		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068A		0DAC		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068B		0DAD		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068C		0DAE		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068D		0DAF		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068E		0DB0		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		068F		0DB1		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0690		0DB2		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0691		0DB3		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0692		0DB4		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0693		0DB5		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0694		0DB6		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0695		0DB7		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0696		0DB8		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		151012_OTHER_SG0122_FDC2804_RDFG100		AIX		FILENET/ADS		SAIXP173		0697		0DB9		NA		fdcgcgfimaa01p		Abhijit		was not in scope		confirmed to add		15/Oct 15:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B1		02ED		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B2		02EE		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B3		02EF		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B4		02F0		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B5		02F1		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B6		02F2		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B7		02F3		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B8		02F4		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06B9		02F5		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BA		02F6		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BB		02F7		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BC		02F8		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BD		02F9		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BE		02FA		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06BF		02FB		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C0		02FC		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C1		02FD		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C2		02FE		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C3		02FF		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C4		0300		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C5		0301		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C6		0302		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C7		0303		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		AIX		Mantas PL		saixp155		06C8		0304		NA		fdcgcgamlad02p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		LINUX		Mantas PL		SLIXAP120		048F		0695		NA		fdcgcgmanla31p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		LINUX		Mantas PL		SLIXAP120		0490		0696		NA		fdcgcgmanla31p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		LINUX		Mantas PL		SLIXAP120		0491		0697		NA		fdcgcgmanla31p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00

		181012_MANTASPL_SG0122_FDC_2804_RDFG100		LINUX		Mantas PL		SLIXAP120		0492		0698		NA		fdcgcgmanla31p		Abhijit		was not in scope		confirmed to add		18/Oct 08:00		21/Oct 09:00





exec



		CEEMEA Application		GB		SG-->FDC ESTABLISH				SG/FDC SPLIT

						Planned Date/Time		Executed Date/Time		Planned Date/Time		Executed Date/Time

		REG CERT		33		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		OCI		330		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		Navigator-Russia (DB)		132		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		Poland Nav		33		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		Citiplanner		1584		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		MEMFIS 		132		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		KANA		66		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		CITI OPTIONS		99		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		URS		132		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		COPS - DB1		264		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		COPS - DB2		132		15/10 15:00		15/10 18:30		21/10 08:30		tbc

		Dataware house		13728		15/10 15:00		15/10 17:20		21/10 08:30		tbc

		SAS		6138		15/10 15:00		15/10 17:20		21/10 08:30		tbc

		JFP		4026		18/10 20:00		18/10 17:50		21/10 07:30		tbc

		AML QS 		2673		21/10 08:00		tbc		21/10 10:00		tbc

		FILENET/ADS		1122		15/10 15:00		15/10 18:30		21/10 09:30		tbc

		Mantas PL		924		18/10 08:00		18/10 16:00		21/10 09:30		tbc

		TOATL GB		31548



		STARTUS				18/10 15:00		18/10 15:00		21/10 09:30		tbc






