## General SAN Work
General SAN Workplan for Saturday - 03-11-2012
SAN Removals
Action | RFC | Request Number | Total Space GB | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices (required field) | Contact | Comments

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR/Aperture | Scheduled Date | Initials | Comments | STATUS
16190709 | OBOYLE/EAMONN | C4 - MIGRATION CLIENTS TO C4C GATEWAYS |  |  |  | Please provide CMP with replication group names, replication action required, and if COB data is required. | Issue
16165395 | BUSCH/DIRK | DS/E/YZ/N JFP PROD DB SAN REPLICATION CHANGE | 121029065311, 121101055423,121101113729 |  | TW | work prepared | approved
16212237 | Weise/Thomas | DS/E/GZ/N MODIFY SYMM AGENT CONFIG |  |  | TW | work prepared
15979974 | PETTS/NICHOLAS | DS/E/GZ/N VIOS PATCHING FRAMES FDC/RDC/WDC |  |  |  | SAN STACK Update
16129284 | PISKORZ/ADAM | DS/E/GZ/N - EQTAP2P - LIFT & SHIFT TO CGC1 | NA |  | AR | PIT team is handling CGC2 exit project | approved
16144382 | ASHER/VIPUL | ORBIFLOW SSA- NDM SERVICE RELEASE | WS11741622 & WS11741944 |  | AR | split and establish required ; split at 10am and est at 12pm | approved
16175564 | LYSZKOWSKI/JAN | DS/E/GZ/N VTM FOR CORP_CONS PROD SERVERS 1.1 | NA |  | AR | VTM patches..info only | approved
16165395 | BUSCH/DIRK | DS/E/YZ/N JFP PROD DB SAN REPLICATION CHANGE | 121029065311 |  | DB | Nov 3rd 14:00 CET and should not take longer than 2 hours. | pending SANM | Nov 3rd 14:00 CET
16180980 | HAYNES/PAUL | INSTALL NEW 5 BAY EMC VMAX (CK292603875) | 121026093509 121029090551 121029091837 121029095817 121029104834 |  | PH | SPIT covered - No BAU activity required. | pending SANM
16195399 | BALOALOA/MARIA | DS/E/GZ/N MQ MAJOR UPGRADE SECROUTER - COB | NA |  | MB | No BAU support required. | pending SANM
16194926 | BALOALOA/MARIA | DS/E/GZ/N MQ MAJOR UPGRADE SMI ZURICH - COB | NA |  | MB | No BAU support required. | pending SANM
15748818 | AMEYA/K | UPDATE QOS CONFIG - UK 65XX CATOS SAC-PAC SW | NA |  | KA | No BAU support required. | pending SANM