## General SAN Work
General SAN Workplan for Saturday - 17-08-2013
SAN Removals
Action | RFC | Request Number | Total Space GB | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices (required field) | Contact | Comments | CONFIIRMATION | Completed By:
removals | 17371528 | 130731075422 |  | RDC | EUCRDCVHSA003 | RDCHDS02 |  | 1FU, 1E | 10:00:00:00:c9:ad:6c:1d |  | 2RU,2E | 10:00:00:00:c9:ad:70:55 | 8a13,8a14,8a15 | Jakub Pawlewski |  | Confirmed | 08/24 - sv73846
decom | 17371528 | 1307180754200002 |  | rdc | tiarcdba1lnu | 3452 |  | 9B0 | 10:00:00:00:c9:72:73:f3 |  | 9B0 | 10:00:00:00:c9:72:72:0e |  | Patrick Barnett |  | Confirmed | 08/24 - sv73846
| 17371528 |  |  |  |  | rdchds_5362 |  | 5A | 10:00:00:00:c9:72:73:f3 |  | 6A | 10:00:00:00:c9:72:72:0e
decom | 17371528 | 1306060452070002 |  | fdc | TIFARMCD1FFD | 3943 |  | 3A1 | 10:00:00:00:c9:7b:8f:e2 |  | 14A0 | 10:00:00:00:c9:7b:8f:ec |  | Gavin Timmins |  | No
| 17371528 |  |  |  |  | fdchds02 |  | 2QL_2D | 10:00:00:00:c9:7b:8f:e2 |  | 1EL_1D | 10:00:00:00:c9:7b:8f:ec
removal | 17371528 | 130814063040 |  | fdc | FDCGTSSFEWD01D | fdchds_0365 |  | 8A | 10:00:00:00:c9:73:bf:df |  | 7A | 10:00:00:00:c9:73:c2:f6 | Please detach all hitachi storage currently connected to fdcgtssfewd01d as it is unused. | Krzysztof Andrzejewski |  | Confirmed | 08/24 - sv73846
removal | 17371528 | 130810044139 |  | rdc | eqfusion2p | 552 |  | 10G0 | 10000000C9EDA812 |  | 07G1 | 10000000C9EDA7D3 | ID=0203 | AP06476 |  | No
removal | 17371528 | 130810043959 |  | rdc | eqfusion1p | 552 |  | 10G0 | 10000000C9EDB8FA |  | 07G1 | 10000000C9EDA813 | ID=0203 | AP06476 |  | No
removal | 17371528 | 20130803 |  |  | Unbind from POOL on #3004 previous unmasked tdevs (SAN decoms / removals 20130803 21.5TB removal for Multifonds SAN) | [10 empty] | Confirmed | 08/24 - sv73846
FOR RE-scheduling (Customer request)
VT46501374

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester |  | RFC Description | VR/Aperture | Scheduled Date | Initials | Time | Comments | STATUS
17293628 | PETTS/NICHOLAS |  | DS/E/GZ/N VIOSERVER PATCHING P7-20RDC/16FDC |  |  | JG | 08/25/13 00:00 - 08/26/13 00:00 |  | Pending
17346420 | FINDEISEN/D |  | DATA CENTER BAU ACTIVITY CHANGE |  |  | HD | 08/19/13 00:00 - 08/24/13 23:59 | You need to provide 10 working days notice for out of hours changes requiring san support to Andy Johnstone and Nigel Chilcott. They need to agree to this work and then we can support. YOu also need to supply correctly filled in CMP's, with replication group name, with the action required. | Approved
17290579 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W25.1-EUFICCSA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 | FYI | Approved
17360710 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.5- PREP TASKS |  |  | HD | 08/23/13 18:00 - 08/24/13 08:00 | FYI | Approved
17309899 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W25.1-EUCTSUXA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 | FYI | Approved
17309678 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W25.1-EUGTSSAA |  |  | HD | 08/24/13 01:00 - 08/25/13 01:00 | FYI | Approved
17309599 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W25.1-SBWINSAM |  |  | HD | 08/24/13 01:00 - 08/25/13 01:00 | FYI | Approved
17290532 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUCTSUXA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 | FYI | Approved
17362367 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUEGVMA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17362347 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUPLBHSA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17362313 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EGWWINIM |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17328340 | MURALIDHARAN/D |  | DS/E/GZ/N REMEDIATE MQV6 EOL ACNT SRV,ZBA COB | WS17224852 - Split WS17224866 - Establish |  | HD | 08/24/13 22:00 - 08/25/13 21:59 | accservldn_3452_3544_A | Approved
17317513 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUFICCSA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17290553 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGUPSLA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17219892 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUCTSUXA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17090587 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGCPSA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17362260 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGUPSLA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17365333 | WEISE/THOMAS |  | CONTINUE CENTERA DATA MIGRATION TEKFEN - COB |  |  | JO | 08/21/13 18:00 - 08/22/13 17:59 | FYI to SAN BAU only. | Approved
17366095 | WEISE/THOMAS |  | SAN SWITCH OS UPGRADE - FDC/RDC JADE |  |  | JO | 08/22/13 18:00 - 08/22/13 23:59 | FYI to SAN BAU only. | Approved
17376177 | KEEFE/R |  | DS/E/GZ/ALL22/N VTM LINUX 13.01.02 |  |  | HD | 08/22/13 18:00 - 08/22/13 23:59 | VTM Patching - zhctipgs02, zhcticgs02, zhctipgs05 & zhcticgs05 | Approved
17375858 | MCBRIDE/J |  | DCSM SERVER DECOMMISSIONS |  |  | HD | 08/23/13 20:00 - 08/25/13 23:00 |  | Approved
17376835 | PANTOL/ARTUR |  | DS/E/GZ/N VSE 8.8 DEPLOYMENT EWCC P.4 |  |  | HD | 08/24/13 20:01 - 08/25/13 23:59 | Deploying McFee AV. | Approved
17375666 | JABLONSKI/B |  | DS/E/GZ/N: CAPE - ADD SAN LUNS TO VOLUME GRP |  |  | HD | 08/24/13 08:00 - 08/24/13 23:59 | Deploying already provisioned SAN luns to Unix. Support only if issues | Approved
17374940 | WYSOKINSKI/P |  | DS/E/GZ/N - HP DMA AGENT INSTALLATION |  |  | HD | 08/24/13 00:00 - 08/24/13 23:59 | The SAN team dont have an DB servers, why are we on this change. Please advise, else remove us from the approvers | Issue
17372313 | MADANI/DJILALI |  | CLEARVISION - EUREX SG FAILBACK TO FDC | WS17503116 - Failback |  | HD | 08/24/13 09:00 - 08/24/13 18:00 | fdcgdsgwy_EUR_2804_3286_A12 | Approved
17371528 | PAWLEWSKI/JAKUB |  | DS/EMEA/GZ/VM14/N/SAN SAN STORAGE – RECLM |  |  | HD | 08/24/13 14:00 - 08/24/13 18:00 | Sent email to Phillipines guys to ask if removal Aprture of HDS storage is okay 130731075422
17318501 | ZUKOWSKI/MAREK |  | DS/E/GZ/N - GCETDSYB1P/1C STORAGE MIGRATION |  |  | HD | 08/24/13 06:00 - 08/25/13 05:00 | FYI< HDS Tech Refresh | Approved
17372426 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUCTSUXA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17371884 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGCPSA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17371822 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGUPSLA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17338432 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUGLUNXA |  |  | HD | 08/24/13 08:00 - 08/25/13 08:00 |  | Approved
17338374 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUCTSUXA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17309852 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUCTOSAA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17362260 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W28.1-EUGUPSLA |  |  | HD | 08/24/13 01:00 - 08/25/13 23:59 |  | Approved
17362347 | DOSHI/NIK |  | EMEA SAN-HDS TECH REFRESH-W26.1-EUPLBHSA |  |  | HD | 08/24/13 14:00 - 08/25/13 14:00 |  | Approved
17121381 | RULEWICZ/MARCIN |  | DS/E/GZ/N - GCOPSAP1P/C-GZ STORAGE MIGRATION |  |  | AR | 08/24/13 07:00 - 08/24/13 23:00 | FYI< HDS Tech Refresh | Approved
17372053 | KLOS/ZBIGNIEW |  | SAN SWITCH OS UPGRADE - FDC/RDC RUBY |  |  | ZK | 08/25/13 09:00 - 08/25/13 18:00 | PIT change, FYI only | Approved
List of hardware for decommissioning.
Timelines for activities.
Tracking |  | Device Name | Building