## General SAN Work
General SAN Workplan for Saturday - 03-11-2012
SAN Removals
Action | RFC | Request Number | Total Space GB | Site | Hostname / Zone Alias | Symm # | Sw1 / Prt1 | FA | HBA WWN | Sw2 /Prt2 | FA | HBA WWN | Devices (required field) | Contact | Comments
decom |  | WS11602736 |  |  | fidatawaredb1d
decom |  | WS11602736 |  |  | fidatawaredb1u
decom |  | WS11602736 |  |  | fitetrisdb1d
decom |  | WS11602736 |  |  | fitetrisdb2d
removal |  | 121031080756 |  |  | RDCCTIFFNWA04C
removal |  | 121031080654 |  |  | RDCCTIFFNWA04U
removal |  | 121031074439 |  |  | FDCCTIFFNWA04P
decom |  | 1210300658221 |  |  | gtsncsap11c
decom |  | 1210300708332 |  |  | tsncsap12c
decom |  | 1210091243331 |  |  | FDCGTSMFAWA06U
decom |  | 121019115735 |  |  | GTBPMDB1P
decom |  | 121019120246 |  |  | GTBPMAP2P
decom |  | 121019120543 |  |  | GTBPMAP3P
removal |  | 121030050610 |  |  | fdcgcgtibla17p | [7 empty] | 141f, 1420, 1421, 1422, 1423, 1424 |  | Allocate these luns 6*33G Cluster disk with SCSI3 PR to server fdcgcgtibla63p/73p server
removal |  | 121030044113 |  |  | rdcgcgtibla17U | [7 empty] | 2249:224E,224F:2251

## Extra Work
Extra Work
All planned RFC's must be in an approved state and have a EUDSANNA approver to be valid.
Only Approve RFC's for COB if accompanied by a valid VR which includes SRDF Group Name and required SRDF action
RFC | Requester | RFC Description | VR/Aperture | Scheduled Date | Initials | Comments | STATUS
15979974 | PETTS/NICHOLAS | DS/E/GZ/N VIOS PATCHING FRAMES FDC/RDC/WDC |  |  |  | SAN STACK Update
16129284 | PISKORZ/ADAM | DS/E/GZ/N - EQTAP2P - LIFT & SHIFT TO CGC1 | NA |  | AR | PIT team is handling CGC2 exit project | approved
16144382 | ASHER/VIPUL | ORBIFLOW SSA- NDM SERVICE RELEASE | WS11741622 & WS11741944 |  | AR | split and establish required ; split at 10am and est at 12pm | approved
16175564 | LYSZKOWSKI/JAN | DS/E/GZ/N VTM FOR CORP_CONS PROD SERVERS 1.1 | NA |  | AR | VTM patches..info only | approved
16165395 | BUSCH/DIRK | DS/E/YZ/N JFP PROD DB SAN REPLICATION CHANGE | 121029065311 | 2012-11-03 | DB | Nov 3rd 14:00 CET and should not take longer than 2 hours. | pending SANM | Nov 3rd 14:00 CET
16180980 | HAYNES/PAUL | INSTALL NEW 5 BAY EMC VMAX (CK292603875) | 121026093509 121029090551 121029091837 121029095817 121029104834 | 11/03/12-11/04/12 | PH | SPIT covered - No BAU activity required. | pending SANM
16195399 | BALOALOA/MARIA | DS/E/GZ/N MQ MAJOR UPGRADE SECROUTER - COB | NA | 2012-11-03 | MB | No BAU support required. | pending SANM
16194926 | BALOALOA/MARIA | DS/E/GZ/N MQ MAJOR UPGRADE SMI ZURICH - COB | NA | 2012-11-03 | MB | No BAU support required. | pending SANM
15748818 | AMEYA/K | UPDATE QOS CONFIG - UK 65XX CATOS SAC-PAC SW | NA | 2012-11-03 | KA | No BAU support required. | pending SANM